## Guidance
Guidance for completing DPS for a Radar and Communications system.
This guidance aims to help you complete the DPS for a Radar and Communications system.
The template (along with the mapping documentation from the WBS and the method of apportionment of costs) should be returned alongside the Contract Notification Report (CNR) and later the Interim Contract Report (ICR) and Contract completion report (CCR).
The DPS is split into 4 level of items and the relationship is broken down as follows:
Level 1 | Level 2 | Level 3 | Level 4
(1) Radar and Communications system
(1.1) Main hardware and software component
|  | (1.1.1) Hardware / Software Component Subsystem | (1.1.1.1) - (1.1.1.6)
|  | (1.1.2) Hardware / Software Component Software Release | (1.1.2.1) - (1.1.2.4)
|  | (1.1.3) Hardware / Software Product Integration, Assembly, Test and Checkout | No level 4
|  | (1.1.4) Other Main hardware/software component | No level 4
| (1.2) Control and communications | (1.2.1) Control & Communication Integration, Assembly, Test, and Checkout | No level 4
|  | (1.2.2) Navigation Systems & equipments | No level 4
|  | (1.2.3) Internal Communications | No level 4
|  | (1.2.4) Main Machinery Control Systems | No level 4
|  | (1.2.5) Weapons Control Electrics | No level 4
|  | (1.2.6) Protective Systems | No level 4
|  | (1.2.7) External Communication Systems | No level 4
|  | (1.2.8) Active / Passive Sonar Systems | No level 4
|  | (1.2.9) Sensor Systems | No level 4
|  | (1.2.10) Other | No level 4
| (1.3) Platform Integration, Assembly, Test and Checkout | (1.3.1) - (1.3.8) | No level 4
| (1.4) System engineering | No level 3 | No level 4
| (1.5) Program management | No level 3 | No level 4
| (1.6) Research and development | No level 3 | No level 4
| (1.7) System test and evaluation | (1.7.1) - (1.7.6) | No level 4
| (1.8) Training | (1.8.1) - (1.8.4) | No level 4
| (1.9) Data | (1.9.1) - (1.9.6) | No level 4
| (1.10) Specialist support equipment | (1.10.1) - (1.10.3) | No level 4
| (1.11) Common support equipment | (1.11.1) - (1.11.3) | No level 4
| (1.12) Operational/site activation | (1.12.1) - (1.12.6) | No level 4
| (1.13) Industrial facilities | (1.13.1) - (1.13.4) | No level 4
| (1.14) Initial spares and repairs | No level 3 | No level 4
In service contract specific tasks | (1.15) On tools manpower - maintenance,rectifications & repair | (1.15.1) | (1.1.15.1) - (1.15.1.3)
| (1.16) Consumables/fungibles | No level 3 | No level 4
| (1.17) Packing, Handling, Storage and Transportation | No level 3 | No level 4
| (1.18) Non touch manpower | (1.18.1) Asset management | (1.18.1.1) - (1.18.1.5)
|  | (1.18.2) Engineering & safety | (1.18.2.1) - (1.18.2.5)
|  | (1.18.3) Post design service | (1.18.3.1) - (1.18.3.5)
|  | (1.18.4) Post design service (Manpower) | (1.18.4.1) - (1.18.4.8)
|  | (1.18.5) In service training | (1.18.5.1) - (1.18.5.3)
|  | (1.18.6) Disposal / Waste Management | No level 4
|  | (1.18.7) Other Maintenance Management activity (Specify) | No level 4
| (1.19) Specialist Equipment | (1.19.1) Rigs, Jigs and Support Equipment (all-up) | (1.19.1.1) - (1.19.1.3)
|  | (1.19.2) Testing and Diagnostics | (1.19.2.1) - (1.19.2.3)
|  | (1.19.3) Specialist Facilities | (1.19.3.1) - (1.19.3.5)
|  | (1.19.4) Individual or Small Scale Modifications | No level 4
|  | (1.19.5) Specialist IT | (1.19.5.1) - (1.19.5.4)
|  | (1.19.6) Other Specialist Equipment (Specify) | No level 4
General
This template has been designed to assist you in apportioning the costs associated with either the construction and/or in-service support of a Radar and Communications system.
The template has also been designed to help you complete the DPS input tab and therefore the price tab on the CNR (and later the ICR and CCR) .
By completing this template first, you will find it easier to translate the relevant DPS levels, descriptors and costs to the CNR, and will also help explain where costs have been allocated.
You should note that the 'descriptor' section on the CNR DPS input tab must be manually completed - the form does not allow copy and paste.
This template should be completed and returned alongside any mapping documents that you may use and your existing work breakdown structure.
The template should be completed in accordance with the SSRO guidance: DPS principles which can be found by clicking on the document to the right.
Apportionment of costs
Costs must add up to the total contract value excluding profit. The DPS, being a breakdown of the total contract value excluding profit, must include all indirect as well as direct costs.
Construction costs (this includes research, development and build) should be entered in column J. The figures automatically format to 'millions' and 3.d.p.
Where there are no costs, or a specific level of the DPS does not apply, this should be left blank.
Where there is a cost and there is no appropriate DPS level, the 'other' row should be used and an explanation entered in the 'additional information' column.
The costs at a subordinate level should total the costs at the superior level, as detailed in the principles document.
Level 1 of the DPS must total 100 per cent of the contract value excluding profit and the breakdown of each subsequent level must total the preceding level.
The 'price tab' of the CNR allows you to split recurring and non recurring costs pre DPS element.
The costs do not auto-calculate so can you please ensure the costs for the relevant level add up correctly.
The section headed 'In service contract specific tasks' does not have to be completed if there is no in-service element.
Full details of the approach to apportioning costs can be found in the SSRO guidance: DPS Principles document.
Use of 'other'
When the description/category is not applicable, an 'other' row is present at level 4 to capture additional information.
At Levels 2,3 and 4, the 'other' section is contained within the descriptor and not as a separate row. Any relevant detail should be added in 'additional information'.
The 'additional information' box should be completed whenever an 'other' description is needed.
Please do not add any additional rows to the spreadsheet. Any additional detail should be captured in the 'additional information' box at each level.
Where this is no specific 'other' row, the relevant information should be put in the additional information box.
Use of the 'other' category is to be used in the following circumstances:
(1) when there is no appropriate description available within the DPS;
(2) for any contingent cost included in the contract; or
(3) where a small proportion of costs would be difficult to apportion to categories listed in the DPS; and
(4) where there is no specific 'other' row (please place a description in the 'additional information' column).
In service costs
Where there is an in-service element, the costs should be entered in column J.
DPS level 1.16 onwards relate specifically to in-service costs.
Some in-service costs may be better suited to match DPS levels 1.1 - 1.15.
The costs at a subordinate level should total the costs at the superior level, as detailed in the principles document.
The costs do not auto-calculate so can you please ensure the costs for the relevant levels add up correctly.
If the contract is construction specific but includes and in-service element, please complete columns J and K for all level (where applicable).
If the contract is for in-service support/maintenance only, please complete DPS levels 1.15 onwards and any previous level you consider appropriate.
Metrics
We have included relevant output metrics (column H), where possible, but you may add any metrics you use in the boxes where appropriate.
The same metrics should be entered on the 'metrics' tab on the CNR (and later the ICR and CCR)
If you have any questions please contact us at
helpdesk@SSRO.gov.uk
Version control
V1: Published 14 December 2015

## Radar DPS
DPS codes | [6 empty] | Output metrics |  | Costs (£m)
Level 1 | Level 2 | Level 3 | Level 4 |  | Descriptor | Additional information | Metric | Figure | In service cost | Construction cost
1 | Radar and communications system |  |  |  | The complex of equipment (hardware/software), data, services, and facilities required to develop and produce an electronic system capability such as a command and control system, radar system, communications system, information system, sensor system, navigation/guidance system, electronic warfare system, support system.
| 1.1 | Main Hardware / Software Component) |  |  | The hardware and software used to accomplish the purpose of the defence materiel item. This DPS element includes the design, development, and production of complete units (i.e., the prototype or operationally configured units, which satisfy the requirements of their applicable specifications, regardless of end use) and is comprised of the sub elements listed below. Includes, for example:
a. All integration, assembly, test and checkout, as well as all technical and management activities associated with individual hardware/software elements
b. Integration, assembly, test and checkout associated with the overall Hardware / Software Component. when the electronic system comprises several Hardware / Software Components, each Hardware / Software Component will be listed separately at Level 2
c. All whole and partial prime contractor, subcontractor, and vendor breadboards, brass boards, and qualification test units
d. The design, development and production of complete units (i.e., the prototype or operationally configured units, which satisfy the requirements of their applicable specification(s), regardless of end use)
e. Factory special test equipment, special tooling, and production planning required to fabricate the Hardware / Software Component
Excludes, for example:
a. Only those "less than whole" units (e.g., test, spares, etc.) Consumed or planned to be consumed in support of system level tests
b. Duplicate or modified factory special test equipment delivered to the Government for depot repair (should be included in the specific support equipment element)
Any other software or hardware component
|  | 1.1.1 | Hardware / Software Component Subsystem |  | The hardware and software components of the specific electronic subsystem. Includes, for example:
a. All associated special test equipment, special tooling, production planning, and all technical and management activities
b. Software components, consisting of the applications and system software required to direct and maintain the specific electronic subsystem
c. All in-plant integration, assembly, test, and checkout of hardware components and software into an electronic subsystem, including the subsystem hardware and software integration and test
d. Interface materials and parts required for the in-plant integration and assembly of other Level 4 components into the electronic subsystem and all materials and parts or other mating equipments furnished by/to an integrating agency or contractor
e. Cables, conduits, connectors, shelters, and other devices associated with the operational electronic subsystem
f. The design, development, production, and assembly efforts to provide each electronic subsystem as an entity
Excludes, for example:
a. All effort directly associated with the remaining Level 3 DPS elements and the integration, assembly, test and checkout of these elements into the Hardware / Software Component
NOTE: All software that is an integral part of any specific equipment system, subsystem or component specification or specifically designed and developed for system test and evaluation should be identified with that system, subsystem, component or effort. It may be appropriate to collect lower level information when it exists. In such cases, the following structure and definitions should be used:
Including:
Hardware / Software Component Subsystem Hardware (Specify)
Hardware / Software Component Subsystem Software Release (Specify)
Other
|  |  | 1.1.1.1 | Hardware / Software Component Subsystem Hardware | The hardware and associated resource components of the specific electronic/automated software subsystem.
|  |  | 1.1.1.2 | Hardware / Software Component Subsystem Software Release | The resources associated with the Hardware / Software Component subsystem software that is associated with the Hardware / Software Component subsystem for release 1…n. A software release is an aggregate of one or more CSCIs that satisfies a specific set or subset of requirements. When incremental, spiral, or other software development methods are used, multiple releases may be necessary to meet program requirements. A release is a separately tested and delivered product. Within releases are CSCIs. When a release is complete, a portion or all of one or more CSCIs will be completed. Therefore, a CSCI may appear in one or more releases, but will be successively more functional as each release is completed. Includes, for example:
a. Software product engineering,
b. Computer Software Configuration Item (CSCI) 1…n
c. Subsystem Integration, Assembly, Test and Checkout.
|  |  | 1.1.1.3 | Software Product Engineering | All of the resources associated with the Hardware / Software Component software product engineering efforts. Software product engineering is focused on process maturity and continuous improvement. Sound software product engineering is a systematic framework, which breaks down the software development process by relating each level to a knowledge domain and localising exactly on those qualities that become visible in that knowledge domain.
|  |  | 1.1.1.4 | Computer Software Configuration Item (CSCI) | An aggregation of software or any of its discrete portions that satisfies an end use function and has been designated by the Government or Contractor, if the Government did not specify, for configuration management. CSCIs are the major software products of a system acquisition, which are developed in accordance with standard MOD or commercial practices and processes. Includes, for example:
a. Software requirements
b. Software architecture and design
c. Software code and unit test
d. Software Integration
e. Software qualification testing
f. Commercial off the Shelf (COTS)/Government off the Shelf (GOTS) approach
g. COTS/GOTS component identification
h. COTS/GOTS assessment and selection
i. COTS/GOTS prototyping
j. COTS/GOTS glue code development
k. COTS/GOTS tailoring and configuration
NOTE: When software development is accomplished, items (a) through (e) are typical development activities. When COTS/GOTS is to be used and integrated, items (f) through (i) are typical integration activities.
|  |  | 1.1.1.5 | Subsystem Integration, Assembly, Test and Checkout | The resources specifically related to evaluating the CSCIs and hardware operation as a subsystem. Includes, for example:
a. All resources necessary to integrate the subsystem components as a complete subsystem
b. Subsystem integration management
c. Requirements definition, planning and scheduling
d. Development of integration plans and procedures
e. Integration test preparations, conduct and teardown and review, analysis and documentation of subsystem integration results.
|  |  | 1.1.1.6 | Other
|  | 1.1.2 | Hardware / Software Component Software Release |  | The resources associated with Hardware / Software Component subsystem software that is not associated with the Hardware / Software Component subsystem (i.e., Distributed SW environment) for release (1...n). Includes, for example:
a. Software product engineering,
b. Computer Software Configuration Item (CSCI)
c. Subsystem Integration, Assembly, Test and Checkout
|  |  | 1.1.2.1 | Software Product Engineering | All of the resources associated with the Hardware / Software Component software product engineering efforts. Software product engineering is focused on process maturity and continuous improvement. Sound software product engineering is a systematic framework, which breaks down the software development process by relating each level to a knowledge domain and localising exactly on those qualities that become visible in that knowledge domain.
|  |  | 1.1.2.2 | Computer Software Configuration Item (CSCI) | An aggregation of software or any of its discrete portions that satisfies an end use function and has been designated by the Government or Contractor, if the Government did not specify, for configuration management. CSCIs are the major software products of a system acquisition, which are developed in accordance with standard MOD or commercial practices and processes. Includes, for example:
a. Software requirements
b. Software architecture and design
c. Software code and unit test
d. Software integration
e. Software qualification testing
f. Commercial off the Shelf (COTS)/Government off the Shelf (GOTS) approach
g. COTS/GOTS component identification
h. COTS/GOTS assessment and selection
i. COTS/GOTS prototyping
j. COTS/GOTS glue code development
k. COTS/GOTS tailoring and configuration
|  |  | 1.1.2.3 | Subsystem Integration, Assembly, Test and Checkout | The resources specifically related to evaluating the CSCIs and hardware operation as a subsystem. Includes, for example:
a. All resources necessary to integrate the subsystem components as a complete subsystem
b. Subsystem integration management
c. Requirements definition, planning and scheduling
d. Development of integration plans and procedures
e. Integration test preparations, conduct and teardown and review, analysis and documentation of subsystem integration results
|  |  | 1.1.2.4 | Other
|  | 1.1.3 | Hardware / Software Product Integration, Assembly, Test and Checkout |  | This DPS element contains all of the resources in order to perform integration, assembly, test, and check out of the Hardware / Software Component. This is the process of combining and evaluating CSCIs and Hardware of a system or segment of a system that have undergone individual CSCI and hardware qualification test.
|  | 1.1.4 | (1.1.4) Other Main hardware/software component
| 1.2 | Control and Communication |  |  | Mission equipment on board the platform which is primarily electronic in nature. Includes, for example:
a. Navigation Systems b. Internal Communications c. Platform & Main Machinery Control Systems d. Weapon Control Systems e. Platform Protective Systems f. External Communications Systems g. Other (please specify)
|  | 1.2.1 |  | Control & Communication Integration, Assembly, Test, and Checkout | This element includes all effort of technical and functional activities associated with the design, development, and production of mating surfaces, structures, equipment, parts, materials, and software required to assemble and test the Control and Communications parts and subsystems (hardware/software) elements.
|  | 1.2.2 |  | Navigation Systems & equipments | Includes, for example:
a. Gyro and Other Compasses b. Inertial Navigation System (SINS) c. Navigation Aids and Direction Finding Equipment d. Log e. Meteorology and Oceanographic Systems f. Navigation Radar g. Viewing Devices h. Chronometers i. Plotting and Chart Tables j. Navigation Lights, Etc.
|  | 1.2.3 |  | Internal Communications | Includes, for example:
a. Broadcasts b. Internal Telephone Network and Telephones c. Sound Reproduction Equipment (SRE) d. Voice and Pneumatic Tubes e. Television, Radio and Cinema Equipment f. Alarms and Warnings g. Chemical, Biological, Radiological and Nuclear (CBRN) Warning Systems h. Engine Telegraph and Propeller Orders i. Rudder Angle Indicators j. Information Systems
|  | 1.2.4 |  | Main Machinery Control Systems | Includes, for example:
a. Platform Control Console (PCC) b. Systems Consoles c. Command Console d. Navigation Control System e. Integrated Navigation Systems f. Moveable Stabilisers and Control System g. Hydrofoil Control System h. Tank Stabilisation Systems (Active and Passive) i. Machinery Control System j. Integrated Platform Management Systems
|  | 1.2.5 |  | Weapons Control Electrics | Includes, for example:
a. Surface/Air Weapon Control Systems b. Surface/Surface Weapon Control Systems c. Surface/Anti-Submarine Weapon Control Systems d. Submerged Launched (Non-Air Flight) Systems e. Submerged Launched (Air Flight) Systems f. Weapon and Surveillance Radars g. Sonars h. Centralised Weapon Control Systems i. Electronic Warfare Systems (EW) j. Control Systems for Autonomous Craft
|  | 1.2.6 |  | Protective Systems | Includes, for example:
a. Degaussing System b. Cathodic Protection System c. Sacrificial Anodes
|  | 1.2.7 |  | External Communication Systems | Includes, for example:
a. Radio Communication Systems b. Underwater Telephones and Echo Sounders c. Visual Signalling Equipment d. Audio Signalling Equipment e. Satellite Communication Systems
|  | 1.2.8 |  | Active / Passive Sonar Systems | Includes, for example:
1. Sonar, all sonar and echo sounding systems (active & passive), including transducer castings, transducers & cabinets, sonar aural recording, cavitation detection equipment and bathythermograph equipment. Also includes all fittings for towed array, GRP Dome fairing and micro puff windows. Excludes; pressure hull glands, cabling, chilled water cooling system, structural fittings for towed array (if built in stabiliser).
|  | 1.2.9 |  | Sensor Systems | Includes, for example:
PT / Contractor input required to populate with Sensor Generic Descriptor / Definition.
|  | 1.2.10 |  | Other systems
| 1.3 | Platform Integration, Assembly, Test and Checkout |  |  | The effort involved in providing technical and engineering services to the platform manufacturer or integrator during the installation and integration of the Hardware / Software Component into the host system. Includes, for example:
a. Labour required to analyse, design, and develop the interfaces with other host vehicle subsystems
b. Drawing preparation and establishment of equipment requirements and specifications
c. Technical liaison and coordination with the military services subcontractors, associated contractors, and test groups
Excludes, for example:
a. All integration effort not directly associated with the host vehicle and management liaison with the military services, subcontractors, and associated contractors
| 1.4 | System Engineering |  |  | The technical and management efforts of directing and controlling a totally integrated engineering effort of a system or program. Includes, for example:
a. Effort to define the system and the integrated planning and control of the technical program efforts of design engineering, specialty engineering, production engineering, and integrated test planning
b. Effort associated with developing the Systems Engineering plan
c. Effort to transform an operational need or statement of deficiency into a description of system requirements and a preferred system configuration
d. Technical planning and control effort for planning, monitoring, measuring, evaluating, directing, and re-planning the management of the technical program
e. All programs, where applicable; value engineering, configuration management, Human Systems Integration (Human factors engineering; Personnel; Habitability; Manpower; Training; Environment, Safety and Occupational Health; Survivability), vulnerability, maintainability, reliability, standardisation, system analysis, logistic support analysis, etc.
f. Technical baseline management and event based technical reviews with independent subject matter expertise participation
g. Cross product IPT integration
h. Survivability/vulnerability analysis
i. System of Systems (SoS) and System Level Architecting, modelling and simulation, verification and validation and external interface definition and management
Excludes, for example:
a. Actual design engineering and the production engineering directly related to the DPS element with which it is associated
| 1.5 | Program Management |  |  | The business and administrative planning, organising, directing, coordinating, controlling, and approval actions designated to accomplish overall program objectives, which are not associated with specific hardware elements and are not included in systems engineering. Includes, for example:
a. Cost, schedule, performance measurement management, warranty administration, contract management, data management, vendor liaison, subcontract management, etc.
b. Support element management, defined as the logistics tasks management effort and technical control, and the business management of the support elements. The logistics management function encompasses the support evaluation and supportability assurance required to produce an affordable and supportable defence materiel system.
c. Planning and management of all the functions of logistics. Examples are: maintenance support planning and support facilities planning; other support requirements determination; support equipment requirements determination; supply support; packaging, handling, storage, and transportation; provisioning requirements determination and planning; training system requirements determination; computer resource determination; organisational, intermediate, and depot maintenance determination management; and data management
| 1.6 | Research and development |  |  | All work directed towards the innovation, introduction, and improvement of products and processes to develop the equipment type prior to testing (which is covered in 1.7) System test and evaluation
| 1.7 | System Test and Evaluation |  |  | The use of pilot, prototype, production, or specifically fabricated hardware/ software to obtain or validate engineering data on the performance of the system during the developmental phase of the program. It also includes all effort associated with the development of any specialised tools or data in support of the system level test program. Includes, for example:
a. Detailed planning, conduct, support, data reduction and reports (excluding the contract data requirements list data) from such testing, and test articles that are functionally configured to represent and test subsystems/components of the defence materiel end item being developed or produced
b. Design and production of models, specimens, fixtures and instrumentation
NOTE: Test articles that are functionally configured to represent and test the complete defence materiel end item being developed or produced, are excluded from this DPS element.
Excludes, for example:
a. All formal and informal testing up through the subsystem level, which can be associated with the hardware/software element acceptance testing
NOTE: These excluded efforts are to be included with the appropriate hardware or software elements.
|  | 1.7.1 | Development Test and Evaluation |  | It includes test and evaluation conducted to:
a. Demonstrate that the engineering design and development process is complete
b. Demonstrate that the design risks have been minimised
c. Demonstrate that the system will meet specifications
d. Estimate the system's military utility when introduced
e. Determine whether the engineering design is supportable (practical, maintainable, safe, etc.) for operational use
f. Provide test data with which to examine and evaluate trade-offs against specification requirements, life cycle cost, and schedule
g. Perform the logistics testing efforts to evaluate the achievement of supportability goals, the adequacy of the support package for the system, (e.g., deliverable maintenance tools, test equipment, technical publications, maintenance instructions, and personnel skills and training requirements, etc.)
Includes, for example:
a. All contractor/system developer in-house effort
b. All programs, where applicable; models, tests and associated simulations (e.g., such as wind tunnel, static, drop, and fatigue); integration ground tests; test bed aircraft and associated support; qualification test and evaluation, development flight test, test instrumentation, environmental tests, ballistics, radiological, range and accuracy demonstrations, test facility operations, test equipment (including its support equipment), chase and calibrated pacer aircraft and support thereto, and logistics testing
c. For aircraft; avionics integration test composed of the following:
1. Test bench/laboratory, including design, acquisition, and installation of basic computers and test equipments that will provide an ability to simulate in the laboratory the operational environment of the avionics system/subsystem
2. Air vehicle equipment, consisting of the avionics and/or other air vehicle subsystem modules that are required by the bench/lab or flying test bed in order to provide a compatible airframe avionics system/subsystem for evaluation purposes
3. Flying test bed, including requirements analysis, design of modifications, lease or purchase of test bed aircraft, modification of aircraft, installation of avionics equipment and instrumentation, and checkout of an existing aircraft used essentially as a flying avionics laboratory
4. Avionics test program, consisting of the effort required to develop test plans/procedures, conduct tests, and analyse hardware and software test results to verify the avionics equipments' operational capability and compatibility as an integrated air vehicle subsystem
5. Software, referring to the effort required to design, code, de-bug, and document software programs necessary to direct the avionics integration test
d. For engines: engine military qualification tests and engine preliminary flight rating tests
e. For sea systems: model basin, hydrostatic, fatigue, shock, special sea tests and trials, etc., trials agenda preparation, data collection and analysis; dock and sea trials; and hull vibration survey elements
f. For missiles: test articles such as Inert Measurement Vehicles, Launch Separation Vehicles, Separation and Control Test Vehicles, Boost Test Vehicles
g. For ordnance: test articles such as Ballistic Test rounds, Inert Measurement rounds, Dummy rounds, Launch Separation rounds, etc.
|  | 1.7.2 | Operational Test and Evaluation |  | The test and evaluation conducted by agencies other than the developing command to assess the prospective system's military utility, operational effectiveness, operational suitability, logistics supportability (including compatibility, inter-operability, reliability, maintainability, logistic requirements, etc.), cost of ownership, and need for any modifications. Includes, for example:
a. Initial operational test and evaluation conducted during the development of a system
b. Such tests as system demonstration, flight tests, sea trials, mobility demonstrations, on-orbit tests, spin demonstration, stability tests, qualification operational test and evaluation, etc., and support thereto, required to prove the operational capability of the deliverable system
c. Contractor support (e.g., technical assistance, maintenance, labour, material, etc.) Consumed during this phase of testing
d. Logistics testing efforts to evaluate the achievement of supportability goals and the adequacy of the support for the system (e.g., deliverable maintenance tools, test equipment, technical publications, maintenance instructions, personnel skills and training requirements, and software support facility/environment elements)
|  | 1.7.3 | Mock-ups / System Integration Labs (SILs) |  | The design engineering and production of system or subsystem mock-ups that have special contractual or engineering significance or that are not required solely for the conduct of one of the above elements of testing. SILs are often used in lieu of (or in addition to) mock-ups. SILs are risk reduction facilities where software and hardware can be developed, integrated, tested and evaluated for both stand alone functionality and/or interoperability prior to being fielded. Includes, for example:
a. Hardware/Lab Equipment
b. SIL Software (written to simulate the operating environment or written to operate the SIL)
|  | 1.7.4 | Test and Evaluation Support |  | The support elements necessary to operate and maintain, during test and evaluation, systems and subsystems, which are not consumed during the testing phase and are not allocated to a specific phase of testing. Includes, for example:
a. Repairable spares, repair of repairables, repair parts, consumables, warehousing and distribution of spares and repair parts, test and support equipment, test bed vehicles, drones, surveillance aircraft, tracking vessels, contractor technical support
Excludes, for example:
a. Operational and maintenance personnel, special fixtures, special instrumentation, etc., that are utilised and/or consumed in a single element of testing and that should be included under that element of testing
|  | 1.7.5 | Test Facilities |  | Test Facilities. The special test facilities required for performance of the various developmental tests necessary to prove the design and reliability of the system or subsystem. Includes, for example:
a. Test tank test fixtures, propulsion test fixtures, white rooms, test chambers
Excludes, for example:
a. Brick and mortar-type facilities identified as industrial facilities
|  | 1.7.6 | Other System test and evaluation
| 1.8 | Training |  |  | Deliverable training services, devices, accessories, aids, equipment, and parts used to facilitate instruction through which personnel will learn to operate and maintain the system with maximum efficiency. Includes, for example:
a. All effort associated with the design, development, and production of deliverable training equipment and its associated software as well as the execution of training services
Excludes, for example:
a. Overall planning, management, and task analysis function inherent in the DPS element systems engineering/program management
|  | 1.8.1 | Equipment |  | Distinctive deliverable end items of training equipment, assigned by either a contractor or military service, required to meet specific training objectives. Includes, for example:
a. Operational trainers, maintenance trainers, and other items such as cutaways, mock-ups, and models (e.g. Operational Instructional Equipment, Maintainer Instructional Equipment)
|  | 1.8.2 | Services |  | Deliverable training services, accessories, and aids necessary to accomplish the objectives of training. Includes, for example:
a. Training course materials; contractor-conducted training (in-plant and service training); and the materials and curriculum required to design, execute, and produce a contractor developed training program. (e.g. Operator Instructional Software, Maintainer Instructional Software)
b. Materiel, courses, and associated documentation (primarily the computer software, courses and training aids)
Excludes, for example:
a. Deliverable training data associated with the DPS element support data
|  | 1.8.3 | Facilities |  | The special construction necessary to accomplish training objectives. Includes, for example:
a. Modification or rehabilitation of existing training facilities and infrastructure used to accomplish training objectives
Excludes, for example:
a. Installed equipment used to acquaint the trainee with the system or establish trainee proficiency
b. The brick and mortar-type facilities identified as industrial facilities
|  | 1.8.4 | Other Training
| 1.9 | Data |  |  | The deliverable data required by the contract. Includes, for example:
a. Only such effort that can be reduced or avoided if the data item is eliminated
b. Government-specific data; acquiring, assembling, reproducing, packaging and shipping the data
c. Transforming data into Government format, reproducing and shipping data identical to that used by the contractor but in a different format
|  | 1.9.1 | Technical Publications |  | Technical data, providing instructions for installation, operation, maintenance, training, and support, formatted into a technical manual. Data may be presented in any form regardless of the form or method of recording. Technical orders that meet the criteria of this definition may also be classified as technical manuals. Includes, for example:
a. Operation and maintenance instructions, parts lists or parts breakdown, and related technical information or procedures exclusive of administrative procedures
b. Data item descriptions
|  | 1.9.2 | Engineering Data |  | Recorded scientific or technical information (regardless of the form or method of recording) including computer software documentation. Engineering data defines and documents an engineering design or product configuration (sufficient to allow duplication of the original items) and is used to support production, engineering and logistics activities. Includes, for example:
a. All final plans, procedures, reports, and documentation pertaining to systems, subsystems, computer and computer resource programs, component engineering, operational testing, human factors, reliability, availability, and maintainability, and other engineering analysis
b. Technical data package (re-procurement package), which includes all engineering drawings, associated lists, process descriptions, and other documents defining physical geometry, material composition, and performance procedures
Excludes, for example:
a. Computer software or financial, administrative, cost or pricing, or management data or other information incidental to contract administration
|  | 1.9.3 | Management Data |  | The data items necessary for configuration management, cost, schedule, contractual data management, program management, etc., required by the Government. Includes, for example:
a. Contractor cost reports, cost performance reports, contract funds status reports, schedules, milestones, networks, integrated support plans
|  | 1.9.4 | Support Data |  | The data items designed to document support planning in accordance with functional categories. Includes, for example
a. Supply; general maintenance plans and reports; training data; transportation, handling, storage, and packaging information; facilities data; data to support the provisioning process and all other support data; and software supportability planning and software support transition planning documents
|  | 1.9.5 | Data Depository |  | The facility, including storage requirements, designated to act as custodian to maintain a master engineering specification and establish a drawing repository service for Government approved documents that are the property of the UK Government. As custodian for the Government, the repository, authorised by approved change orders, maintains these master documents at the latest approved revision level. This facility is a distinct entity that may hold electronic or hard copy data. Includes, for example:
a. All drafting and clerical effort necessary to maintain documents
Excludes, for example:
a. All similar effort for facility’s specification and drawing control system, in support of its engineering and production activities
NOTE: When documentation is called for on a given item of data retained in the Repository, the charges (if charged as direct) will be to the appropriate data element.
|  | 1.9.6 | Other data (please specify)
| 1.1 | Specialist Support Equipment |  |  | The design, development, and production of those deliverable items and associated software required to support and maintain the system or portions of the system while the system is not directly engaged in the performance of its mission, and which are not common support equipment. Includes, for example:
a. Vehicles, equipment, tools, etc., used to fuel, service, transport, hoist, repair, overhaul, assemble, disassemble, test, inspect, or otherwise maintain mission equipment
b. Any production of duplicate or modified factory test or tooling equipment delivered to the Government for use in maintaining the system. (Factory test and tooling equipment initially used by the contractor in the production process but subsequently delivered to the Government will be included as cost of the item produced.)
c. Any additional equipment or software required to maintain or modify the software portions of the system
Excludes, for example:
a. Overall planning, management and task analysis functions inherent in the Work Breakdown Structure element, systems Engineering/Program Management
b. Common support equipment, presently in the MOD inventory or commercially available, bought by the using command, not by the acquiring command
|  | 1.10.1 | Test and Measurement Equipment |  | The specific or unique testing and measurement equipment that allows an operator or maintenance function to evaluate operational conditions of a system or equipment by performing specific diagnostics, screening or quality assurance effort at an organisational, intermediate, or depot level of equipment support. Includes, for example:
a. Test measurement and diagnostic equipment, precision measuring equipment, automatic test equipment, manual test equipment, automatic test systems, test program sets, appropriate interconnect devices, automated load modules, tapes, and related software, firmware and support hardware (power supply equipment, etc.) Used at all levels of maintenance
b. Packages that enable line or shop replaceable units, printed circuit boards, or similar items to be diagnosed using automatic test equipment
|  | 1.10.2 | Support and Handling Equipment |  | The deliverable tools and handling equipment used for support of the mission system. Includes, for example:
a. Ground support equipment, vehicular support equipment, powered support equipment, non-powered support equipment, munitions material handling equipment, materiel handling equipment, and software support equipment (hardware and software)
|  | 1.10.3 | Other Specialist Support Equipment
| 1.11 | Common Support Equipment |  |  | The items required to support and maintain the system or portions of the system while not directly engaged in the performance of its mission, and which are presently in the MOD inventory for support of other systems. Includes, for example:
a. Acquisition of additional quantities of this equipment needed to support the item
b. All efforts required to assure the availability of this equipment to support the item
|  | 1.11.1 | Test and Measurement Equipment |  | The common testing and measurement equipment that allows an operator or maintenance function to evaluate operational conditions of a system or equipment by performing specific diagnostics, screening or quality assurance effort at an organisational, intermediate, or depot level of equipment support. Includes, for example:
a. Test measurement and diagnostic equipment, precision measuring equipment, automatic test equipment, manual test equipment, automatic test systems, test program sets, appropriate interconnect devices, automated load modules, tapes, and related software, firmware and support hardware (power supply equipment, etc.) Used at all levels of maintenance
b. Packages that enable line or shop replaceable units, printed circuit boards, or similar items to be diagnosed using automatic test equipment
|  | 1.11.2 | Support and Handling Equipment |  | The deliverable tools and handling equipment used for support of the mission system. Includes, for example:
a. Ground support equipment, vehicular support equipment, powered support equipment, non-powered support equipment, munitions material handling equipment, materiel handling equipment, and software support equipment (hardware/software)
|  | 1.11.3 | Other Common Support Equipment
| 1.12 | Operational/Site Activation |  |  | The estates, construction, conversion, utilities, and equipment to provide all facilities required to house, service, and launch the system at the organisational and intermediate level. Includes, for example:
a. Conversion of site, ship, or vehicle
b. System assembly, checkout, and installation (of mission and support equipment) into site facility or ship to achieve operational status
c. Contractor support in relation to operational/site activation
|  | 1.12.1 | System Assembly, Installation and Checkout on Site |  | The materials and services involved in the assembly of mission equipment at the site. Includes, for example:
a. Installation of mission and support equipment in the operations or support facilities and complete system checkout or shakedown to ensure operational status. Where appropriate, specify by site, ship or vehicle.
b. The efforts and activities associated with shipping the system from contractor facility to customer site. That site could be a MOD site, an installation and checkout site or any similar site that is outside the direct control of the contractor.
|  | 1.12.2 | Contractor Technical Support |  | The materials and services provided by the contractor related to activation. Includes, for example:
a. Repair of repairables, standby services, final turnover
|  | 1.12.3 | Site Construction |  | Estates, site planning and preparation, construction, and other special-purpose facilities necessary to achieve system operational status. Includes, for example:
a. Construction of utilities, roads, and interconnecting cabling
|  | 1.12.4 | Site/Ship/Vehicle Conversion |  | The materials and services required to convert existing sites, ships, or vehicles to accommodate the mission equipment and selected support equipment directly related to the specific system. Includes, for example:
a. Operations, support, and other special purpose facilities conversion necessary to achieve system operational status, e.g., launch. Where appropriate, specify by site, ship or vehicle
|  | 1.12.5 | Sustainment/Interim Contractor Support |  | The complex of equipment (hardware/software), data, and services required to operate, maintain, support and modernise existing operational systems before the In Service Date. Includes, for example:
a. System maintenance and modernisation. The cost for this element includes maintenance and modernisation (including the development and production) of existing, operational systems. It excludes the development and production of the original system.
b. Support functions required to maintain and modernise the system, such as sustaining engineering, program management, logistics support, and supply chain management
c. Test and evaluation for system and subsystem modifications
d. Replacement of common and specific support equipment
e. Replacement of repairable items
f. Operational, maintenance and other personnel required at the operational unit level
g. Unit operations costs, including operating material and support services at the operating unit
h. Installation and personnel support functions in support of the unit level manpower
|  | 1.12.6 | Other Operational/Site activation
| 1.13 | Industrial Facilities |  |  | The construction, conversion, or expansion of industrial facilities for production, inventory, and contractor depot maintenance required when that service is for the specific system. Includes, for example:
a. Equipment acquisition or modernisation, where applicable
b. Maintenance of these facilities or equipment
c. Industrial facilities for hazardous waste management to satisfy environmental standards
Excludes, for example:
a. Capital equipment
|  | 1.13.1 | Construction/Conversion/Expansion |  | The real estate and preparation of system specific industrial facilities for production, inventory, depot maintenance, and other related activities.
|  | 1.13.2 | Equipment Acquisition or Modernisation |  | The production equipment acquisition, modernisation, or transferral of equipment for the particular system. This pertains to Government owned and leased equipment under facilities contract.
|  | 1.13.3 | Maintenance (Industrial Facilities) |  | The maintenance, preservation, and repair of industrial facilities and equipment.
|  | 1.13.4 | Other Industrial Facilities
| 1.14 | Initial Spares and Repair Parts |  |  | The deliverable spare components, assemblies and subassemblies used for initial replacement purposes in the materiel system equipment end item. Includes, for example:
a. Repairable spares and repair parts required as initial stock to support and maintain newly fielded systems or subsystems during the initial phase of service, including pipeline and war reserve quantities, at all levels of maintenance and support
Excludes, for example:
a. Developmental Test spares and spares provided specifically for use during installation, assembly, and checkout on site. Lower level DPS breakouts should be by subsystem
In-service contract specific tasks
| 1.15 | On Tools Manpower - Maintenance, Rectifications and Repair Activity |  |  | The costs included under this level 2 element will be the aggregated costs of all ‘On Tools’ contractor operators, contractor maintenance personnel and other sub contractors working directly on the equipment. All ‘Non Touch’ Manpower relating to Project and Project support activity will be recorded under 1.18
|  | 1.15.1 | Maintenance Activities |  | This will include all ‘On Tools’ contractor operators, contractor maintenance personnel and other sub contractors at GRADE (n) working directly on the equipment. Insert a level 3 cost line for each relevant grade consuming resource in this area. Wherever possible all defined grades should match those used in the contractors Rates Claim. Where this is not the case the contractor should justify the reason why this methodology has not been adopted. All ‘Non Touch’ Manpower relating to Project and Project support activity will be recorded under 1.18
|  |  | 1.15.1.1 | Depth maintenance activities
|  |  | 1.15.1.2 | Forward maintenance activities
|  |  | 1.15.1.3 | Other (Specify, i.e. Forward-Depth Maintenance if carried out by contractor on site)
| 1.16 | Consumables / Fungibles (Contract Specific) |  |  | These will be items which are required to fulfil the obligations of the contract. In the case of the DPS for in service contracts the consumables must not be part of the overhead of the supplier but be specific consumables and fungibles which are required for the contract. This cost is only needed at aggregated level. Consumables are materials used for the maintenance and support of systems and associated sub systems and training equipment. This will include items such as oil, fuel, coolants and de-icers. Fungibles are items which are required for the installation and integration of parts used for maintenance, such as nuts and bolts but they are interchangeable and not specific to a particular equipment type. Guidance --- Only needed at aggregated level. Should not include items that have gone through the overheads
| 1.17 | Packing, Handling, Storage and Transportation |  |  | These costs will include any specific costs associated with the movement of items up and down the supply chain in order to fulfil the obligations under the contract. They must be costs which are incurred specifically on this QDC. This cost is only needed at aggregated level. Packing – provides for the product security, transportability and storability with the added utility of serving as a medium of communication from the provider to the user. The nature of an item determines the type and extent of protection needed to prevent its deterioration during transport. The mode of shipping will dictate the materials selected for the preservation in addition to packaging. Handling – involves the moving of items from one place to another within a limited range and is normally confirmed to a single area, such as between warehouses, storage areas or operational areas or movement from storage to moved of transportation. Storage – involves the short or long term stockpiling of items. Storage can be accomplished in either temporary or permanent facilities. It may be a function of the transportation timeline or it may be required for material in reserve. Transportation – any specifically attributable transportation costs associated with the transit of items
| 1.18 | Non Touch Manpower |  |  | The costs included under this level 2 element will be the aggregated costs (by grade) of all project and project support manpower involved in; • Asset Management • Engineering & Safety • Post Design Services • Contract & Project Management • Training • Waste Management Notes Wherever possible all defined grades should match those used in the contractors Rates Claim. Where this is not the case the contractor should justify the reason why this methodology has not been adopted
|  | 1.18.1 | Asset Management |  | The costs included here will be for the manpower taken to manage all assets held and used in fulfilment of the contract. The costs will be split out by the relevant grade consuming resource under this code. They will generally cover the following Level 4 activities;
|  |  | 1.18.1.1 | Planning and Optimisation | Typical activity will include the initial and ongoing consideration of the Factors influencing; Demand, Production & Overall Supply and Delivery of the product or service. Having considered all key factors and constraints the functional area will use the analysis to optimise the service delivery plan to meet contract requirements.
|  |  | 1.18.1.2 | Inventory Management | This functional area typically covers the control, ordering, storage and use of all consumable spares, materials and parts to maintain operating capability whilst minimising stock holding costs.
|  |  | 1.18.1.3 | Supply Chain Management | This functional area typically controls the flow of goods and services from the point of origin to the point of consumption.
|  |  | 1.18.1.4 | Procurement Management | This functional area typically covers the identification and sourcing of consumables, materials and parts of the correct quality and specification at the most competitive price to meet the criteria of the contract.
|  |  | 1.18.1.5 | Other Asset Management item (Please specify in additional information)
|  | 1.18.2 | Engineering and Safety |  | The costs included here will be for the manpower taken to manage all engineering support services and the safety aspects required to fulfil the contract with regard to overall System / Equipment Integrity and other legislative obligations (such as HSAW, Environmental Protection directives and regulations). The costs will be split out by the relevant grade consuming resource under this code. They will generally cover the following Level 4 activities;
|  |  | 1.18.2.1 | Air/Sea/Road Worthiness - Integrity Assurance | This functional area typically covers all activity that underpins the continued structural integrity of the equipment which in turn supports the continued assurance of safe operation within the Equipment’s defined performance envelope. This will include any mandated activities to ensure continued compliance with all requirements of any National or International Safety Board.
|  |  | 1.18.2.2 | Specialist Labour | This category will include all costs of any external specialist labour required to fulfil obligations under the contract. Note this category should not be used to capture routine sub-contract labour used to supplement prime contractor workforce.
|  |  | 1.18.2.3 | Technical Queries - On Call Support | This category will include all resource costs relating to the provision of an on call support service or technical queries to the level specified in the contract.
|  |  | 1.18.2.4 | Reliability Management | This functional area typically covers the monitoring and review of initial and continuing in service data on the performance of individual components and assemblies against the expected performance criteria. Analysis of data will then identify performance and reliability issues and feed into other engineering support areas to define remedial action to restore performance standards.
|  |  | 1.18.2.5 | Other Engineering and Safety (Please specify in additional information)
|  | 1.18.3 | Post design Services |  | Post Design Services can cover a variety of activities all designed to maintain equipment capability. The activity will vary depending on contract type but will typically include the cost for; Configuration Management, Obsolescence Management, Technical Publications, Modification Design and Prototype Testing. The costs will be split out by the relevant grade consuming resource under this code. They will generally cover the following Level 4 activities; Note – PDS normally covers costs for contractor provided training services, for DPS purposes all training costs should be recorded under the specific training category at 1.18.5.
|  |  | 1.18.3.1 | Configuration Management | For Equipment Hardware contracts this activity includes the engineering processes for establishing and maintaining consistency of product performance. This includes functional and physical attributes with the stated operating requirements, design and operational information throughout the life of the contract. For Software specific contracts this activity includes the discipline for evaluating, co-ordinating, approving and implementing changes in artefacts that are used to construct and maintain software systems.
|  |  | 1.18.3.2 | Obsolescence Management | Typically covers the costs to analyse designs and products to identify parts and components for which vendors are no longer available, or which can no longer be repaired, and to identify new vendors or interchangeable or replacement parts. It can also include costs associated with reverse engineering to identify part functionality, form-fit-function studies, materials analysis, and life cycle maturity assessments.
|  |  | 1.18.3.3 | Technical Publications | Typically covers the cost of maintaining and updating all technical support media thru the life of the contract. This would include the generation of amendment instructions to all users of the data and maintaining a master reference set of amendments detailing change history.
|  |  | 1.18.3.4 | Modifications - Assessment & Design Effort | Typically covers the cost of design effort for the proposed modification along with prototype testing. Contracts involving a major modification programme such as, Mid Life Updates, Capability Sustainment Programme or Life Extension Programme would almost certainly form a new QDC and therefore all costs for On Tools and Non Touch Manpower along with associated parts and materials would be recorded against the relevant categories of the DPS for that particular contract.
|  |  | 1.18.3.5 | Other PDS (Please specify in additional information)
|  | 1.18.4 | Post design Services (manpower) |  | These costs will be specific costs in relation to the manpower expended in managing the contract and projects under the contract. They are not general overheads but specific costs related to a particular contract. The costs will be split out by the relevant grade consuming resource under this code.
|  |  | 1.18.4.1 | Finance | This element includes costs to provide financial management, including costs vs. budget analyses, full funding assessments, appropriations and obligations management, etc. This element also includes the costs associated with the allocation of funding to tasks and work packages and assessing impacts of schedule changes on final costs.
|  |  | 1.18.4.2 | Commercial | This element will include all costs incurred in relation to the specific commercial activities undertaken for the contract.
|  |  | 1.18.4.3 | Legal | This element will include all costs incurred in relation to the specific legal activities undertaken for the contract. This will include any non recurring costs in relation to legal disputes or obligations.
|  |  | 1.18.4.4 | Senior Management - Direct to Project or Programme | This element will include the cost of any senior management required for the contract. This will only include specific costs and these should be allocated on an appropriate and proportionate basis.
|  |  | 1.18.4.5 | Programme Quality Assurance | This element includes the costs of the systematic monitoring and evaluation of the various aspects of a project or service are fit for the intended purpose as defined in the Statement of Requirement and that sufficient control and feedback is generated to assure continuing conformity, generating corrective action or improvements where necessary.
|  |  | 1.18.4.6 | Data Management | This element includes all costs of data collection and analysis to assess the effectiveness of the contract. It can also include any explicit data capture and analysis as mandated in the contract requirements.
|  |  | 1.18.4.7 | Security / Insurance | This element includes the cost to provide and maintain physical security such as perimeter fences and gates, guard stations, closed circuit and electronic monitoring, badging and access control. It also includes protection from and remediation for damage from natural and manmade disasters, accidents, electrical power losses and spikes, fire and theft etc. Insurance will include any costs for specific insurances relating to the fulfilment of the contract.
|  |  | 1.18.4.8 | Other Contract and Project Management activity (Please specify in additional information)
|  | 1.18.5 | In service Training costs |  | These costs will cover the costs associated with the delivery of specific training requirements as required in the execution of the contract. The costs will be split out by the relevant grade consuming resource under this code.
|  |  | 1.18.5.1 | Operator or Maintainer Training | Delivery of Initial and Refresher training for Operators and Maintenance staff. This could be at contractor’s site or MoD establishment.
|  |  | 1.18.5.2 | Project Specific Training | Attendance of project staff on specific training courses required by personnel in execution of the specific contract roles.
|  |  | 1.18.5.3 | Other in service training costs (Please specify in additional information)
|  | 1.18.6 | Disposal / Waste Management |  | These costs will cover the management costs associated with the maintenance obligations completed under the contract. The costs will be split out by the relevant grade consuming resource under this code.
|  | 1.18.7 | Other Maintenance Management activity ( (Please specify in additional information)
| 1.19 | Specialist Equipment |  |  | These costs will include any costs associated with the purchase of specialist equipment required to fulfil the obligations of the contract.
|  | 1.19.1 | Rigs, Jigs and Support Equipment (all-up) |  | This element will include costs incurred in relation to any specialist support equipment. Including Rigs, Jigs and Specialist Support Equipment. Specialist equipment – specialist equipment means any equipment which is specifically required for the contractor’s obligation under the contract.
|  |  | 1.19.1.1 | Special To Type Support Equipment | Equipment unique to this particular contract or Major Equipment. This will typically include maintenance, upkeep and replacement costs of specialist lifting equipment or ground handling equipment.
|  |  | 1.19.1.2 | Common Support Equipment | Support Equipment that is in common use (2 or more equipments.) across the Defence Inventory. This will typically include maintenance, upkeep and replacement of the equipment.
|  |  | 1.19.1.3 | Other support equipment (Please specify in additional information)
|  | 1.19.2 | Testing and Diagnostics |  | These costs will cover any specialist equipment required for testing and diagnostics purposes. These equipment types typically confirm the existence of a fault and possibly identify and sentence the sub-system, line replacement unit or component causing the fault. The cost category will capture the costs of usage, maintenance, upkeep and replacement.
|  |  | 1.19.2.1 | Special To Type Test Equipment | Testing & Diagnostic Equipment unique to this particular contract or Major Equipment. Equipment would typically download fault codes or run diagnostic scenarios in controlled sequence to identify and sentence fault. Costs will include maintenance, upkeep and replacement of the equipment.
|  |  | 1.19.2.2 | Common Test Equipment | Functionality as 1.19.2.1 where the equipment is in common use (2 or more equipments.) across the Defence Inventory. Costs will typically include maintenance, upkeep and replacement of the equipment.
|  |  | 1.19.2.3 | Other testing and equipment (Please specify in additional information)
|  | 1.19.3 | Specialist Facilities |  | This category will include the costs of any specialist facilities required to fulfil the obligations of the contract. The facility will meet or facilitate a specific contract requirement and will be for the exclusive use of the contract. Any cost of surplus capacity should be bourne by the contractor unless there is a specific contract requirement to maintain surge capacity or expansion options
|  |  | 1.19.3.1 | Rent of premises | This will include the rental costs of premises required to fulfil obligations under the contract. Where only part of the rented premises is required, then an appropriate and reasonable apportionment of the costs should be included here if they are costs which have been taken on for the purpose of the contract. If the cost of the premises would have been absorbed by the contractor regardless of the contract they should NOT be included.
|  |  | 1.19.3.2 | Major Training Equipment - Simulators & STE (specify) | This will include the costs of usage, maintenance, upkeep and replacement of any major training equipment including the operational simulators and advanced synthetic training environments.
|  |  | 1.19.3.3 | Conversion and Expansion | This will include the costs of converting or expanding existing assets for use on the specified contract. The cost of conversion / expansion must be derived from a definite need and the contractor should prove the costs are the most economic means of meeting the requirement.
|  |  | 1.19.3.4 | Maintenance of specialist facilities | This will include the costs of maintaining the specialist facility throughout the life of the contract. Maintenance activity should be commensurate and appropriate to the operating use and local environment. If the facility is not used exclusively for the contract then the cost should be apportioned on a reasonable basis.
|  |  | 1.19.3.5 | Other specialist facilities item (Please specify in additional information)
|  | 1.19.4 | Individual or Small Scale Modifications |  | This element includes the cost of parts and materials required for small scale routine modifications to the equipment. Because these items will cover routine modifications the materiality the cost may be captured at aggregated level.
|  | 1.19.5 | Specialist IT |  | This element includes the cost of any specialist IT required to fulfil obligations of the contract. If the Specialist IT or any level 4 component is used in other areas of the contractors business then the contract shall only bear a proportion of the costs commensurate with a reasonable basis of apportionment.
|  |  | 1.19.5.1 | Specialist Software | This element includes the cost of any specialist software. Software is intangible programmes, libraries and applications used for the operation of computers. Specialist Software Licences. - This element includes the cost of software licences, either enterprise-wide or seat based. Technology Refresh. - This element includes the costs of the periodic replacement of computers and peripherals to maintain operating functionality and business efficacy in relation to contract delivery.
|  |  | 1.19.5.2 | Specialist Hardware | This element includes the cost of any specialist hardware. Computer hardware is the physical element of a computer system.
|  |  | 1.19.5.3 | Maintenance of specialist IT | This cost is only valid to the contract if the maintenance of the specialist IT is performed by dedicated support staff. If the IT is maintained by routine staff who maintain all other IT then this cost should be part of the overhead.
|  |  | 1.19.5.4 | Other specialist IT equipment (Specify)
|  | 1.19.6 | Any other category not included above (Please specify in additional information)