## Guidance
Guidance for completing DPS for a Surface Ship (v3)
This guidance aims to help you complete the DPS for a Surface ship.
The template (along with the mapping documentation from the WBS and the method of apportionment of costs) should be returned alongside the Contract Notification Report (CNR) and later the Interim Contract Report (ICR) and Contract completion report (CCR).
The DPS is split into 4 level of items and the relationship is broken down as follows:
Level 1 | Level 2 | Level 3 | Level 4
(1) Surface Ship
(1.1) Surface Ship
|  | (1.1.1) Hull Structure And Super structural | (1.1.1.1) - (1.1.1.12)
|  | (1.1.2) Propulsion | (1.1.2.1) - (1.1.2.12)
|  | (1.1.3) Electrical | (1.1.3.1) - (1.1.3.6)
|  | (1.1.4) Control and Communication | (1.1.4.1) - (1.1.4.8)
|  | (1.1.5) Ancillary Systems | (1.1.5.1) - (1.1.5.11)
|  | (1.1.6) Outfit and Furnishing | (1.1.6.1) - (1.1.6.12)
|  | (1.1.7) Armament | (1.1.7.1) - (1.1.7.12)
|  | (1.1.8) Ship System Software | No level 4
|  | (1.1.9) Surface Ship Integration, Assembly, Test and Checkout | No level 4
| (1.2) System Engineering | No level 3 | No level 4
| (1.3) Program Management | No level 3 | No level 4
| (1.4) Research and development | No level 3 | No level 4
| (1.5) System Test and Evaluation | (1.5.1) - (1.5.6) | No level 4
| (1.6) Training | (1.6.1) - 1.6.3) | No level 4
| (1.7) Data | (1.7.1) - (1.7.5) | No level 4
| (1.8) Specialist Support Equipment | (1.8.1) - (1.8.3) | No level 4
| (1.9) Common Support Equipment | (1.9.1) - (1.9.3) | No level 4
| (1.10) Operational/Site Activation | (1.10.1) - (1.10.6) | No level 4
| (1.11) Industrial Facilities | (1.11.1) - (1.11.4) | No level 4
| (1.12) Initial Spares and Repair Parts | No level 3 | No level 4
| (1.13) Additional Categories Relevant to contracts for; Mid Life Update, Life Extension, Capability Sustainment | (1.13.1) - (1.13.3) | No level 4
In-service element | (1.14) On tools manpower - maintenance, rectifications & repair | (1.14.1) | (1.1.14.1) - (1.14.1.3)
| (1.15) Consumables/fungibles | No level 3 | No level 4
| (1.16) Packing, Handling, Storage and Transportation | No level 3 | No level 4
| (1.17) Non touch manpower | (1.17.1) Asset management | (1.17.1.1) - (1.17.1.5)
|  | (1.17.2) Engineering & safety | (1.17.2.1) - (1.17.2.5)
|  | (1.17.3) Post design service | (1.17.3.1) - (1.17.3.5)
|  | (1.17.4) Post design service (Manpower) | (1.17.4.1) - (1.17.4.7)
|  | (1.17.5) In service training | (1.17.5.1) - (1.17.5.7)
|  | (1.17.6) Disposal / Waste Management | No level 4
|  | (1.17.7) Other Maintenance Management activity (Specify) | No level 4
| (1.18) Specialist Equipment | (1.18.1) Rigs, Jigs and Support Equipment (all-up) | (1.18.1.1) - (1.18.1.2)
|  | (1.18.2) Testing and Diagnostics | (1.18.2.1) - (1.18.2.2)
|  | (1.18.3) Specialist Facilities | (1.18.3.1) - (1.18.3.5)
|  | (1.18.4) Individual or Small Scale Modifications | No level 4
|  | (1.18.5) Specialist IT | (1.18.5.1) - (1.18.5.4)
|  | (1.18.6) Other Specialist Equipment (Specify) | No level 4
General
This template has been designed to assist you in apportioning the costs associated with either the construction and/or in-service support of a surface ship.
The template has also been designed to help you complete the DPS input tab and therefore the price tab on the Contract Notification Report (CNR).
By completing this template first, you will find it easier to translate the relevant DPS levels, descriptors and costs to the CNR, and will also help explain where costs have been allocated.
You should note that the 'descriptor' section on the CNR DPS input tab must be manually completed - the form does not allow copy and paste.
This template should be completed and returned alongside any mapping documents that you may use and your existing work breakdown structure.
The template should be completed in accordance with the SSRO guidance: DPS principles which can be found by clicking on the document to the right.
Apportionment of costs
Costs must add up to the total contract value excluding profit. The DPS, being a breakdown of the total contract value excluding profit, must include all indirect as well as direct costs.
Construction costs (this includes research, development and build) should be entered in column L. The figures automatically format to 'millions' and 3.d.p.
Where there are no costs, or a specific level of the DPS does not apply, this should be left blank.
Where there is a cost and there is no appropriate DPS level, the 'other' row should be used and an explanation entered in the 'additional information' column (see 'Use of other' below).
The costs at a subordinate level should total the costs at the superior level, as detailed in the principles document.
Level 1 of the DPS must total 100 per cent of the contract value excluding profit and the breakdown of each subsequent level must total the preceding level.
The 'price tab' of the CNR allows you to split recurring and non recurring costs pre DPS element.
The costs do not auto-calculate so can you please ensure the costs for the relevant level add up correctly.
Only one cost entry needs to be entered at level 4, regardless of the number of codes selected from the drop down boxes (see use of CPV/UNSPSC codes below)
The section headed 'In service contract specific tasks' does not have to be completed if there is no in-service element.
Full details of the approach to apportioning costs can be found in the SSRO guidance: DPS Principles document.
Use of CPV/UNSPSC mapping codes
We have included (where possible) the relevant CPV and UNSPSC codes to help you apportion the costs from your existing WBS for each level of the DPS.
Columns A-F contain the DPS code and relevant descriptor for each level, in order to help you apportion the costs.
We have mapped the relevant CPV and UNSPSC codes (G and H) columns to each level of the DPS to signpost where the costs should go.
We have put the relevant CPV/UNSPSC codes in drop down boxes so you can easily see which one could apply to the relevant DPS.
All cells corresponding to a particular level contain the same drop down menu. For example at level 1.1, all cells contain the same information enabling a different code to be selected, if appropriate.
As many codes as necessary can be applied at each DPS level.
You do not have to use the drop down boxes but these are in place to help apportion the costs, which should be entered in column L or M.
For level 4 items, more than one drop down box may be selected, however only one cost entry for that level should be entered, not a cost for each CPV/UNSPSC code.
Use of 'other'
When the description/category is not applicable, an 'other' row is present at level 4 to capture additional information.
At Levels 2,3 and 4, the 'other' section is contained within the descriptor and not as a separate row. Any relevant detail should be added in 'additional information'.
The 'additional information' box should be completed whenever an 'other' description is needed.
Please do not add any additional rows to the spreadsheet. Any additional detail should be captured in the 'additional information' box at each level.
Where this is no specific 'other' row, the relevant information should be put in the additional information box.
Use of the 'other' category is to be used in the following circumstances:
(1) when there is no appropriate description available within the DPS;
(2) for any contingent cost included in the contract; or
(3) where a small proportion of costs would be difficult to apportion to categories listed in the DPS; and
(4) where there is no specific 'other' row (please place a description in the 'additional information' column).
In service costs
Where there is an in-service element, the costs should be entered in column L.
DPS level 1.14 onwards relate specifically to in-service costs.
Some in-service costs may be better suited to match DPS levels 1.1 - 1.13.
The costs at a subordinate level should total the costs at the superior level, as detailed in the principles document.
The costs do not auto-calculate so can you please ensure the costs for the relevant levels add up correctly.
If the contract is construction specific but includes and in-service element, please complete columns L and M for all level (where applicable).
If the contract is for in-service support/maintenance only, please complete DPS levels 1.14 onwards and any previous level you consider appropriate.
Metrics
We have included relevant output metrics (column J), where possible, but you may add any metrics you use in the boxes where appropriate.
The same metrics should be entered on the 'metrics' tab on the CNR.
If you have any questions please contact us at
helpdesk@SSRO.gov.uk
Version control
V1: Published 23 June 2015
V2: Published 30 September 2015 – In-service DPS added.
V3: Published 14 December 2015 - Research and development moved from level 3 line item to level 2. Subsequent numbering amended.

## SurfaceShip DPS
DPS codes | [5 empty] | CPV codes | UNSPSC codes | Additional information | Output metrics |  | Costs (£m)
Level 1 | Level 2 | Level 3 | Level 4 |  | Descriptor
1 | Surface ship |  |  |  |  | 34510000 : Ships | 25111712 : Frigates |  | Metric | Figure | In service costs | Construction costs
| 1.1 | Surface ship |  |  | The complete working ship - includes the design, development, and production of complete units (i.e. the prototype or operationally configured units, which satisfy the requirements of their applicable specification(s), regardless of end use). Includes, for example, hull & superstructure, propulsion, electrical, control & communications, armament, ancillary systems and all other installed equipment. |  |  |  | Mass: Full Load Displacement, Tonnes
Performance: Max Speed, Kn
Performance: Range Of Ship, Nm
Crew Size, Number
|  | 1.1.1 | Hull and Superstructure |  | The assembled structural components of the hull and superstructure that support subsystems essential to designated mission requirements. Includes, for example: |  |  |  | Full Load Displacement, Tonnes
[5 empty] | a. Hull structure |  |  |  | Principle Structure Material (Steel/GRP/Composite)
b. Superstructure
c. Structural Bulkheads
d. Structural Decks
e. Doors, Hatches & Scuttles
f. Seats, Supports & Masts
g. Control Surfaces
h. Structural Castings & Forgings
i. Buoyancy & Ballast units
j. Fastenings
k. Other
|  |  | 1.1.1.1 | Hull and Superstructure Subsystem Integration, Assembly, Test, and Checkout | This element includes all effort of technical and functional activities associated with the design, development, and production of mating surfaces, structures, equipment, parts, materials, and software required to assemble and test the subsystem parts and subsystems equipment (hardware/software) elements.
|  |  | 1.1.1.2 | Hull Structure | Includes, for example:
a. Hull Plating
b. Hull Longitudinal and Transverse Framing
c. Inner Bottom Plating
d. Hull Structural Walkways/Sponsons
e. Metallic Hull Armour and Protection
f. Sonar Domes Forming Part of the Hull Structure
g. Radar Absorbent Material
h. Non-Metallic Hull-Armour and Protection
|  |  | 1.1.1.3 | Superstructure | Includes, for example:
a. Superstructure Plating b. Superstructure Longitudinal and Transverse Framing c. Superstructure Decks and Flats d. Superstructure Bulkheads e. Superstructure Hangar f. Superstructure Structural Walkways and Sponsons g. Metallic Superstructure Armour and Protection h. Non-Metallic Superstructure and Armour i. Ramps to Assist Aircraft Take-Off j. Radar Absorbent Material
|  |  | 1.1.1.4 | Structural Bulkheads | Includes, for example:
a. Main Transverse Bulkheads b. Main Longitudinal Bulkheads c. Other Bulkheads d. Funnel, Structural Trunks and Enclosures e. Metallic Bulkhead Armour and Protection f. Non-Metallic Bulkhead Armour and Protection
|  |  | 1.1.1.5 | Structural decks | Includes, for example:
a. Main Decks b. Minor Decks and Flats c. Metallic Deck Armour and Protection d. Non-Metallic Deck Armour and Protection
|  |  | 1.1.1.6 | Bridge Windows, Sidelights, Doors, Hatches and Scuttles | Includes, for example:
a. Bridge Windows, Sidelights and Scuttles b. Watertight and Gastight Doors and Hatches c. Escape Hatches and Scuttles d. Manholes e. Blow-Off plates f. Bow, Side and Stern Doors Including Associated Ramps
|  |  | 1.1.1.7 | Seats, supports and masts | Includes, for example:
a. Seats and supports for 1.1.1 items b. Seats and supports for 1.1.2 items c. Seats and supports for 1.1.3 items d. Seats and supports for 1.1.4 items and masts e. Seats and supports for 1.1.5 items f. Seats and supports for 1.1.6 items g. Seats and supports for 1.1.7 items
|  |  | 1.1.1.8 | Control Surfaces | Includes, for example:
a. Rudders and Skegs b. Stabilisers (Fixed) c. Hydrofoils d. Bilge Keels e. Stabilising Tanks
|  |  | 1.1.1.9 | Structural Castings and Forgings | Includes, for example:
a. Shaft Brackets b. Forgings and Castings c. Sea Chests d. Anchor Hawse Pipes and Navel Pipes e. Stern Tubes f. Sea Tubes
|  |  | 1.1.1.10 | Fixed Ballast | Includes, for example:
a. Buoyancy Units b. Ballast Units
|  |  | 1.1.1.11 | Fastenings | Includes, for example:
a. Welding b. Riveting c. Bolting d. Bonding
|  |  | 1.1.1.12 | Other (Please specify in additional information)
|  | 1.1.2 | Propulsion |  | That portion of the sea system that pertains to installed equipment (propulsion unit and other propulsion) to provide power/thrust to propel the vessel through the water and generate internal power (mechanical and electrical). Includes, for example: |  |  |  | Number of engines
[5 empty] | a. Power Plant (Nuclear) b. Power Plant (Non Nuclear) c. Propulsion Units and Control Equipment d. Main Condensers and Air Ejectors e. Shafting, Bearings and Propulsors f. Combustion Air Supply and Exhaust Systems g. Steam Systems h. Circulating & Cooling Water systems, Feed water & Condensate Systems i. Fuel Oil Service Systems j. Lubricating Oil Systems k.Other |  |  |  | Combined For Max Speed
Power Per Engine, SHP
|  |  | 1.1.2.1 | Propulsion Integration, Assembly, Test, and Checkout | This element includes all effort of technical and functional activities associated with the design, development, and production of mating surfaces, structures, equipment, parts, materials, and software required to assemble and test the subsystem parts and subsystems equipment (hardware/software) elements.
|  |  | 1.1.2.2 | Propulsion Power Plant (Nuclear) | Includes, for example:
a. Reactor b. Steam Generators c. Primary Circuit System d. Primary Circuit Service System e. Reactor Plant Auxiliary Systems f. Reactor plant Control and Instrumentation g. Primary Shielding h. Secondary Shielding
|  |  | 1.1.2.3 | Propulsion Power Plant (Non-Nuclear) | Includes, for example:
a. Main Boilers b. Main Boiler Systems Control and Instrumentation c. Main Electrical Storage Batteries d. Main Electrical Storage Battery System, Switchgear and Instrumentation e. Gas Generators (if Separate from Power Turbine) f. Gas Generator Systems, Control and Instrumentation
|  |  | 1.1.2.4 | Propulsion Units and Control Equipment | Includes, for example: |  |  |  | No. of auxiliary engines
[5 empty] | a. Steam Turbines b. Gas Turbines c. Propulsion Diesel Engines d. Electric Propulsion Drives e. Propulsion Unit Control Equipment f. Clutches, Gearing, Flexible Couplings and Turning Gear g. Machinery Space Lifting Gear h. Insulation |  |  |  | Power per auxiliary engine, SHP
|  |  | 1.1.2.5 | Main Condensers and Air Ejectors | Includes, for example:
a. Main Condensers b. Air Ejectors c. Insulation, Lagging and Liners
|  |  | 1.1.2.6 | Shafting, Bearings and Propulsors | Includes, for example:
a. Shafting b. Propulsors Including Thrusters and Activated Rudders c. Shaft Bearings, Bulkhead Glands, Seals, Etc d. Torsion meters and Brakes
|  |  | 1.1.2.7 | Combustion Air Supply and Exhaust Systems | Includes, for example:
1. Reactor fresh water cooling system. Includes FW pumps, motors & starters, pipes, valves, fittings & cooling coils in the PST. Excludes FW/SW heat exchangers.
2. Valve operating & gas system.
3. Evacuation System.
|  |  | 1.1.2.8 | Steam Systems | Includes, for example:
a. Main Superheated Steam System b. Auxiliary Superheated Steam System c. Saturated Steam System d. Steam Exhaust System e. Steam Drain System
|  |  | 1.1.2.9 | Circulating and Cooling Water Systems, Feed Water and Condensate Systems | Includes, for example:
a. Main Circulating Water System to Condensers b. Cooling Water System for Propulsion Units c. Feed Water System for Propulsion Units d. Condensate System for Propulsion Units
|  |  | 1.1.2.10 | Fuel Oil Service Systems | Includes, for example:
a. Combustion Fuel Oil Service to Propulsion Units
|  |  | 1.1.2.11 | Lubricating Oil Systems | Includes, for example:
a. Lubricating Oil System to Propulsion Units
|  |  | 1.1.2.12 | Other propulsion (Please specify in additional information)
|  | 1.1.3 | Electrical |  | The Generation, conditioning and distribution of the electrical power supply throughout the ship. Includes, for example:
a. Electrical Main Power Supply Generation b. Power Distribution Equipment c. Power Distribution Cabling d. Lighting Systems e. Other
|  |  | 1.1.3.1 | Electrical Integration, Assembly, Test, and Checkout | This element includes all effort of technical and functional activities associated with the design, development, and production of mating surfaces, structures, equipment, parts, materials, and software required to assemble and test the subsystem parts and subsystems equipment (hardware/software) elements.
|  |  | 1.1.3.2 | Electrical Power Generation Equipment & mechanical systems | Includes, for example:
a. Steam Turbine Generator Sets b. Gas Turbine Generator Sets c. Diesel Generator Sets d. Shaft Generators e. Fuel Cell Generators f. Ride Through Power Supply g. Renewable Technology
|  |  | 1.1.3.3 | Power Distribution Equipment | Includes, for example:
a. Main Supply Equipment b. Distribution Equipment c. General Service Conversion Equipment d. Power Distribution Equipment for Portable Apparatus
|  |  | 1.1.3.4 | Power Distribution Cabling | Includes, for example:
a. Cabling b. Glands and Cable Support Equipment
|  |  | 1.1.3.5 | Lighting Systems | Includes, for example:
a. General Lighting Systems b. Emergency Lighting System c. Ceremonial Lighting System d. Contingency Lighting System
|  |  | 1.1.3.6 | Other electrical (Please specify in additional information)
|  | 1.1.4 | Control and Communication |  | Mission equipment on board the ship, which is primarily electronic in nature. Includes, for example: |  |  |  | Flagship facilities (yes/no)
[5 empty] | a. Navigation Systems b. Internal Communications c. Ships & Main Machinery Control Systems d. Weapon Control Systems e. Ships Protective Systems f. External Communications Systems g. Other |  |  |  | Sonars, Hull Mounted Arrays
Sonars, Towed Arrays
Sonars, Variable Depth Sonars
|  |  | 1.1.4.1 | Control & Communication Integration, Assembly, Test, and Checkout | This element includes all effort of technical and functional activities associated with the design, development, and production of mating surfaces, structures, equipment, parts, materials, and software required to assemble and test the Control and Communications parts and subsystems (hardware/software) elements.
|  |  | 1.1.4.2 | Navigation Systems & equipments | Includes, for example:
a. Gyro and Other Compasses b. Ship Inertial Navigation System (SINS) c. Navigation Aids and Direction Finding Equipment d. Log e. Meteorology and Oceanographic Systems f. Navigation Radar g. Viewing Devices h. Chronometers i. Plotting and Chart Tables j. Navigation Lights, Etc.
|  |  | 1.1.4.3 | Internal Communications | Includes, for example:
a. Broadcasts b. Internal Telephone Network and Telephones c. Sound Reproduction Equipment (SRE) d. Voice and Pneumatic Tubes e. Television, Radio and Cinema Equipment f. Alarms and Warnings g. Chemical, Biological, Radiological and Nuclear (CBRN) Warning Systems h. Engine Telegraph and Propeller Orders i. Rudder Angle Indicators j. Information Systems
|  |  | 1.1.4.4 | Ship and Main Machinery Control Systems | Includes, for example:
a. Ship Control Console (SCC) b. Systems Consoles c. Command Console d. Rudder Control System e. Integrated Navigation Systems f. Moveable Stabilisers and Control System g. Hydrofoil Control System h. Tank Stabilisation Systems (Active and Passive) i. Machinery Control System j. Integrated Platform Management Systems
|  |  | 1.1.4.5 | Weapons Control Electrics | Includes, for example:
a. Surface/Air Weapon Control Systems b. Surface/Surface Weapon Control Systems c. Surface/Anti-Submarine Weapon Control Systems d. Submerged Launched (Non-Air Flight) Systems e. Submerged Launched (Air Flight) Systems f. Weapon and Surveillance Radars g. Sonars h. Centralised Weapon Control Systems i. Electronic Warfare Systems (EW) j. Control Systems for Autonomous Craft
|  |  | 1.1.4.6 | Ship's Protective Systems | Includes, for example:
a. Degaussing System b. Cathodic Protection System c. Sacrificial Anodes
|  |  | 1.1.4.7 | External Communication Systems | Includes, for example:
a. Radio Communication Systems b. Underwater Telephones and Echo Sounders c. Visual Signalling Equipment d. Audio Signalling Equipment e. Satellite Communication Systems
|  |  | 1.1.4.8 | Other control and communication (Please specify in additional information)
|  | 1.1.5 | Ancillary Systems |  | General support systems on board the ship to support crew and mission equipment. Includes, for example:
a. Air Conditioning, Ventilation, Refrigeration Systems & Equipment b. Fuel Systems (Excluding Aircraft Systems) c. Sea & Fresh Water Systems d. Air & Gas Systems e. Hydraulic Systems (Excluding Aircraft Systems) f. Aircraft Systems g. Waste Disposal Systems h. Auxiliary Steam, Exhaust Steam and Steam Drain Systems i. Lubricating Oil Systems j. Other
|  |  | 1.1.5.1 | Ancillary Systems Integration, Assembly, Test, and Checkout | This element includes all effort of technical and functional activities associated with the design, development, and production of mating surfaces, structures, equipment, parts, materials, and software required to assemble and test the Ancillary Systems parts and subsystems (hardware/software) elements.
|  |  | 1.1.5.2 | Air Conditioning, Ventilation, Refrigeration - Systems and Equipment | Includes, for example:
a. Air Conditioning Plants b. Chilled and Tepid Water Systems c. Air Conditioning and Mechanical Ventilation System d. Free Standing Air Conditioning Units and Electrical Space Heaters e. Natural Ventilation Systems f. Refrigeration Plant and Equipment g. Air Conditioning and Ventilation System in Main Machinery Spaces h. Smoke Clearance Ventilation
|  |  | 1.1.5.3 | Fuel Systems (Excluding Aircraft Systems) | Includes, for example:
a. Main Fuel Filling, Heating and Transfer Systems b. Auxiliary Fuel Systems c. Tank Cleaning Systems
|  |  | 1.1.5.4 | Sea and Fresh Water Systems | Includes, for example:
a. Sea Water System (Including HPSW) b. Sea Water Fire Fighting System c. Flooding and Spraying Systems d. Pre-Wetting System e. Ballasting, Trimming and Drainage Systems f. Sea Water/Fresh Water Cooling System g. Distilling Plant System h. Fresh Water System i. Fresh Water Spraying systems
|  |  | 1.1.5.5 | Air and Gas Systems | Includes, for example:
a. HP Air System b. LP Air System c. Breathing Air Systems d. Control Air Systems e. Salvage Air Systems f. Recompression Chamber g. Special Services Air Systems h. Gas Fire Extinguishing Systems
|  |  | 1.1.5.6 | Hydraulic Systems (Excluding Aircraft Systems) | Includes, for example:
a. Hydraulic Systems
|  |  | 1.1.5.7 | Aircraft Systems | Includes, for example: |  |  |  | No. Of Spots (Landing spots)
[5 empty] | a. Aircraft Handling Systems b. Aircraft Lifts c. Arresting Gear and Barriers d. Catapults and Jet Blast Deflectors e. Aircraft Gas Producing Systems f. Aircraft Liquid Systems g. Aircraft Electrical Systems |  |  |  | No. Supported
Operating Mass Empty (Each), Kg
|  |  | 1.1.5.8 | Waste Disposal Systems | Includes, for example:
a. Sewage Disposal Systems b. Waste Water Disposal System c. Garbage Disposal System d. Oil Slick Dispersal System
|  |  | 1.1.5.9 | Auxiliary Steam, Exhaust Steam and Steam Drain Systems | Includes, for example:
a. Auxiliary Steam Generators and Systems b. Exhaust Steam Systems
|  |  | 1.1.5.10 | Lubricating Oil Systems | Includes, for example:
a. Main Lubricating Oil Filling and Transfer System b. Auxiliary Lubricating Oil Systems
|  |  | 1.1.5.11 | Other ancillary systems (Please specify in additional information)
|  | 1.1.6 | Outfit and Furnishing |  | General Fittings and Furnishings that complement the ship technical and domestic services. Includes, for example:
a. General Fittings b. Boats & Lifesaving Equipment c. Minor Bulkhead Partitions, Deck & Bulkhead Coverings in the Main Hull d. Furnishings & Fittings in Storerooms & Stowages e. Furnishings for Living Spaces f. Furnishings for Offices and Medical Spares etc. g. Equipment for Galleys, Laundries and Workshops h. Minor Bulkhead Partitions, Deck & Bulkhead Coverings in the Superstructure i. Portable Fire Fighting, Damage Control, CBRN & Escape Equipment j. Load Handling & RAS Equipment k. Other
|  |  | 1.1.6.1 | Outfit & Furnishings Integration, Assembly, Test, and Checkout | This element includes all effort of technical and functional activities associated with the design, development, and production of mating surfaces, structures, equipment, parts, materials, and software required to assemble and test the Outfit and Furnishings parts and subsystems (hardware/software) elements.
|  |  | 1.1.6.2 | General Fittings | Includes, for example:
a. Anchors, Cables, Winches, Bollards, Fairleads, Cleats, Etc. b. Guard-Rails, Stanchions, Rigging, Awnings, Etc. c. Ladders and Fittings d. Non-Structural Walkways e. Miscellaneous Fittings
|  |  | 1.1.6.3 | Boats and Lifesaving Equipment | Includes, for example:
a. Powered and Non-Powered Boats b. Davits and Handling Equipment for Boats c. Life rafts, Lifejackets, Stowages, Floats, Etc.
|  |  | 1.1.6.4 | Minor Bulkheads, Partitions, Deck and Bulkhead Coverings in the Main Hull | Includes, for example:
a. Minor Bulkheads and Doors b. Partitions and Linings c. External and Internal Paint d. Deck Coverings e. Deck Treads and Tread Plates f. Acoustic Insulation g. Thermal, Thermal/Acoustic Insulation h. Deck, Bulkhead and Hull Damping i. Modular Accommodation
|  |  | 1.1.6.5 | Furnishings and Fittings in Storerooms and Stowages | Includes, for example:
a. Furnishings and Fittings in Named General Stores b. Furnishings and Fittings in Victualling Stores (Including Medical and NAAFI Canteen Stores) c. Spare Gear Stowages throughout the Ship d. Furnishings and Fittings in All Other Stores
|  |  | 1.1.6.6 | Furnishings for Living Spaces | Includes, for example:
a. Furnishings for Officers’ Accommodation b. Furnishings for Crew’s Accommodation c. Furnishings for Heads and Bathrooms d. Furnishings for Aviation Crew Accommodation e. Furnishings for Embarked Forces/Trainees Accommodation
|  |  | 1.1.6.7 | Furnishings for Offices, Medical Spaces | Includes, for example:
a. Furnishings for Offices (Excluding Air Offices - 657) b. Furnishings for Sick Bay and Dental Surgeries c. Furnishings for Operating Theatres d. First Aid Equipment throughout the Ship e. Furnishings for Health Physics Laboratory f. Furnishings for Operational Rooms and Spaces g. Furnishings for Amenity Spaces h. Furnishings for Air Offices i. Furnishings for Lobbies and Passageways
|  |  | 1.1.6.8 | Equipment for Galleys, Laundries and Workshops | Includes, for example:
a. Equipment for Galleys, Pantries and Other Food Preparation Spaces b. Water Coolers, Domestic Refrigerators, Ice Cream Machines, Etc. c. Equipment for Laundry and Drying Rooms d. Equipment for Workshops and Repair Spaces e. Equipment for Air Workshops and Repair Spaces
|  |  | 1.1.6.9 | Minor Bulkheads, Partitions, Deck and Bulkhead Coverings in the Superstructure | Includes, for example:
a. Main Transverse Bulkheads b. Main Longitudinal Bulkheads c. Other Bulkheads d. Funnel, Structural Trunks and Enclosures e. Metallic Bulkhead Armour and Protection f. Non-Metallic Bulkhead Armour and Protection
|  |  | 1.1.6.10 | Portable Fire Fighting, Damage Control, CBRN, and Escape Equipment | Includes, for example:
a. Portable Fire Fighting Equipment b. Damage Control Equipment c. CBRN Equipment d. Escape Equipment
|  |  | 1.1.6.11 | Load Handling and RAS Equipment | Includes, for example:
a. RAS Mast Highpoints and Tripods b. Stores Handling and RAS Strike Down Equipment c. Cranes, Lifts and Other Non-Portable Lifting Appliances d. Portable Lifting Equipment
|  |  | 1.1.6.12 | Other outfit/furnishings (Please specify in additional information)
|  | 1.1.7 | Armament |  | Includes, for example: |  |  |  | Equipped For Strategic Missiles
[5 empty] | a. Surface/Air Missile Armament b. Surface/Surface Missile Armament c. Anti Submarine Armament d. Submerged Launched (Non-Air Flight) Armament e. Submerged Launched (Air Flight) Armament f. Air Launched Armament g. Mine hunting, Minelaying & Minesweeping Equipment h. Rocket Launchers, Small Arms & Pyrotechnic Stowages & Launchers i. Gun Armament j. Unmanned Aerial, Surface and Submersible Vehicles (UXV’s) Support Systems k. Other |  |  |  | No. Trainable SAM Launchers
No. Vertical GW Launch Systems
[9 empty] | LRLAM | Launch Mass, Kg
[9 empty] | Armament ; Sonars | Hull Mounted Arrays
[9 empty] | Armament ; Sonars | Towed Arrays
[9 empty] | Armament ; Sonars | Variable Depth Sonars
|  |  | 1.1.7.1 | Armament Integration, Assembly, Test, and Checkout | This element includes all effort of technical and functional activities associated with the design, development, and production of mating surfaces, structures, equipment, parts, materials, and software required to assemble and test the Armament parts and subsystems (hardware/software) elements.
|  |  | 1.1.7.2 | Surface/Air Missile Armament | Includes, for example:
[5 empty] | a. Mountings and Launchers b. Missile Handling Systems c. Missile Stowages |  |  |  | SAM,Effective Range, Km
SAM, No. Of Systems
|  |  | 1.1.7.3 | Surface/Surface Missile Armament | Includes, for example: |  |  |  | SSM, Effective Range, Km
[5 empty] | a. Mountings and Launchers b. Missile Handling Systems c. Missile Stowages |  |  |  | SSM, No. Mounted
|  |  | 1.1.7.4 | Anti-Submarine Armament | Includes, for example:
a. Mountings and Launchers b. Ammunition and Missile Handling Systems c. Weapon Stowages
|  |  | 1.1.7.5 | Submerged Launched (Non-Air Flight) Armament | Includes, for example:
a. Mountings and Launchers b. Weapon Handling System c. Weapon Stowages
|  |  | 1.1.7.6 | Submerged Launched (Air Flight) Armament | Includes, for example:
a. Mountings and Launchers b. Missile Handling Systems c. Missile Stowages
|  |  | 1.1.7.7 | Air Launched Armament | Includes, for example:
a. Weapon Handling System b. Weapon Stowages
|  |  | 1.1.7.8 | Mine hunting, Minelaying and Minesweeping Equipment | Includes, for example:
a. Mine hunting Equipment b. Minelaying Equipment c. Minesweeping Equipment
|  |  | 1.1.7.9 | Rocket Launchers, Small Arms and Pyrotechnic Stowages and Launchers | Includes, for example:
a. Rocket Flare and Decoy Launchers b. Small Arms Stowages c. Pyrotechnics Stowages
|  |  | 1.1.7.10 | Gun Armament | Includes, for example: |  |  |  | Armament: Primary Gun | Calibre, mm
[5 empty] | a. Mountings b. Ammunition Handling Systems c. Ammunition Stowages |  |  |  | Armament: Secondary Gun | Calibre, mm
|  |  | 1.1.7.11 | Unmanned Aerial, Surface and Submersible Vehicles (UXVs) Support Systems | Includes, for example:
a. UXV Stowage System b. UXV Handling System b. UXV Launcher System
|  |  | 1.1.7.12 | Other armament (Please specify in additional information)
|  | 1.1.8 | Ship System Software |  | All Ship / ship System software not associated with a specific Level 3 or Level 4 element.
All Ship System software not associated with a specific Level 3 or Level 4 element.
|  | 1.1.9 | Surface Ship Integration, Assembly, Test and Checkout |  | All efforts as described at the bottom of this document to provide the integration, assembly, test, and checkout of all Level 3 elements to form the air vehicle as a whole.
| 1.2 | System Engineering |  |  | The technical and management efforts of directing and controlling a totally integrated engineering effort of a system or program. Includes, for example:
a. Effort to define the system and the integrated planning and control of the technical program efforts of design engineering, specialty engineering, production engineering, and integrated test planning b. Effort associated with developing the Systems Engineering plan c. Effort to transform an operational need or statement of deficiency into a description of system requirements and a preferred system configuration d. Technical planning and control effort for planning, monitoring, measuring, evaluating, directing, and re-planning the management of the technical program e. All programs, where applicable; value engineering, configuration management, Human Systems Integration (Human factors engineering; Personnel; Habitability; Manpower; Training; Environment, Safety and Occupational Health; Survivability), vulnerability, maintainability, reliability, standardisation, system analysis, logistic support analysis, etc. f. Technical baseline management and event based technical reviews with independent subject matter expertise participation g. Cross product IPT integration h. Survivability/vulnerability analysis i. System of Systems (SoS) and System Level Architecting, modelling and simulation, verification and validation and external interface definition and management Excludes, for example: a. Actual design engineering and the production engineering directly related to the DPS element with which it is associated
| 1.3 | Programme Management |  |  | The business and administrative planning, organising, directing, coordinating, controlling, and approval actions designated to accomplish overall program objectives, which are not associated with specific hardware elements and are not included in systems engineering. Includes, for example:
a. Cost, schedule, performance measurement management, warranty administration, contract management, data management, vendor liaison, subcontract management, etc. b. Support element management, defined as the logistics tasks management effort and technical control, and the business management of the support elements. The logistics management function encompasses the support evaluation and supportability assurance required to produce an affordable and supportable defence materiel system. c. Planning and management of all the functions of logistics. Examples are: maintenance support planning and support facilities planning; other support requirements determination; support equipment requirements determination; supply support; packaging, handling, storage, and transportation; provisioning requirements determination and planning; training system requirements determination; computer resource determination; organisational, intermediate, and depot maintenance determination management; and data management
| 1.4 | Research and development |  |  | All work directed towards the innovation, introduction, and improvement of products and processes to develop the equipment type prior to testing (which is covered in 1.5) System test and evaluation
| 1.5 | System Test and Evaluation |  |  | The use of pilot, prototype, production, or specifically fabricated hardware/ software to obtain or validate engineering data on the performance of the system during the developmental phase of the program. It also includes all effort associated with the development of any specialised tools or data in support of the system level test program. Includes, for example:
a. Detailed planning, conduct, support, data reduction and reports (excluding the contract data requirements list data) from such testing, and test articles that are functionally configured to represent and test subsystems/components of the defence materiel end item being developed or produced b. Design and production of models, specimens, fixtures and instrumentation NOTE: Test articles that are functionally configured to represent and test the complete defence materiel end item being developed or produced, are excluded from this DPS element. Excludes, for example: a. All formal and informal testing up through the subsystem level, which can be associated with the hardware/software element acceptance testing NOTE: These excluded efforts are to be included with the appropriate hardware or software elements.
|  | 1.5.1 | Development Test and Evaluation |  | Includes, for example:
a. Demonstrate that the engineering design and development process is complete b. Demonstrate that the design risks have been minimised c. Demonstrate that the system will meet specifications d. Estimate the system's military utility when introduced e. Determine whether the engineering design is supportable (practical, maintainable, safe, etc.) for operational use f. Provide test data with which to examine and evaluate trade-offs against specification requirements, life cycle cost, and schedule g. Perform the logistics testing efforts to evaluate the achievement of supportability goals, the adequacy of the support package for the system, (e.g., deliverable maintenance tools, test equipment, technical publications, maintenance instructions, and personnel skills and training requirements, etc.) Includes, for example: a. All contractor/system developer in-house effort b. All programs, where applicable; models, tests and associated simulations (e.g., such as wind tunnel, static, drop, and fatigue); integration ground tests; test bed aircraft and associated support; qualification test and evaluation, development flight test, test instrumentation, environmental tests, ballistics, radiological, range and accuracy demonstrations, test facility operations, test equipment (including its support equipment), chase and calibrated pacer aircraft and support thereto, and logistics testing c. For aircraft; avionics integration test composed of the following: 1. Test bench/laboratory, including design, acquisition, and installation of basic computers and test equipments that will provide an ability to simulate in the laboratory the operational environment of the avionics system/subsystem 2. Air vehicle equipment, consisting of the avionics and/or other air vehicle subsystem modules that are required by the bench/lab or flying test bed in order to provide a compatible airframe avionics system/subsystem for evaluation purposes 3. Flying test bed, including requirements analysis, design of modifications, lease or purchase of test bed aircraft, modification of aircraft, installation of avionics equipment and instrumentation, and checkout of an existing aircraft used essentially as a flying avionics laboratory 4. Avionics test program, consisting of the effort required to develop test plans/procedures, conduct tests, and analyse hardware and software test results to verify the avionics equipments' operational capability and compatibility as an integrated air vehicle subsystem 5. Software, referring to the effort required to design, code, de-bug, and document software programs necessary to direct the avionics integration test d. For engines: engine military qualification tests and engine preliminary flight rating tests e. For sea systems: model basin, hydrostatic, fatigue, shock, special sea tests and trials, etc., trials agenda preparation, data collection and analysis; dock and sea trials; and hull vibration survey elements f. For missiles: test articles such as Inert Measurement Vehicles, Launch Separation Vehicles, Separation and Control Test Vehicles, Boost Test Vehicles g. For ordnance: test articles such as Ballistic Test rounds, Inert Measurement rounds, Dummy rounds, Launch Separation rounds, etc.
|  | 1.5.2 | Operational Test and Evaluation |  | The test and evaluation conducted by agencies other than the developing command to assess the prospective system's military utility, operational effectiveness, operational suitability, logistics supportability (including compatibility, inter-operability, reliability, maintainability, logistic requirements, etc.), cost of ownership, and need for any modifications. Includes, for example:
a. Initial operational test and evaluation conducted during the development of a system b. Such tests as system demonstration, flight tests, sea trials, mobility demonstrations, on-orbit tests, spin demonstration, stability tests, qualification operational test and evaluation, etc., and support thereto, required to prove the operational capability of the deliverable system c. Contractor support (e.g., technical assistance, maintenance, labour, material, etc.) Consumed during this phase of testing d. Logistics testing efforts to evaluate the achievement of supportability goals and the adequacy of the support for the system (e.g., deliverable maintenance tools, test equipment, technical publications, maintenance instructions, personnel skills and training requirements, and software support facility/environment elements)
|  | 1.5.3 | Mock-ups / System Integration Labs (SILs) |  | The design engineering and production of system or subsystem mock-ups that have special contractual or engineering significance or that are not required solely for the conduct of one of the above elements of testing. SILs are often used in lieu of (or in addition to) mock-ups. SILs are risk reduction facilities where software and hardware can be developed, integrated, tested and evaluated for both stand alone functionality and/or interoperability prior to being fielded. Includes, for example:
a. Hardware/Lab Equipment b. SIL Software (written to simulate the operating environment or written to operate the SIL)
|  | 1.5.4 | Test and Evaluation Support |  | The support elements necessary to operate and maintain, during test and evaluation, systems and subsystems, which are not consumed during the testing phase and are not allocated to a specific phase of testing. Includes, for example:
a. Repairable spares, repair of repairables, repair parts, consumables, warehousing and distribution of spares and repair parts, test and support equipment, test bed vehicles, drones, surveillance aircraft, tracking vessels, contractor technical support Excludes, for example: a. Operational and maintenance personnel, special fixtures, special instrumentation, etc., that are utilised and/or consumed in a single element of testing and that should be included under that element of testing
|  | 1.5.5 | Test Facilities |  | Test Facilities. The special test facilities required for performance of the various developmental tests necessary to prove the design and reliability of the system or subsystem. Includes, for example:
a. Test tank test fixtures, propulsion test fixtures, white rooms, test chambers Excludes, for example: a. Brick and mortar-type facilities identified as industrial facilities
|  | 1.5.6 | Other system test and evaluation (Please specify in additional information)
| 1.6 | Training |  |  | Deliverable training services, devices, accessories, aids, equipment, and parts used to facilitate instruction through which personnel will learn to operate and maintain the system with maximum efficiency. Includes, for example:
a. All effort associated with the design, development, and production of deliverable training equipment and its associated software as well as the execution of training services Excludes, for example: a. Overall planning, management, and task analysis function inherent in the DPS element systems engineering/program management
|  | 1.6.1 | Equipment |  | Distinctive deliverable end items of training equipment, assigned by either a contractor or military service, required to meet specific training objectives. Includes, for example:
1. Operational trainers, maintenance trainers, and other items such as cutaways, mock-ups, and models (e.g. Operational Instructional Equipment, Maintainer Instructional Equipment).
|  | 1.6.2 | Services |  | Deliverable training services, accessories, and aids necessary to accomplish the objectives of training. Includes, for example:
1. Training course materials; contractor-conducted training (in-plant and service training); and the materials and curriculum required to design, execute, and produce a contractor developed training program. (e.g. Operator Instructional Software, Maintainer Instructional Software).
2. Materiel, courses, and associated documentation (primarily the computer software, courses and training aids).
Excludes, for example:
Deliverable training data associated with the WBS element support data.
The special construction necessary to accomplish training objectives. Includes, for example:
|  | 1.6.3 | Facilities |  | 1. Modification or rehabilitation of existing training facilities and infrastructure used to accomplish training objectives.
Excludes, for example:
1. Installed equipment used to acquaint the trainee with the system or establish trainee proficiency.
2. The brick and mortar-type facilities identified as industrial facilities.
|  | 1.6.4 | Other training (Please specify in additional information)
| 1.7 | Data |  |  | The deliverable data required by the contract. Includes, for example:
1. Only such effort that can be reduced or avoided if the data item is eliminated.
2. Government-peculiar data; acquiring, assembling, reproducing, packaging and shipping the data.
3. Transforming data into Government format, reproducing and shipping data identical to that used by the contractor but in a different format.
|  | 1.7.1 | Technical Publications |  | Technical data, providing instructions for installation, operation, maintenance, training, and support, formatted into a technical manual. Data may be presented in any form regardless of the form or method of recording. Technical orders that meet the criteria of this definition may also be classified as technical manuals. Includes, for example:
1. Operation and maintenance instructions, parts lists or parts breakdown, and related technical information or procedures exclusive of administrative procedures.
2. Data item descriptions.
|  | 1.7.2 | Engineering Data |  | Recorded scientific or technical information (regardless of the form or method of recording) including computer software documentation. Engineering data defines and documents an engineering design or product configuration (sufficient to allow duplication of the original items) and is used to support production, engineering and logistics activities. Includes, for example:
1. All final plans, procedures, reports, and documentation pertaining to systems, subsystems, computer and computer resource programs, component engineering, operational testing, human factors, reliability, availability, and maintainability, and other engineering analysis.
2. Standards Department. For drawing office costs only.
3. Technical data package (re-procurement package), which includes all engineering drawings, associated lists, process descriptions, and other documents defining physical geometry, material composition, and performance procedures.
Excludes, for example:
Computer software or financial, administrative, cost or pricing, or management data or other information incidental to contract administration.
|  | 1.7.3 | Management Data |  | The data items necessary for configuration management, cost, schedule, contractual data management, program management, etc., required by the Government. Includes, for example:
1. Contractor cost reports, cost performance reports, contract funds status reports, schedules, milestones, networks, integrated support plans.
|  | 1.7.4 | Support Data |  | The data items designed to document support planning in accordance with functional categories. Includes, for e.g.
1. Supply; general maintenance plans and reports; training data; transportation, handling, storage, and packaging information; facilities data; data to support the provisioning process and all other support data; and software supportability planning and software support transition planning documents.
|  | 1.7.5 | Data Depository |  | The facility, including storage requirements, designated to act as custodian to maintain a master engineering specification and establish a drawing repository service for Government approved documents that are the property of the UK Government. As custodian for the Government, the repository, authorized by approved change orders, maintains these master documents at the latest approved revision level. This facility is a distinct entity that may hold electronic or hard copy data. Includes, for example:
1. All drafting and clerical effort necessary to maintain documents.
Excludes, for example:
All similar effort for facility’s specification and drawing control system, in support of its engineering and production activities
NOTE: When documentation is called for on a given item of data retained in the Repository, the charges (if charged as direct) will be to the appropriate data element.
|  | 1.7.6 | Other data (Please specify in additional information)
| 1.8 | Specialist Support Equipment |  |  | The design, development, and production of those deliverable items and associated software required to support and maintain the system or portions of the system while the system is not directly engaged in the performance of its mission, and which are not common support equipment. Includes, for example:
1. Vehicles, equipment, tools, etc., used to fuel, service, transport, hoist, repair, overhaul, assemble, disassemble, test, inspect, or otherwise maintain mission equipment.
2. Any production of duplicate or modified factory test or tooling equipment delivered to the Government for use in maintaining the system. (Factory test and tooling equipment initially used by the contractor in the production process but subsequently delivered to the Government will be included as cost of the item produced).
3. Any additional equipment or software required to maintain or modify the software portions of the system.
Excludes, for example:
1. Overall planning, management and task analysis functions inherent in the Work Breakdown Structure element, systems Engineering/Program Management.
2. Common support equipment, presently in the DoD inventory or commercially available, bought by the using command, not by the acquiring command
Other
|  | 1.8.1 | Test and Measurement Equipment |  | The peculiar or unique testing and measurement equipment that allows an operator or maintenance function to evaluate operational conditions of a system or equipment by performing specific diagnostics, screening or quality assurance effort at an organizational, intermediate, or depot level of equipment support. Includes, for example:
1. Test measurement and diagnostic equipment, precision measuring equipment, automatic test equipment, manual test equipment, automatic test systems, test program sets, appropriate interconnect devices, automated load modules, tapes, and related software, firmware and support hardware (power supply equipment, etc.) Used at all levels of maintenance.
2. Packages that enable line or shop replaceable units, printed circuit boards, or similar items to be diagnosed using automatic test equipment.
|  | 1.8.2 | Support and Handling Equipment |  | The deliverable tools and handling equipment used for support of the mission system. Includes, for example:
1. Ground support equipment, vehicular support equipment, powered support equipment, non-powered support equipment, munitions material handling equipment, materiel handling equipment, and software support equipment (hardware and software).
|  | 1.8.3 | Other specialist support equipment (Please specify in additional information)
| 1.9 | Common Support Equipment |  |  | The items required to support and maintain the system or portions of the system while not directly engaged in the performance of its mission, and which are presently in the MoD inventory for support of other systems. Includes, for example:
1. Acquisition of additional quantities of this equipment needed to support the item.
2. All efforts required to assure the availability of this equipment to support the item.
3. Other
|  | 1.9.1 | Test and Measurement Equipment |  | The common testing and measurement equipment that allows an operator or maintenance function to evaluate operational conditions of a system or equipment by performing specific diagnostics, screening or quality assurance effort at an organizational, intermediate, or depot level of equipment support. Includes, for example:
1. Test measurement and diagnostic equipment, precision measuring equipment, automatic test equipment, manual test equipment, automatic test systems, test program sets, appropriate interconnect devices, automated load modules, tapes, and related software, firmware and support hardware (power supply equipment, etc.) Used at all levels of maintenance.
2. Packages that enable line or shop replaceable units, printed circuit boards, or similar items to be diagnosed using automatic test equipment.
|  | 1.9.2 | Support and Handling Equipment |  | The deliverable tools and handling equipment used for support of the mission system. Includes, for example:
1. Ground support equipment, vehicular support equipment, powered support equipment, non-powered support equipment, munitions material handling equipment, materiel handling equipment, and software support equipment (hardware/software).
|  | 1.9.3 | Other common support equipment (Please specify in additional information)
| 1.1 | Operational/Site Activation |  |  | The real estate, construction, conversion, utilities, and equipment to provide all facilities required to house, service, and launch prime mission equipment at the organizational and intermediate level. Includes, for example:
1. Conversion of site, ship, or vehicle.
2. System assembly, checkout, and installation (of mission and support equipment) into site facility or ship to achieve operational status.
3. Contractor support in relation to operational/site activation.
4. Other
|  | 1.10.1 | System Assembly, Installation and Checkout on Site |  | The materials and services involved in the assembly of mission equipment at the site. Includes, for example:
1. Installation of mission and support equipment in the operations or support facilities and complete system checkout or shakedown to ensure operational status. Where appropriate, specify by site, ship or vehicle.
2. The efforts and activities associated with shipping the system from contractor facility to customer site. That site could be a DT&E site, an installation and checkout site or any similar site that is outside the direct control of the contractor.
|  | 1.10.2 | Contractor Technical Support |  | The materials and services provided by the contractor related to activation. Includes, for example:
1. Repair of repairables, standby services, final turnover.
|  | 1.10.3 | Site Construction |  | Real estate, site planning and preparation, construction, and other special-purpose facilities necessary to achieve system operational status. Includes, for example:
1. Construction of utilities, roads, and interconnecting cabling.
|  | 1.10.4 | Site/Ship/Vehicle Conversion |  | The materials and services required to convert existing sites, ships, or vehicles to accommodate the mission equipment and selected support equipment directly related to the specific system. Includes, for example:
1. Operations, support, and other special purpose facilities conversion necessary to achieve system operational status, e.g., launch. Where appropriate, specify by site, ship or vehicle.
|  | 1.10.5 | Sustainment/Interim Contractor Support |  | The complex of equipment (hardware/software), data, and services required to operate, maintain, support and modernize prime mission product of existing operational systems done before the In Service Date. Includes, for example:
1. Prime Mission Product (PMP) maintenance and modernization. The cost for this element includes maintenance and modernization (including the development and production) of existing, operational systems. It excludes the development and production of the original prime mission product.
2. Support functions required to maintain and modernize the system, such as sustaining engineering, program management, logistics support, and supply chain management.
3. Test and evaluation for system and subsystem modifications.
4. Replacement of common and peculiar support equipment.
5. Replacement of repairable items.
6. Operational, maintenance and other personnel required at the operational unit level.
7. Unit operations costs, including operating material and support services at the operating unit.
8. Installation and personnel support functions in support of the unit level manpower.
|  | 1.10.6 | Other operational/site activation (Please specify in additional information)
| 1.11 | Industrial Facilities |  |  | The construction, conversion, or expansion of industrial facilities for production, inventory, and contractor depot maintenance required when that service is for the specific system. Includes, for example:
1. Equipment acquisition or modernization, where applicable.
2. Maintenance of these facilities or equipment.
3. Industrial facilities for hazardous waste management to satisfy environmental standards.
Excludes, for example:
Capital equipment.
|  | 1.11.1 | Construction/Conversion/ Expansion |  | The real estate and preparation of system peculiar industrial facilities for production, inventory, depot maintenance, and other related activities.
|  | 1.11.2 | Equipment Acquisition or Modernization |  | The production equipment acquisition, modernization, or transferral of equipment for the particular system. This pertains to Government owned and leased equipment under facilities contract.
|  | 1.11.3 | Maintenance (Industrial Facilities) |  | The maintenance, preservation, and repair of industrial facilities and equipment.
|  | 1.11.4 | Other industrial facilities not specified above (Please specify in additional information)
| 1.12 | Initial Spares and Repair Parts |  |  | The deliverable spare components, assemblies and subassemblies used for initial replacement purposes in the materiel system equipment end item. Includes, for example:
1. Repairable spares and repair parts required as initial stock to support and maintain newly fielded systems or subsystems during the initial phase of service, including pipeline and war reserve quantities, at all levels of maintenance and support.
2. All commissioning spares. Normally excluded from contract, only include here if part of this qualifying defence contract.
Excludes, for example:
Developmental Test spares and spares provided specifically for use during installation, assembly, and checkout on site. Lower level WBS breakouts should be by subsystem.
Other (Please specify in additional information)
| 1.13 | Additional Categories Relevant to contracts for; Mid Life Update, Life Extension, Capability Sustainment |  |  | MLU or CSP will be a stand alone Qualifying Defence Contract and all costs for this activity will be apportioned to the appropriate elements of the full Sea System (SM) defined pricing structure. The two other additional cost elements (below) will be appropriate to this type of QDC.
|  | 1.13.1 | Dismantling Costs |  | Costs to strip down and prepare the donor equipment for the main MLU / CSP activity. Assembly costs will be included in the ‘Integration, Assembly, Test and Checkout’ category for each level of the hierarchal structure.
|  | 1.13.2 | Emergent Work - Work to bring enduring equipment up to 'entry' level for MLU/CSP/LEP activity |  | The work required to bring enduring equipment up to 'entry' level for MLU/CSP/LEP activity. This could include scheduled maintenance activity deferred up to delivery into MLU/CSP programme.
|  | 1.13.3 | Other additional categories (Please specify in additional information)
In service contract specific
| 1.14 | On Tools Manpower - Maintenance, Rectifications and Repair Activity |  |  | The costs included under this level 2 element will be the aggregated costs of all ‘On Tools’ contractor operators, contractor maintenance personnel and other sub contractors working directly on the equipment. All ‘Non Touch’ Manpower relating to Project and Project support activity will be recorded under 1.17.
|  | 1.14.1 | Maintenance Activities |  | This will include all ‘On Tools’ contractor operators, contractor maintenance personnel and other sub contractors at GRADE (n) working directly on the equipment. Insert a level 3 cost line for each relevant grade consuming resource in this area. Wherever possible all defined grades should match those used in the contractors Rates Claim. Where this is not the case the contractor should justify the reason why this methodology has not been adopted. All ‘Non Touch’ Manpower relating to Project and Project support activity will be recorded under 1.17.
|  |  | 1.14.1.1 | Depth maintenance activities
|  |  | 1.14.1.2 | Forward maintenance activities
|  |  | 1.14.1.3 | Other (Specify, i.e. Forward-Depth Maintenance if carried out by contractor on site)
| 1.15 | Consumables / Fungibles (Contract Specific) |  |  | These will be items which are required to fulfil the obligations of the contract. In the case of the DPS for in service contracts the consumables must not be part of the overhead of the supplier but be specific consumables and fungibles which are required for the contract. This cost is only needed at aggregated level. Consumables are materials used for the maintenance and support of systems and associated sub systems and training equipment. This will include items such as oil, fuel, coolants and de-icers. Fungibles are items which are required for the installation and integration of parts used for maintenance, such as nuts and bolts but they are interchangeable and not specific to a particular equipment type. Guidance --- Only needed at aggregated level. Should not include items that have gone through the overheads
| 1.16 | Packing, Handling, Storage and Transportation |  |  | These costs will include any specific costs associated with the movement of items up and down the supply chain in order to fulfil the obligations under the contract. They must be costs which are incurred specifically on this QDC. This cost is only needed at aggregated level. Packing – provides for the product security, transportability and storability with the added utility of serving as a medium of communication from the provider to the user. The nature of an item determines the type and extent of protection needed to prevent its deterioration during transport. The mode of shipping will dictate the materials selected for the preservation in addition to packaging. Handling – involves the moving of items from one place to another within a limited range and is normally confirmed to a single area, such as between warehouses, storage areas or operational areas or movement from storage to moved of transportation. Storage – involves the short or long term stockpiling of items. Storage can be accomplished in either temporary or permanent facilities. It may be a function of the transportation timeline or it may be required for material in reserve. Transportation – any specifically attributable transportation costs associated with the transit of items
| 1.17 | Non Touch Manpower |  |  | The costs included under this level 2 element will be the aggregated costs (by grade) of all project and project support manpower involved in; • Asset Management • Engineering & Safety • Post Design Services • Contract & Project Management • Training • Waste Management Notes All Level 3 ‘Non-Touch’ Manpower activities (1.17.1 to 1.17.7 or greater) will be split out by the relevant grade consuming resource. Wherever possible all defined grades should match those used in the contractors Rates Claim. Where this is not the case the contractor should justify the reason why this methodology has not been adopted
|  | 1.17.1 | Asset Management |  | The costs included here will be for the manpower taken to manage all assets held and used in fulfilment of the contract. The costs will be split out by the relevant grade consuming resource under this code. They will generally cover the following Level 4 activities;
|  |  | 1.17.1.1 | Planning and Optimisation | Typical activity will include the initial and ongoing consideration of the Factors influencing; Demand, Production & Overall Supply and Delivery of the product or service. Having considered all key factors and constraints the functional area will use the analysis to optimise the service delivery plan to meet contract requirements.
|  |  | 1.17.1.2 | Inventory Management | This functional area typically covers the control, ordering, storage and use of all consumable spares, materials and parts to maintain operating capability whilst minimising stock holding costs.
|  |  | 1.17.1.3 | Supply Chain Management | This functional area typically controls the flow of goods and services from the point of origin to the point of consumption.
|  |  | 1.17.1.4 | Procurement Management | This functional area typically covers the identification and sourcing of consumables, materials and parts of the correct quality and specification at the most competitive price to meet the criteria of the contract.
|  |  | 1.17.1.5 | Other Asset Management item (Please specify in additional information)
|  | 1.17.2 | Engineering and Safety |  | The costs included here will be for the manpower taken to manage all engineering support services and the safety aspects required to fulfil the contract with regard to overall System / Equipment Integrity and other legislative obligations (such as HSAW, Environmental Protection directives and regulations). The costs will be split out by the relevant grade consuming resource under this code. They will generally cover the following Level 4 activities;
|  |  | 1.17.2.1 | Air/Sea/Road Worthiness - Integrity Assurance | This functional area typically covers all activity that underpins the continued structural integrity of the equipment which in turn supports the continued assurance of safe operation within the Equipment’s defined performance envelope. This will include any mandated activities to ensure continued compliance with all requirements of any National or International Safety Board.
|  |  | 1.17.2.2 | Specialist Labour | This category will include all costs of any external specialist labour required to fulfil obligations under the contract. Note this category should not be used to capture routine sub-contract labour used to supplement prime contractor workforce.
|  |  | 1.17.2.3 | Technical Queries - On Call Support | This category will include all resource costs relating to the provision of an on call support service or technical queries to the level specified in the contract.
|  |  | 1.17.2.4 | Reliability Management | This functional area typically covers the monitoring and review of initial and continuing in service data on the performance of individual components and assemblies against the expected performance criteria. Analysis of data will then identify performance and reliability issues and feed into other engineering support areas to define remedial action to restore performance standards.
|  |  | 1.17.2.5 | Other Engineering and Safety (Please specify in additional information)
|  | 1.17.3 | Post design Services |  | Post Design Services can cover a variety of activities all designed to maintain equipment capability. The activity will vary depending on contract type but will typically include the cost for; Configuration Management, Obsolescence Management, Technical Publications, Modification Design and Prototype Testing. The costs will be split out by the relevant grade consuming resource under this code. They will generally cover the following Level 4 activities; Note – PDS normally covers costs for contractor provided training services, for DPS purposes all training costs should be recorded under the specific training category at 1.17.5.
|  |  | 1.17.3.1 | Configuration Management | For Equipment Hardware contracts this activity includes the engineering processes for establishing and maintaining consistency of product performance. This includes functional and physical attributes with the stated operating requirements, design and operational information throughout the life of the contract. For Software specific contracts this activity includes the discipline for evaluating, co-ordinating, approving and implementing changes in artefacts that are used to construct and maintain software systems.
|  |  | 1.17.3.2 | Obsolescence Management | Typically covers the costs to analyse designs and products to identify parts and components for which vendors are no longer available, or which can no longer be repaired, and to identify new vendors or interchangeable or replacement parts. It can also include costs associated with reverse engineering to identify part functionality, form-fit-function studies, materials analysis, and life cycle maturity assessments.
|  |  | 1.17.3.3 | Technical Publications | Typically covers the cost of maintaining and updating all technical support media thru the life of the contract. This would include the generation of amendment instructions to all users of the data and maintaining a master reference set of amendments detailing change history.
|  |  | 1.17.3.4 | Modifications - Assessment & Design Effort | Typically covers the cost of design effort for the proposed modification along with prototype testing. Contracts involving a major modification programme such as, Mid Life Updates, Capability Sustainment Programme or Life Extension Programme would almost certainly form a new QDC and therefore all costs for On Tools and Non Touch Manpower along with associated parts and materials would be recorded against the relevant categories of the DPS for that particular contract.
|  |  | 1.17.3.5 | Other PDS (Please specify in additional information)
|  | 1.17.4 | Post design Services (manpower) |  | These costs will be specific costs in relation to the manpower expended in managing the contract and projects under the contract. They are not general overheads but specific costs related to a particular contract. The costs will be split out by the relevant grade consuming resource under this code. They will generally cover the following Level 4 activities;
|  |  | 1.17.4.1 | Finance | This element includes costs to provide financial management, including costs vs. budget analyses, full funding assessments, appropriations and obligations management, etc. This element also includes the costs associated with the allocation of funding to tasks and work packages and assessing impacts of schedule changes on final costs.
|  |  | 1.17.4.2 | Commercial | This element will include all costs incurred in relation to the specific commercial activities undertaken for the contract.
|  |  | 1.17.4.3 | Legal | This element will include all costs incurred in relation to the specific legal activities undertaken for the contract. This will include any non recurring costs in relation to legal disputes or obligations.
|  |  | 1.17.4.4 | Senior Management - Direct to Project or Programme | This element will include the cost of any senior management required for the contract. This will only include specific costs and these should be allocated on an appropriate and proportionate basis.
|  |  | 1.17.4.5 | Programme Quality Assurance | This element includes the costs of the systematic monitoring and evaluation of the various aspects of a project or service are fit for the intended purpose as defined in the Statement of Requirement and that sufficient control and feedback is generated to assure continuing conformity, generating corrective action or improvements where necessary.
|  |  | 1.17.4.6 | Data Management | This element includes all costs of data collection and analysis to assess the effectiveness of the contract. It can also include any explicit data capture and analysis as mandated in the contract requirements.
|  |  | 1.17.4.7 | Security / Insurance | This element includes the cost to provide and maintain physical security such as perimeter fences and gates, guard stations, closed circuit and electronic monitoring, badging and access control. It also includes protection from and remediation for damage from natural and manmade disasters, accidents, electrical power losses and spikes, fire and theft etc. Insurance will include any costs for specific insurances relating to the fulfilment of the contract.
|  |  | 1.17.4.8 | Other Contract and Project Management activity (Please specify in additional information)
|  | 1.17.5 | In service Training costs |  | These costs will cover the costs associated with the delivery of specific training requirements as required in the execution of the contract. The costs will be split out by the relevant grade consuming resource under this code. They will generally cover the following Level 4 activities;
|  |  | 1.17.5.1 | Operator or Maintainer Training | Delivery of Initial and Refresher training for Operators and Maintenance staff. This could be at contractor’s site or MoD establishment.
|  |  | 1.17.5.2 | Project Specific Training | Attendance of project staff on specific training courses required by personnel in execution of the specific contract roles.
|  |  | 1.17.5.3 | Other training (Please specify in additional information)
|  | 1.17.6 | Disposal / Waste Management |  | These costs will cover the management costs associated with the maintenance obligations completed under the contract. The costs will be split out by the relevant grade consuming resource under this code.
|  | 1.17.7 | Other Maintenance Management activity (Specify)
| 1.18 | Specialist Equipment |  |  | These costs will include any costs associated with the purchase of specialist equipment required to fulfil the obligations of the contract.
|  | 1.18.1 | Rigs, Jigs and Support Equipment (all-up) |  | This element will include costs incurred in relation to any specialist support equipment. Including Rigs, Jigs and Specialist Support Equipment. Specialist equipment – specialist equipment means any equipment which is specifically required for the contractor’s obligation under the contract.
|  |  | 1.18.1.1 | Special To Type Support Equipment | Equipment unique to this particular contract or Major Equipment. This will typically include maintenance, upkeep and replacement costs of specialist lifting equipment or ground handling equipment.
|  |  | 1.18.1.2 | Common Support Equipment | Support Equipment that is in common use (2 or more equipments.) across the Defence Inventory. This will typically include maintenance, upkeep and replacement of the equipment.
|  |  | 1.18.1.3 | Other support equipment (Please specify in additional information)
|  | 1.18.2 | Testing and Diagnostics |  | These costs will cover any specialist equipment required for testing and diagnostics purposes. These equipment types typically confirm the existence of a fault and possibly identify and sentence the sub-system, line replacement unit or component causing the fault. The cost category will capture the costs of usage, maintenance, upkeep and replacement.
|  |  | 1.18.2.1 | Special To Type Test Equipment | Testing & Diagnostic Equipment unique to this particular contract or Major Equipment. Equipment would typically download fault codes or run diagnostic scenarios in controlled sequence to identify and sentence fault. Costs will include maintenance, upkeep and replacement of the equipment.
|  |  | 1.18.2.2 | Common Test Equipment | Functionality as 1.18.2.1 where the equipment is in common use (2 or more equipments.) across the Defence Inventory. Costs will typically include maintenance, upkeep and replacement of the equipment.
|  |  | 1.18.2.3 | Other test equipment (Please specify in additional information)
|  | 1.18.3 | Specialist Facilities |  | This category will include the costs of any specialist facilities required to fulfil the obligations of the contract. The facility will meet or facilitate a specific contract requirement and will be for the exclusive use of the contract. Any cost of surplus capacity should be bourne by the contractor unless there is a specific contract requirement to maintain surge capacity or expansion options
|  |  | 1.18.3.1 | Rent of premises | This will include the rental costs of premises required to fulfil obligations under the contract. Where only part of the rented premises is required, then an appropriate and reasonable apportionment of the costs should be included here if they are costs which have been taken on for the purpose of the contract. If the cost of the premises would have been absorbed by the contractor regardless of the contract they should NOT be included.
|  |  | 1.18.3.2 | Major Training Equipment - Simulators & STE (specify) | This will include the costs of usage, maintenance, upkeep and replacement of any major training equipment including the operational simulators and advanced synthetic training environments.
|  |  | 1.18.3.3 | Conversion and Expansion | This will include the costs of converting or expanding existing assets for use on the specified contract. The cost of conversion / expansion must be derived from a definite need and the contractor should prove the costs are the most economic means of meeting the requirement.
|  |  | 1.18.3.4 | Maintenance of specialist facilities | This will include the costs of maintaining the specialist facility throughout the life of the contract. Maintenance activity should be commensurate and appropriate to the operating use and local environment. If the facility is not used exclusively for the contract then the cost should be apportioned on a reasonable basis.
|  |  | 1.18.3.5 | Other specialist facilities item (Please specify in additional information)
|  | 1.18.4 | Individual or Small Scale Modifications |  | This element includes the cost of parts and materials required for small scale routine modifications to the equipment. Because these items will cover routine modifications the materiality the cost may be captured at aggregated level.
|  | 1.18.5 | Specialist IT |  | This element includes the cost of any specialist IT required to fulfil obligations of the contract. If the Specialist IT or any level 4 component is used in other areas of the contractors business then the contract shall only bear a proportion of the costs commensurate with a reasonable basis of apportionment.
|  |  | 1.18.5.1 | Specialist Software | This element includes the cost of any specialist software. Software is intangible programmes, libraries and applications used for the operation of computers. - Specialist Software Licences. - This element includes the cost of software licences, either enterprise-wide or seat based. - Technology Refresh. - This element includes the costs of the periodic replacement of computers and peripherals to maintain operating functionality and business efficacy in relation to contract delivery.
|  |  | 1.18.5.2 | Specialist Hardware | This element includes the cost of any specialist hardware. Computer hardware is the physical element of a computer system.
|  |  | 1.18.5.3 | Maintenance of specialist IT | This cost is only valid to the contract if the maintenance of the specialist IT is performed by dedicated support staff. If the IT is maintained by routine staff who maintain all other IT then this cost should be part of the overhead.
|  |  | 1.18.5.4 | Other specialist IT equipment (Please specify in additional information)
|  | 1.18.6 | Other - all other cost categories not covered elsewhere (Please specify in additional information)

## Dropdown menu lists (hidden)
|  | CPV code (1st revision) |  |  | UNSPSC Code (1st revision)
1 Surface Ship |  | 35512000 | Ships |  | 25111701 | Frigates
|  |  |  | CPVL11 |  |  | UNSPSCL11
1.1 | Surface ship | 31000000 | Electrical machinery, apparatus, equipment and consumables; Lighting | 31000000 Electrical machinery, apparatus, equipment and consumables; Lighting | 12000000 | Chemicals including Bio Chemicals and Gas Materials | 12000000 Chemicals including Bio Chemicals and Gas Materials |  | Other
|  | 32000000 | Radio, television, communication, telecommunication and related equipment | 32000000 Radio, television, communication, telecommunication and related equipment | 24000000 | Material Handling and Conditioning and Storage Machinery and their Accessories and Supplies | 24000000 Material Handling and Conditioning and Storage Machinery and their Accessories and Supplies
|  | 33000000 | Medical equipments, pharmaceuticals and personal care products | 33000000 Medical equipments, pharmaceuticals and personal care products | 25000000 | Commercial and Military and Private Vehicles and their Accessories and Components | 25000000 Commercial and Military and Private Vehicles and their Accessories and Components
|  | 34000000 | Transport equipment and auxiliary products to transportation | 34000000 Transport equipment and auxiliary products to transportation | 26000000 | Power Generation and Distribution Machinery and Accessories | 26000000 Power Generation and Distribution Machinery and Accessories
|  | 35000000 | Security, fire-fighting, police and defence equipment | 35000000 Security, fire-fighting, police and defence equipment | 26000000 | Power Generation and Distribution Machinery and Accessories | 26000000 Power Generation and Distribution Machinery and Accessories
|  | 38000000 | Laboratory, optical and precision equipments (excl. glasses) | 38000000 Laboratory, optical and precision equipments (excl. glasses) | 30000000 | Structures and Building and Construction and Manufacturing Components and Supplies | 30000000 Structures and Building and Construction and Manufacturing Components and Supplies
|  | 39000000 | Furniture (incl. office furniture), furnishings, domestic appliances (excl. lighting) and cleaning products | 39000000 Furniture (incl. office furniture), furnishings, domestic appliances (excl. lighting) and cleaning products | 31000000 | Manufacturing Components and Supplies | 31000000 Manufacturing Components and Supplies
|  | 42000000 | Industrial machinery | 42000000 Industrial machinery | 39000000 | Electrical Systems and Lighting and Components and Accessories and Supplies | 39000000 Electrical Systems and Lighting and Components and Accessories and Supplies
|  | 44000000 | Construction structures and materials; auxiliary products to construction (excepts electric apparatus) | 44000000 Construction structures and materials; auxiliary products to construction (excepts electric apparatus) | 40000000 | Distribution and Conditioning Systems and Equipment and Components | 40000000 Distribution and Conditioning Systems and Equipment and Components
|  | 45000000 | Construction work | 45000000 Construction work | 41000000 | Laboratory and Measuring and Observing and Testing Equipment | 41000000 Laboratory and Measuring and Observing and Testing Equipment
|  | 48000000 | Software package and information systems | 48000000 Software package and information systems | 42000000 | Medical Equipment and Accessories and Supplies | 42000000 Medical Equipment and Accessories and Supplies
|  | 51000000 | Installation services (except software) | 51000000 Installation services (except software) | 43000000 | Information Technology Broadcasting and Telecommunications | 43000000 Information Technology Broadcasting and Telecommunications
|  | 63000000 | Supporting and auxiliary transport services; travel agencies services | 63000000 Supporting and auxiliary transport services; travel agencies services | 46000000 | Defense and Law Enforcement and Security and Safety Equipment and Supplies | 46000000 Defense and Law Enforcement and Security and Safety Equipment and Supplies
|  | 71000000 | Architectural, construction, engineering and inspection services | 71000000 Architectural, construction, engineering and inspection services | 47000000 | Cleaning Equipment and Supplies | 47000000 Cleaning Equipment and Supplies
|  | 90000000 | Sewage-, refuse-, cleaning-, and environmental services | 90000000 Sewage-, refuse-, cleaning-, and environmental services | 55000000 | Published Products | 55000000 Published Products
[5 empty] | 56000000 | Furniture and Furnishings | 56000000 Furniture and Furnishings
[5 empty] | 72000000 | Building and Facility Construction and Maintenance Services | 72000000 Building and Facility Construction and Maintenance Services
[5 empty] | 73000000 | Industrial Production and Manufacturing Services | 73000000 Industrial Production and Manufacturing Services
[5 empty] | 76000000 | Industrial Cleaning Services | 76000000 Industrial Cleaning Services
[5 empty] | 80000000 | Management and Business Professionals and Administrative Services | 80000000 Management and Business Professionals and Administrative Services
[5 empty] | 81000000 | Engineering and Research and Technology Based Services | 81000000 Engineering and Research and Technology Based Services
|  |  |  | CPVL111N |  |  | UNSPSCL111
1.1.1 | Hull and Superstructure | 31300000 | Insulated wire and cable | 31300000 Insulated wire and cable | 24100000 | Material handling machinery and equipment | 24100000 Material handling machinery and equipment
|  | 35500000 | Warships and associated parts | 35500000 Warships and associated parts | 24110000 | Containers and storage | 24110000 Containers and storage
|  | 39700000 | Domestic appliances | 39700000 Domestic appliances | 25110000 | Marine transport | 25110000 Marine transport
|  | 42500000 | Cooling and ventilation equipment | 42500000 Cooling and ventilation equipment | 26000000 | Power Generation and Distribution Machinery and Accessories | 26000000 Power Generation and Distribution Machinery and Accessories
|  | 44100000 | Construction materials and associated items | 44100000 Construction materials and associated items | 30000000 | Structures and Building and Construction and Manufacturing Components and Supplies | 30000000 Structures and Building and Construction and Manufacturing Components and Supplies
|  | 44200000 | Structural products | 44200000 Structural products | 31000000 | Manufacturing Components and Supplies | 31000000 Manufacturing Components and Supplies
|  | 44300000 | Cable, wire and related products | 44300000 Cable, wire and related products | 39000000 | Electrical Systems and Lighting and Components and Accessories and Supplies | 39000000 Electrical Systems and Lighting and Components and Accessories and Supplies
|  | 45200000 | Works for complete or part construction and civil engineering work | 45200000 Works for complete or part construction and civil engineering work | 40100000 | Heating and ventilation and air circulation | 40100000 Heating and ventilation and air circulation
|  | 48000000 | Software package and information systems | 48000000 Software package and information systems | 40170000 | Pipe piping and pipe fittings | 40170000 Pipe piping and pipe fittings
|  | 51100000 | Installation services of electrical and mechanical equipment | 51100000 Installation services of electrical and mechanical equipment | 43230000 | Software | 43230000 Software
|  | 71300000 | Engineering services | 71300000 Engineering services | 43230000 | Software | 43230000 Software
|  | 42600000 | Machine tools | 42600000 Machine tools | 72000000 | Building and Facility Construction and Maintenance Services | 72000000 Building and Facility Construction and Maintenance Services
[5 empty] | 73150000 | Manufacturing support services | 73150000 Manufacturing support services
[5 empty] | 73180000 | Machining and processing services | 73180000 Machining and processing services
[5 empty] | 81100000 | Professional engineering services | 81100000 Professional engineering services
[5 empty] | 81110000 | Computer services | 81110000 Computer services
|  | rr |  | CPVL1111 |  |  | UNSPSCL1111
1.1.1.1 | Hull and Superstructure Subsystem Integration, Assembly, Test, and Checkout | 35520000 | Parts of war ships | 35520000 Parts of war ships | 30000000 | Structures and Building and Construction and Manufacturing Components and Supplies | 30000000 Structures and Building and Construction and Manufacturing Components and Supplies
|  | 44110000 | Construction materials | 44110000 Construction materials | 31000000 | Manufacturing Components and Supplies | 31000000 Manufacturing Components and Supplies
|  | 44162000 | Piping | 44162000 Piping | 40170000 | Pipe piping and pipe fittings | 40170000 Pipe piping and pipe fittings
|  | 44316400 | Hardware | 44316400 Hardware | 43230000 | Software | 43230000 Software
|  | 45223100 | Assembly of metal structures | 45223100 Assembly of metal structures | 73151501 | Assembly line work | 73151501 Assembly line work
|  | 45223800 | Assembly and erection of prefabricated structures | 45223800 Assembly and erection of prefabricated structures | 73151502 | Joint sealing services | 73151502 Joint sealing services
|  | 45223820 | Prefabricated units and components | 45223820 Prefabricated units and components | 73151503 | Original design and manufacturing service | 73151503 Original design and manufacturing service
|  | 48000000 | Software package and information systems | 48000000 Software package and information systems | 73151504 | Electronics manufacturing service | 73151504 Electronics manufacturing service
|  | 71300000 | Engineering services | 71300000 Engineering services | 73151505 | Sequenced delivery service | 73151505 Sequenced delivery service
[5 empty] | 73151506 | Final or sub-assembly service | 73151506 Final or sub-assembly service
[5 empty] | 81101600 | Mechanical engineering | 81101600 Mechanical engineering
[5 empty] | 81101700 | Electrical and electronic engineering | 81101700 Electrical and electronic engineering
[5 empty] | 81110000 | Computer services | 81110000 Computer services
|  |  |  | CPVL1112 |  |  | UNSPSCL1112
1.1.1.2 | Hull Structure | 35520000 | Parts for warships | 35520000 Parts for warships | 30000000 | Structures and Building and Construction and Manufacturing Components and Supplies | 30000000 Structures and Building and Construction and Manufacturing Components and Supplies
|  | 35521000 | Hull and mechanical spare parts for warships | 35521000 Hull and mechanical spare parts for warships | 31000000 | Manufacturing Components and Supplies | 31000000 Manufacturing Components and Supplies
|  | 44210000 | Structures and parts of structures | 44210000 Structures and parts of structures | 39000000 | Electrical Systems and Lighting and Components and Accessories and Supplies | 39000000 Electrical Systems and Lighting and Components and Accessories and Supplies
|  | 45262000 | Special trade construction works other than roof works | 45262000 Special trade construction works other than roof works | 73180000 | Machining and processing services | 73180000 Machining and processing services
|  | 51145000 | Installation services of marine engines | 51145000 Installation services of marine engines
|  |  |  | CPVL1113N |  |  | UNSPSCL1113
1.1.1.3 | Superstructure | 35521000 | Hull and mechanical spare parts for warships | 35521000 Hull and mechanical spare parts for warships | 30000000 | Structures and Building and Construction and Manufacturing Components and Supplies | 30000000 Structures and Building and Construction and Manufacturing Components and Supplies
|  | 44210000 | Structures and parts of structures | 44210000 Structures and parts of structures
|  | 42630000 | Metal-working machine tools | 42630000 Metal-working machine tools
|  |  |  | CPVL1114 |  |  | UNSPSCL1114
1.1.1.4 | Structural Bulkheads | 35520000 | Parts for warships | 35520000 Parts for warships | 30000000 | Structures and Building and Construction and Manufacturing Components and Supplies | 30000000 Structures and Building and Construction and Manufacturing Components and Supplies
|  |  |  | CPVL1115 |  |  | UNSPSCL1115
1.1.1.5 | Structural decks | 44210000 | Structures and parts of structures | 44210000 Structures and parts of structures | 24110000 | Containers and storage | 24110000 Containers and storage
[5 empty] | 26140000 | Atomic and nuclear energy machinery and equipment | 26140000 Atomic and nuclear energy machinery and equipment
|  |  |  | CPVL1116 |  |  | UNSPSCL1116
1.1.1.6 | Bridge Windows, Sidelights, Doors, Hatches and Scuttles | 44316400 | Hardware | 44316400 Hardware | 25110000 | Marine transport | 25110000 Marine transport
[5 empty] | 30000000 | Structures and Building and Construction and Manufacturing Components and Supplies | 30000000 Structures and Building and Construction and Manufacturing Components and Supplies
|  |  |  | CPVL1117 |  |  | UNSPSCL1117
1.1.1.7 | Seats, supports and masts | 31300000 | Insulated wire and cable | 31300000 Insulated wire and cable | 31000000 | Manufacturing Components and Supplies | 31000000 Manufacturing Components and Supplies
|  | 39717200 | Air-conditioning appliances | 39717200 Air-conditioning appliances | 26000000 | Power Generation and Distribution Machinery and Accessories | 26000000 Power Generation and Distribution Machinery and Accessories
|  | 42514000 | Machinery and apparatus for filtering or purifying gases | 42514000 Machinery and apparatus for filtering or purifying gases | 39000000 | Electrical Systems and Lighting and Components and Accessories and Supplies | 39000000 Electrical Systems and Lighting and Components and Accessories and Supplies
|  | 44162000 | Piping | 44162000 Piping | 40100000 | Heating and ventilation and air circulation | 40100000 Heating and ventilation and air circulation
|  | 48780000 | System, storage and content management software package | 48780000 System, storage and content management software package
|  |  |  | CPVL1118 |  |  | UNSPSCL1118
1.1.1.8 | Penetrations | 48781000 | System management software package | 48781000 System management software package
|  |  |  | CPVL1119 |  |  | UNSPSCL1119
1.1.1.8 | Control Surfaces |  |  |  | 31000000 | Manufacturing Components and Supplies | 31000000 Manufacturing Components and Supplies
|  |  |  | CPVL11110 |  |  | UNSPSCL11110
1.1.1.10 | Constructional services | 71310000 | Consultative engineering and construction services | 71310000 Consultative engineering and construction services | 72000000 | Building and Facility Construction and Maintenance Services | 72000000 Building and Facility Construction and Maintenance Services
|  |  |  | CPVL112 |  |  | UNSPSCL112
1.1.2 | Propulsion | 31100000 | Electric motors, generators and transformers | 31100000 Electric motors, generators and transformers | 25110000 | Marine transport | 25110000 Marine transport
|  | 31400000 | Accumulators, primary cells and primary batteries | 31400000 Accumulators, primary cells and primary batteries | 25170000 | Transportation components and systems | 25170000 Transportation components and systems
|  | 34300000 | Parts and accessories for vehicles and their engines | 34300000 Parts and accessories for vehicles and their engines | 26100000 | Power sources | 26100000 Power sources
|  | 35500000 | Warships and associated parts | 35500000 Warships and associated parts | 26110000 | Batteries and generators and kinetic power transmission | 26110000 Batteries and generators and kinetic power transmission
|  | 42100000 | Machinery for the production and use of mechanical power | 42100000 Machinery for the production and use of mechanical power | 26130000 | Power generation | 26130000 Power generation
|  | 44100000 | Construction materials and associated items | 44100000 Construction materials and associated items | 26140000 | Atomic and nuclear energy machinery and equipment | 26140000 Atomic and nuclear energy machinery and equipment
|  | 44300000 | Cable, wire and related products | 44300000 Cable, wire and related products | 30000000 | Structures and Building and Construction and Manufacturing Components and Supplies | 30000000 Structures and Building and Construction and Manufacturing Components and Supplies
|  | 45200000 | Works for complete or part construction and civil engineering work | 45200000 Works for complete or part construction and civil engineering work | 31000000 | Manufacturing Components and Supplies | 31000000 Manufacturing Components and Supplies
|  | 45300000 | Building installation work | 45300000 Building installation work | 40000000 | Distribution and Conditioning Systems and Equipment and Components | 40000000 Distribution and Conditioning Systems and Equipment and Components
|  | 48700000 | Software package utilities | 48700000 Software package utilities | 43230000 | Software | 43230000 Software
|  | 71300000 | Engineering services | 71300000 Engineering services | 73150000 | Manufacturing support services | 73150000 Manufacturing support services
[5 empty] | 81100000 | Professional engineering services | 81100000 Professional engineering services
[5 empty] | 81110000 | Computer services | 81110000 Computer services
|  |  |  | CPVL1121 |  |  | UNSPSCL1121
1.1.2.1 | Propulsion Integration, Assembly, Test, and Checkout | 35520000 | Parts of war ships | 35520000 Parts of war ships | 30000000 | Structures and Building and Construction and Manufacturing Components and Supplies | 30000000 Structures and Building and Construction and Manufacturing Components and Supplies
|  | 44110000 | Construction materials | 44110000 Construction materials | 31000000 | Manufacturing Components and Supplies | 31000000 Manufacturing Components and Supplies
|  | 44162000 | Piping | 44162000 Piping | 40170000 | Pipe piping and pipe fittings | 40170000 Pipe piping and pipe fittings
|  | 44162000 | Piping | 44162000 Piping | 43230000 | Software | 43230000 Software
|  | 44316400 | Hardware | 44316400 Hardware | 73151501 | Assembly line work | 73151501 Assembly line work
|  | 45223100 | Assembly of metal structures | 45223100 Assembly of metal structures | 73151502 | Joint sealing services | 73151502 Joint sealing services
|  | 45223800 | Assembly and erection of prefabricated structures | 45223800 Assembly and erection of prefabricated structures | 73151503 | Original design and manufacturing service | 73151503 Original design and manufacturing service
|  | 45223820 | Prefabricated units and components | 45223820 Prefabricated units and components | 73151504 | Electronics manufacturing service | 73151504 Electronics manufacturing service
|  | 48000000 | Software package and information systems | 48000000 Software package and information systems | 73151505 | Sequenced delivery service | 73151505 Sequenced delivery service
|  | 71300000 | Engineering services | 71300000 Engineering services | 73151506 | Final or sub-assembly service | 73151506 Final or sub-assembly service
|  | 71330000 | Miscellaneous engineering services | 71330000 Miscellaneous engineering services | 81101600 | Mechanical engineering | 81101600 Mechanical engineering
|  | 71340000 | Integrated engineering services | 71340000 Integrated engineering services | 81101700 | Electrical and electronic engineering | 81101700 Electrical and electronic engineering
|  | 71350000 | Engineering-related scientific and technical services | 71350000 Engineering-related scientific and technical services | 81110000 | Computer services | 81110000 Computer services
|  |  |  | CPVL1122 |  |  | UNSPSCL1122
1.1.2.2 & 1.1.2.3 | Propulsion Power Plant (Nuclear) | 35522000 | Electronic and electrical spare parts for warships | 35522000 Electronic and electrical spare parts for warships | 26101105 | Heating and cooling system motor AC | 26101105 Heating and cooling system motor AC
|  |  |  | CPVL1123 |  |  | UNSPSCL1123
1.1.2.9 | Circulating and Cooling Water Systems, Feed Water and Condensate Systems | 42100000 | Machinery for the production and use of mechanical power | 42100000 Machinery for the production and use of mechanical power | 40100000 | Heating and ventilation and air circulation | 40100000 Heating and ventilation and air circulation
|  |  |  | CPVL1124 |  |  | UNSPSCL1124
1.1.2.7 | Combustion Air Supply and Exhaust Systems |  |  |  | 26140000 | Atomic and nuclear energy machinery and equipment | 26140000 Atomic and nuclear energy machinery and equipment
|  |  |  | CPVL1125 |  |  | UNSPSCL1125
1.1.2.4 | Propulsion Units and Control Equipment |  |  |  | 26140000 | Atomic and nuclear energy machinery and equipment | 26140000 Atomic and nuclear energy machinery and equipment
|  |  |  | CPVL1126 |  |  | UNSPSCL1126
1.1.2.6 | Reactor Shielding |  |  |  | 26140000 | Atomic and nuclear energy machinery and equipment | 26140000 Atomic and nuclear energy machinery and equipment
|  |  |  | CPVL1127 |  |  | UNSPSCL1127
1.1.2.7 | Miscellaneous Propulsion Items | 45300000 | Building installation work | 45300000 Building installation work | 30140000 | Insulation | 30140000 Insulation
|  |  |  | CPVL1128 |  |  | UNSPSCL1128
1.1.2.5 | Main Condensers and Air Ejectors | 31100000 | Electric motors, generators and transformers | 31100000 Electric motors, generators and transformers | 26101100 | Electric alternating current AC motors | 26101100 Electric alternating current AC motors
[5 empty] | 26101200 | Electric direct current DC motors | 26101200 Electric direct current DC motors
[5 empty] | 26101300 | Non electric motors | 26101300 Non electric motors
[5 empty] | 26101500 | Engines | 26101500 Engines
[5 empty] | 26111710 | Product specific battery packs | 26111710 Product specific battery packs
|  |  |  | CPVL1129 |  |  | UNSPSCL1129
1.1.2.8 | Steam Systems | 44163000 | Pipes and fittings | 44163000 Pipes and fittings | 40000000 | Distribution and Conditioning Systems and Equipment and Components | 40000000 Distribution and Conditioning Systems and Equipment and Components
[5 empty] | 26131600 | Exhaust structures or screening equipment | 26131600 Exhaust structures or screening equipment
|  |  |  | CPVL11210 |  |  | UNSPSCL11210
1.1.2.10 | Fuel Oil Service Systems | 42113150 | Lubricating oil systems | 42113150 Lubricating oil systems | 25172800 | Hydraulic systems and components | 25172800 Hydraulic systems and components
|  | 42124000 | Parts of pumps, compressors, engines or motors | 42124000 Parts of pumps, compressors, engines or motors | 40160000 | Industrial filtering and purification | 40160000 Industrial filtering and purification
|  |  |  | CPVL11211 |  |  | UNSPSCL11211
1.1.2.6 | Shafting, Bearings and Propulsors | 31100000 | Electric motors, generators and transformers | 31100000 Electric motors, generators and transformers | 25111900 | Marine craft systems and subassemblies | 25111900 Marine craft systems and subassemblies
[5 empty] | 26101100 | Electric alternating current AC motors | 26101100 Electric alternating current AC motors
[5 empty] | 26101200 | Electric direct current DC motors | 26101200 Electric direct current DC motors
[5 empty] | 26111710 | Product specific battery packs | 26111710 Product specific battery packs
|  |  |  | CPVL113 |  |  | UNSPSCL113
1.1.3 | Electrical | 31100000 | Electric motors, generators and transformers | 31100000 Electric motors, generators and transformers | 26100000 | Power sources | 26100000 Power sources
|  | 31200000 | Electricity distribution and control apparatus | 31200000 Electricity distribution and control apparatus | 26120000 | Electrical wire and cable and harness | 26120000 Electrical wire and cable and harness
|  | 31300000 | Insulated wire and cable | 31300000 Insulated wire and cable | 30000000 | Structures and Building and Construction and Manufacturing Components and Supplies | 30000000 Structures and Building and Construction and Manufacturing Components and Supplies
|  | 31500000 | Lighting equipment and electric lamps | 31500000 Lighting equipment and electric lamps | 31000000 | Manufacturing Components and Supplies | 31000000 Manufacturing Components and Supplies
|  | 31600000 | Electrical equipment and apparatus | 31600000 Electrical equipment and apparatus | 39100000 | Lamps and lightbulbs and lamp components | 39100000 Lamps and lightbulbs and lamp components
|  | 34300000 | Parts and accessories for vehicles and their en | 34300000 Parts and accessories for vehicles and their en | 39120000 | Electrical equipment and components and supplies | 39120000 Electrical equipment and components and supplies
|  | 35500000 | Warships and associated parts | 35500000 Warships and associated parts | 40170000 | Pipe piping and pipe fittings | 40170000 Pipe piping and pipe fittings
|  | 42100000 | Machinery for the production and use of mechanical power | 42100000 Machinery for the production and use of mechanical power | 43230000 | Software | 43230000 Software
|  | 44100000 | Construction materials and associated items | 44100000 Construction materials and associated items | 73150000 | Manufacturing support services | 73150000 Manufacturing support services
|  | 44300000 | Cable, wire and related products | 44300000 Cable, wire and related products | 81100000 | Professional engineering services | 81100000 Professional engineering services
|  | 45200000 | Works for complete or part construction and civil engineering work | 45200000 Works for complete or part construction and civil engineering work | 81110000 | Computer services | 81110000 Computer services
|  | 48700000 | Software package utilities | 48700000 Software package utilities
|  | 71300000 | Engineering services | 71300000 Engineering services
|  |  |  | CPVL1131 |  |  | UNSPSCL1131
1.1.3.1 | Electrical Integration, Assembly, Test, and Checkout | 31100000 | Electric motors, generators and transformers | 31100000 Electric motors, generators and transformers | 26101100 | Electric alternating current AC motors | 26101100 Electric alternating current AC motors
|  | 35520000 | Parts of war ships | 35520000 Parts of war ships | 26101200 | Electric direct current DC motors | 26101200 Electric direct current DC motors
|  | 44110000 | Construction materials | 44110000 Construction materials | 26101300 | Non electric motors | 26101300 Non electric motors
|  | 44162000 | Piping | 44162000 Piping | 26101500 | Engines | 26101500 Engines
|  | 44316400 | Hardware | 44316400 Hardware | 30000000 | Structures and Building and Construction and Manufacturing Components and Supplies | 30000000 Structures and Building and Construction and Manufacturing Components and Supplies
|  | 45223100 | Assembly of metal structures | 45223100 Assembly of metal structures | 31000000 | Manufacturing Components and Supplies | 31000000 Manufacturing Components and Supplies
|  | 45223800 | Assembly and erection of prefabricated structures | 45223800 Assembly and erection of prefabricated structures | 40170000 | Pipe piping and pipe fittings | 40170000 Pipe piping and pipe fittings
|  | 45223820 | Prefabricated units and components | 45223820 Prefabricated units and components | 43230000 | Software | 43230000 Software
|  | 48780000 | System, storage and content management software package | 48780000 System, storage and content management software package | 73151501 | Assembly line work | 73151501 Assembly line work
|  | 71310000 | Consultative engineering and construction services | 71310000 Consultative engineering and construction services | 73151502 | Joint sealing services | 73151502 Joint sealing services
|  | 71320000 | Engineering design services | 71320000 Engineering design services | 73151503 | Original design and manufacturing service | 73151503 Original design and manufacturing service
|  | 71330000 | Miscellaneous engineering services | 71330000 Miscellaneous engineering services | 73151504 | Electronics manufacturing service | 73151504 Electronics manufacturing service
|  | 71340000 | Integrated engineering services | 71340000 Integrated engineering services | 73151505 | Sequenced delivery service | 73151505 Sequenced delivery service
|  | 71350000 | Engineering-related scientific and technical services | 71350000 Engineering-related scientific and technical services | 73151506 | Final or sub-assembly service | 73151506 Final or sub-assembly service
[5 empty] | 81101600 | Mechanical engineering | 81101600 Mechanical engineering
[5 empty] | 81101700 | Electrical and electronic engineering | 81101700 Electrical and electronic engineering
[5 empty] | 81110000 | Computer services | 81110000 Computer services
[5 empty] | 81111500 | Software or hardware engineering | 81111500 Software or hardware engineering
|  |  |  | CPVL1132 |  |  | UNSPSCL1132
1.1.3.4 | Power Distribution Cabling | 31600000 | Electrical equipment and apparatus | 31600000 Electrical equipment and apparatus | 26120000 | Electrical wire and cable and harness | 26120000 Electrical wire and cable and harness
|  | 31200000 | Electricity distribution and control apparatus | 31200000 Electricity distribution and control apparatus | 39120000 | Electrical equipment and components and supplies | 39120000 Electrical equipment and components and supplies
|  | 31300000 | Insulated wire and cable | 31300000 Insulated wire and cable | 73152108 | Electrical equipment maintenance and repair service | 73152108 Electrical equipment maintenance and repair service
|  |  |  | CPVL1133N |  |  | UNSPSCL1133N
1.1.3.2 | Electrical Power Generation Equipment & mechanical systems | 31100000 | Electric motors, generators and transformers | 31100000 Electric motors, generators and transformers | 26101100 | Electric alternating current AC motors | 26101100 Electric alternating current AC motors
|  | 42100000 | Machinery for the production and use of mechanical power | 42100000 Machinery for the production and use of mechanical power | 26101200 | Electric direct current DC motors | 26101200 Electric direct current DC motors
1.1.3.4 | Electrical Power Generation- Mechanical Systems | 34311000 | Engines | 34311000 Engines | 26101300 | Non electric motors | 26101300 Non electric motors
|  | 42121000 | Hydraulic or pneumatic power engines and motors | 42121000 Hydraulic or pneumatic power engines and motors | 26101500 | Engines | 26101500 Engines
|  | 42163000 | Steam generators | 42163000 Steam generators
|  |  |  | CPVL1135 |  |  | UNSPSCL1135
1.1.3.3 | Power Distribution Equipment | 71314100 | Electrical services | 71314100 Electrical services | 39120000 | Electrical equipment and components and supplies | 39120000 Electrical equipment and components and supplies
|  |  |  | CPVL1136 |  |  | UNSPSCL1136
1.1.3.5 | Lighting Systems | 31000000 | Electrical machinery, apparatus, equipment and consumables; lighting | 31000000 Electrical machinery, apparatus, equipment and consumables; lighting | 39100000 | Lamps and lightbulbs and lamp components | 39100000 Lamps and lightbulbs and lamp components
|  |  |  | CPVL1137 |  |  | UNSPSCL1137
1.1.3.7 | Sundry Electrical Labour |  |  |  | 72151500 | Electrical system services | 72151500 Electrical system services
|  |  |  | CPVL1138 |  |  | UNSPSCL1138
1.1.3.8 | Misc Electrical Work |  |  |  | 72151500 | Electrical system services | 72151500 Electrical system services
|  |  |  | CPVL114 |  |  | UNSPSCL114
1.1.4 | Control and Communication | 32200000 | Transmission apparatus for radiotelephony, radiotelegraphy, radio broadcasting and television | 32200000 Transmission apparatus for radiotelephony, radiotelegraphy, radio broadcasting and television | 30000000 | Structures and Building and Construction and Manufacturing Components and Supplies | 30000000 Structures and Building and Construction and Manufacturing Components and Supplies
|  | 32500000 | Telecommunications equipment and supplies | 32500000 Telecommunications equipment and supplies | 31000000 | Manufacturing Components and Supplies | 31000000 Manufacturing Components and Supplies
|  | 34900000 | Miscellaneous transport equipment and spare parts | 34900000 Miscellaneous transport equipment and spare parts | 39120000 | Electrical equipment and components and supplies | 39120000 Electrical equipment and components and supplies
|  | 35100000 | Emergency and security equipment | 35100000 Emergency and security equipment | 40170000 | Pipe piping and pipe fittings | 40170000 Pipe piping and pipe fittings
|  | 35300000 | Weapons, ammunition and associated parts | 35300000 Weapons, ammunition and associated parts | 41100000 | Laboratory and scientific equipment | 41100000 Laboratory and scientific equipment
|  | 35500000 | Warships and associated parts | 35500000 Warships and associated parts | 41110000 | Measuring and observing and testing instruments | 41110000 Measuring and observing and testing instruments
|  | 38100000 | Navigational and meteorological instruments | 38100000 Navigational and meteorological instruments | 43190000 | Communications Devices and Accessories | 43190000 Communications Devices and Accessories
|  | 38600000 | Optical instruments | 38600000 Optical instruments | 43230000 | Software | 43230000 Software
|  | 44100000 | Construction materials and associated items | 44100000 Construction materials and associated items | 46110000 | Conventional war weapons | 46110000 Conventional war weapons
|  | 44300000 | Cable, wire and related products | 44300000 Cable, wire and related products | 46170000 | Security surveillance and detection | 46170000 Security surveillance and detection
|  | 45200000 | Works for complete or part construction and civil engineering work | 45200000 Works for complete or part construction and civil engineering work | 73150000 | Manufacturing support services | 73150000 Manufacturing support services
|  | 48700000 | Software package utilities | 48700000 Software package utilities | 81100000 | Professional engineering services | 81100000 Professional engineering services
|  | 71300000 | Engineering services | 71300000 Engineering services | 81110000 | Computer services | 81110000 Computer services
|  |  |  | CPVL1141 |  |  | UNSPSCL1141
1.1.4.1 | Control & Communication Integration, Assembly, Test, and Checkout | 35520000 | Parts of war ships | 35520000 Parts of war ships | 30000000 | Structures and Building and Construction and Manufacturing Components and Supplies | 30000000 Structures and Building and Construction and Manufacturing Components and Supplies
|  | 44110000 | Construction materials | 44110000 Construction materials | 31000000 | Manufacturing Components and Supplies | 31000000 Manufacturing Components and Supplies
|  | 44162000 | Piping | 44162000 Piping | 40170000 | Pipe piping and pipe fittings | 40170000 Pipe piping and pipe fittings
|  | 44316400 | Hardware | 44316400 Hardware | 43230000 | Software | 43230000 Software
|  | 45223100 | Assembly of metal structures | 45223100 Assembly of metal structures | 73151501 | Assembly line work | 73151501 Assembly line work
|  | 45223800 | Assembly and erection of prefabricated structures | 45223800 Assembly and erection of prefabricated structures | 73151502 | Joint sealing services | 73151502 Joint sealing services
|  | 45223820 | Prefabricated units and components | 45223820 Prefabricated units and components | 73151503 | Original design and manufacturing service | 73151503 Original design and manufacturing service
|  | 48780000 | System, storage and content management software package | 48780000 System, storage and content management software package | 73151504 | Electronics manufacturing service | 73151504 Electronics manufacturing service
|  | 71310000 | Consultative engineering and construction services | 71310000 Consultative engineering and construction services | 73151505 | Sequenced delivery service | 73151505 Sequenced delivery service
|  | 71320000 | Engineering design services | 71320000 Engineering design services | 73151506 | Final or sub-assembly service | 73151506 Final or sub-assembly service
|  | 71330000 | Miscellaneous engineering services | 71330000 Miscellaneous engineering services | 81101600 | Mechanical engineering | 81101600 Mechanical engineering
|  | 71340000 | Integrated engineering services | 71340000 Integrated engineering services | 81101700 | Electrical and electronic engineering | 81101700 Electrical and electronic engineering
|  | 71350000 | Engineering-related scientific and technical services | 71350000 Engineering-related scientific and technical services | 81110000 | Computer services | 81110000 Computer services
|  |  |  | CPVL1142 |  |  | UNSPSCL1142
1.1.4.2 | Navigation Systems & equipments | 34933000 | Navigation equipment | 34933000 Navigation equipment | 41112900 | Navigational equipment and instruments | 41112900 Navigational equipment and instruments
|  | 38641000 | Periscopes | 38641000 Periscopes | 41111742 | Periscope or protectorscope | 41111742 Periscope or protectorscope
|  |  |  | CPVL1143 |  |  | UNSPSCL1143
1.1.4.3 | Internal Communications | 32500000 | Telecommunications equipment and supplies | 32500000 Telecommunications equipment and supplies | 43191500 | Personal communication devices | 43191500 Personal communication devices
|  |  |  | CPVL1144 |  |  | UNSPSCL1144
1.1.4.4 | Ship and Main Machinery Control Systems |  |  |  | 41111900 | Indicating and recording instruments | 41111900 Indicating and recording instruments | Electronic and electrical spare parts for warships
[5 empty] | 39121100 | Distribution and control centers and accessories | 39121100 Distribution and control centers and accessories
|  |  |  | CPVL1145 |  |  | UNSPSCL1145
1.1.4.5 | Weapons Control Electrics | 35300000 | Weapons, ammunition and associated parts | 35300000 Weapons, ammunition and associated parts | 46111000 | Conventional weapons | 46111000 Conventional weapons
|  |  |  | CPVL1146 |  |  | UNSPSCL1146
1.1.4.6 | Ships Protective Systems
|  |  |  | CPVL1147 |  |  | UNSPSCL1147
1.1.4.7 | External Communication Systems | 32210000 | Broadcasting equipment | 32210000 Broadcasting equipment | 46171600 | Surveillance and detection equipment | 46171600 Surveillance and detection equipment
|  |  |  | CPVL1148 |  |  | UNSPSCL1148
1.1.4.8 | Active / Passive Sonar Systems | 38110000 | Navigational instruments | 38110000 Navigational instruments | 41115200 | Radar and sonar systems and components | 41115200 Radar and sonar systems and components
|  |  |  | CPVL1149 |  |  | UNSPSCL1149
1.1.4.9 | Sensor Systems | 35125000 | Surveillance system | 35125000 Surveillance system | 46171600 | Surveillance and detection equipment | 46171600 Surveillance and detection equipment
[5 empty] | 41111900 | Indicating and recording instruments | 41111900 Indicating and recording instruments
|  |  |  | CPVL115 |  |  | UNSPSCL115
1.1.5 | Ancillary Systems | 31100000 | Electric motors, generators and transformers | 31100000 Electric motors, generators and transformers | 25110000 | Marine transport | 25110000 Marine transport
|  | 33100000 | Medical equipment | 33100000 Medical equipment | 25170000 | Transportation components and systems | 25170000 Transportation components and systems
|  | 34300000 | Parts and accessories for vehicles and their engines | 34300000 Parts and accessories for vehicles and their engines | 26110000 | Batteries and generators and kinetic power transmission | 26110000 Batteries and generators and kinetic power transmission
|  | 35500000 | Warships and associated parts | 35500000 Warships and associated parts | 30000000 | Structures and Building and Construction and Manufacturing Components and Supplies | 30000000 Structures and Building and Construction and Manufacturing Components and Supplies
|  | 39700000 | Domestic appliances | 39700000 Domestic appliances | 31000000 | Manufacturing Components and Supplies | 31000000 Manufacturing Components and Supplies
|  | 42100000 | Machinery for the production and use of mechanical power | 42100000 Machinery for the production and use of mechanical power | 40000000 | Distribution and Conditioning Systems and Equipment and Components | 40000000 Distribution and Conditioning Systems and Equipment and Components
|  | 42500000 | Cooling and ventilation equipment | 42500000 Cooling and ventilation equipment | 42270000 | Respiratory and anesthesia and resuscitation products | 42270000 Respiratory and anesthesia and resuscitation products
|  | 44100000 | Construction materials and associated items | 44100000 Construction materials and associated items | 43230000 | Software | 43230000 Software
|  | 44300000 | Cable, wire and related products | 44300000 Cable, wire and related products | 46180000 | Personal safety and protection | 46180000 Personal safety and protection
|  | 45200000 | Works for complete or part construction and civil engineering work | 45200000 Works for complete or part construction and civil engineering work | 72150000 | Specialized trade construction and maintenance services | 72150000 Specialized trade construction and maintenance services
|  | 45300000 | Building installation work | 45300000 Building installation work | 73150000 | Manufacturing support services | 73150000 Manufacturing support services
|  | 48700000 | Software package utilities | 48700000 Software package utilities | 76120000 | Refuse disposal and treatment | 76120000 Refuse disposal and treatment
|  | 71300000 | Engineering services | 71300000 Engineering services | 81100000 | Professional engineering services | 81100000 Professional engineering services
|  | 90500000 | Refuse and waste related services | 90500000 Refuse and waste related services | 81110000 | Computer services | 81110000 Computer services
|  |  |  | CPVL1151 |  |  | UNSPSCL1151
1.1.5.1 | Ancillary Systems Integration, Assembly, Test, and Checkout | 35520000 | Parts of war ships | 35520000 Parts of war ships | 30000000 | Structures and Building and Construction and Manufacturing Components and Supplies | 30000000 Structures and Building and Construction and Manufacturing Components and Supplies
|  | 44110000 | Construction materials | 44110000 Construction materials | 31000000 | Manufacturing Components and Supplies | 31000000 Manufacturing Components and Supplies
|  | 44162000 | Piping | 44162000 Piping | 40170000 | Pipe piping and pipe fittings | 40170000 Pipe piping and pipe fittings
|  | 44316400 | Hardware | 44316400 Hardware | 43230000 | Software | 43230000 Software
|  | 45223100 | Assembly of metal structures | 45223100 Assembly of metal structures | 73151501 | Assembly line work | 73151501 Assembly line work
|  | 45223800 | Assembly and erection of prefabricated structures | 45223800 Assembly and erection of prefabricated structures | 73151502 | Joint sealing services | 73151502 Joint sealing services
|  | 45223820 | Prefabricated units and components | 45223820 Prefabricated units and components | 73151503 | Original design and manufacturing service | 73151503 Original design and manufacturing service
|  | 48780000 | System, storage and content management software package | 48780000 System, storage and content management software package | 73151504 | Electronics manufacturing service | 73151504 Electronics manufacturing service
|  | 71310000 | Consultative engineering and construction services | 71310000 Consultative engineering and construction services | 73151505 | Sequenced delivery service | 73151505 Sequenced delivery service
|  | 71320000 | Engineering design services | 71320000 Engineering design services | 73151506 | Final or sub-assembly service | 73151506 Final or sub-assembly service
|  | 71330000 | Miscellaneous engineering services | 71330000 Miscellaneous engineering services | 81101600 | Mechanical engineering | 81101600 Mechanical engineering
|  | 71340000 | Integrated engineering services | 71340000 Integrated engineering services | 81101700 | Electrical and electronic engineering | 81101700 Electrical and electronic engineering
|  | 71350000 | Engineering-related scientific and technical services | 71350000 Engineering-related scientific and technical services | 81110000 | Computer services | 81110000 Computer services
|  |  |  | CPVL1152 |  |  | UNSPSCL1152
1.1.5.7 | Aircraft Systems | 42520000 | Ventilation equipment | 42520000 Ventilation equipment
|  | 44160000 | Pipeline, piping, pipes, casing, tubing and related items | 44160000 Pipeline, piping, pipes, casing, tubing and related items
|  | 45331000 | Heating, ventilation and air-conditioning installation work | 45331000 Heating, ventilation and air-conditioning installation work
|  |  |  | CPVL1152N |  |  | UNSPSCL1152
1.1.5.3 | Fuel Systems (Excluding Aircraft Systems) | 44160000 | Pipeline, piping, pipes, casing, tubing and related items | 44160000 Pipeline, piping, pipes, casing, tubing and related items
|  |  |  | CPVL1153N |  |  | UNSPSCL1153N
1.1.5.2 | Air Conditioning, Ventilation, Refrigeration - Systems and Equipment | 39717200 | Air-conditioning appliances | 39717200 Air-conditioning appliances | 40100000 | Heating and ventilation and air circulation | 40100000 Heating and ventilation and air circulation
|  | 42514000 | Machinery and apparatus for filtering or purifying gases | 42514000 Machinery and apparatus for filtering or purifying gases | 40160000 | Industrial filtering and purification | 40160000 Industrial filtering and purification
1.1.5.4 | Air Conditioning Systems | 42512000 | Air-conditioning installations | 42512000 Air-conditioning installations | 40100000 | Heating and ventilation and air circulation | 40100000 Heating and ventilation and air circulation
[5 empty] | 40160000 | Industrial filtering and purification | 40160000 Industrial filtering and purification
|  |  |  | CPVL1155 |  |  | UNSPSCL1155
1.1.5.4 | Sea and Fresh Water Systems | 42120000 | Pumps and compressors | 42120000 Pumps and compressors | 72150000 | Specialized trade construction and maintenance services | 72150000 Specialized trade construction and maintenance services
|  | 45332000 | Plumbing and drain-laying work | 45332000 Plumbing and drain-laying work | 40000000 | Distribution and Conditioning Systems and Equipment and Components | 40000000 Distribution and Conditioning Systems and Equipment and Components
[5 empty] | 30180000 | Plumbing fixtures | 30180000 Plumbing fixtures
|  |  |  | CPVL1156 |  |  | UNSPSCL1156
1.1.5.5 | Air and Gas Systems | 33157000 | Gas-therapy and respiratory devices | 33157000 Gas-therapy and respiratory devices | 42270000 | Respiratory and anesthesia and resuscitation products | 42270000 Respiratory and anesthesia and resuscitation products
[5 empty] | 46182000 | Respiratory protection | 46182000 Respiratory protection
|  |  |  | CPVL1157 |  |  | UNSPSCL1157
1.1.5.9 | Auxiliary Steam, Exhaust Steam and Steam Drain Systems | 31124000 | Steam-turbine generator and related apparatus | 31124000 Steam-turbine generator and related apparatus | 26111608 | Steam generators | 26111608 Steam generators
|  | 42163000 | Steam generators | 42163000 Steam generators | 40151514 | Steam pumps | 40151514 Steam pumps
|  |  |  | CPVL1158 |  |  | UNSPSCL1158
1.1.5.6 | Hydraulic Systems (Excluding Aircraft Systems) | 42121000 | Hydraulic or pneumatic power engines and motors | 42121000 Hydraulic or pneumatic power engines and motors | 25172803 | Marine hydraulic systems | 25172803 Marine hydraulic systems
|  |  |  | CPVL1159 |  |  | UNSPSCL1159
1.1.5.10 see 1.1.2.10 | Lubricating Oil Systems | 34327000 | Steering wheels, columns and boxes | 34327000 Steering wheels, columns and boxes | 25174200 | Steering system | 25174200 Steering system
[5 empty] | 25111938 | Marine steering gear | 25111938 Marine steering gear
|  |  |  | CPVL11510 |  |  | UNSPSCL11510
1.1.5.8 | Waste Disposal Systems | 90510000 | Refuse disposal and treatment | 90510000 Refuse disposal and treatment | 76120000 | Refuse disposal and treatment | 76120000 Refuse disposal and treatment
|  |  |  | CPVL116N |  |  | UNSPSCL116N
1.1.6 | Outfit and Furnishing | 31500000 | Lighting equipment and electric lamps | 31500000 Lighting equipment and electric lamps | 25110000 | Marine transport | 25110000 Marine transport
|  | 35100000 | Emergency and security equipment | 35100000 Emergency and security equipment | 30000000 | Structures and Building and Construction and Manufacturing Components and Supplies | 30000000 Structures and Building and Construction and Manufacturing Components and Supplies
|  | 35500000 | Warships and associated parts | 35500000 Warships and associated parts | 30140000 | Insulation | 30140000 Insulation
|  | 39000000 | Furniture (incl. office furniture), furnishings, domestic appliances (excl. lighting) and cleaning products | 39000000 Furniture (incl. office furniture), furnishings, domestic appliances (excl. lighting) and cleaning products | 30190000 | Construction and maintenance support equipment | 30190000 Construction and maintenance support equipment
|  | 44100000 | Construction materials and associated items | 44100000 Construction materials and associated items | 31000000 | Manufacturing Components and Supplies | 31000000 Manufacturing Components and Supplies
|  | 44300000 | Cable, wire and related products | 44300000 Cable, wire and related products | 40150000 | Industrial pumps and compressors | 40150000 Industrial pumps and compressors
|  | 44400000 | Miscellaneous fabricated products and related items | 44400000 Miscellaneous fabricated products and related items | 40170000 | Pipe piping and pipe fittings | 40170000 Pipe piping and pipe fittings
|  | 45200000 | Works for complete or part construction and civil engineering work | 45200000 Works for complete or part construction and civil engineering work | 41110000 | Measuring and observing and testing instruments | 41110000 Measuring and observing and testing instruments
|  | 45300000 | Building installation work | 45300000 Building installation work | 42270000 | Respiratory and anesthesia and resuscitation products | 42270000 Respiratory and anesthesia and resuscitation products
|  | 45400000 | Building completion work | 45400000 Building completion work | 24100000 | Materials handling machinery and equipment | 24100000 Materials handling machinery and equipment
|  | 48700000 | Software package utilities | 48700000 Software package utilities | 43230000 | Software | 43230000 Software
|  | 63700000 | Support services for land, water and air transport | 63700000 Support services for land, water and air transport | 46190000 | Fire protection | 46190000 Fire protection
|  | 71300000 | Engineering services | 71300000 Engineering services | 47130000 | Cleaning and janitorial supplies | 47130000 Cleaning and janitorial supplies
|  | 42400000 | Lifting and handling equipment and parts | 42400000 Lifting and handling equipment and parts | 55120000 | Signage and accessories | 55120000 Signage and accessories
[5 empty] | 56000000 | Furniture and Furnishings | 56000000 Furniture and Furnishings
[5 empty] | 72150000 | Specialized trade construction and maintenance services | 72150000 Specialized trade construction and maintenance services
[5 empty] | 73150000 | Manufacturing support services | 73150000 Manufacturing support services
[5 empty] | 81100000 | Professional engineering services | 81100000 Professional engineering services
[5 empty] | 81110000 | Computer services | 81110000 Computer services
|  |  |  | CPVL1161 |  |  | UNSPSCL1161
1.1.6.1 | Outfit & Furnishings Integration, Assembly, Test, and Checkout | 35520000 | Parts of war ships | 35520000 Parts of war ships | 30000000 | Structures and Building and Construction and Manufacturing Components and Supplies | 30000000 Structures and Building and Construction and Manufacturing Components and Supplies
|  | 44110000 | Construction materials | 44110000 Construction materials | 31000000 | Manufacturing Components and Supplies | 31000000 Manufacturing Components and Supplies
|  | 44162000 | Piping | 44162000 Piping | 40170000 | Pipe piping and pipe fittings | 40170000 Pipe piping and pipe fittings
|  | 44316400 | Hardware | 44316400 Hardware | 43230000 | Software | 43230000 Software
|  | 45223100 | Assembly of metal structures | 45223100 Assembly of metal structures | 73151501 | Assembly line work | 73151501 Assembly line work
|  | 45223800 | Assembly and erection of prefabricated structures | 45223800 Assembly and erection of prefabricated structures | 73151502 | Joint sealing services | 73151502 Joint sealing services
|  | 45223820 | Prefabricated units and components | 45223820 Prefabricated units and components | 73151503 | Original design and manufacturing service | 73151503 Original design and manufacturing service
|  | 48780000 | System, storage and content management software package | 48780000 System, storage and content management software package | 73151504 | Electronics manufacturing service | 73151504 Electronics manufacturing service
|  | 71310000 | Consultative engineering and construction services | 71310000 Consultative engineering and construction services | 73151505 | Sequenced delivery service | 73151505 Sequenced delivery service
|  | 71320000 | Engineering design services | 71320000 Engineering design services | 73151506 | Final or sub-assembly service | 73151506 Final or sub-assembly service
|  | 71330000 | Miscellaneous engineering services | 71330000 Miscellaneous engineering services | 81101600 | Mechanical engineering | 81101600 Mechanical engineering
|  | 71340000 | Integrated engineering services | 71340000 Integrated engineering services | 81101700 | Electrical and electronic engineering | 81101700 Electrical and electronic engineering
|  | 71350000 | Engineering-related scientific and technical services | 71350000 Engineering-related scientific and technical services | 81110000 | Computer services | 81110000 Computer services
|  |  |  | CPVL1162 |  |  | UNSPSCL1162
1.1.6.3 | Boats and Lifesaving Equipment | 63724000 | Navigation services | 63724000 Navigation services | 25111600 | Safety and rescue water craft | 25111600 Safety and rescue water craft
[5 empty] | 25111520 | Buoy | 25111520 Buoy
[5 empty] | 42272223 | Breathing apparatus accessories or supplies | 42272223 Breathing apparatus accessories or supplies
|  |  |  | CPVL1163N |  |  | UNSPSCL1163N
1.1.6.10 | Portable Fire Fighting, Damage Control, CBRN, and Escape Equipment | 35111000 | Firefighting equipment | 35111000 Firefighting equipment | 40151563 | Fire pump sets | 40151563 Fire pump sets
1.1.6.11 | Load Handling and RAS Equipment | 42414000 | Cranes, mobile lifting frames and works trucks fitted with a crane | 42414000 Cranes, mobile lifting frames and works trucks fitted with a crane | 46190000 | Fire protection | 46190000 Fire protection
|  |  |  | CPVL11611N |  |  | UNSPSCL11611N
|  | 42414000 | Cranes, mobile lifting frames and works trucks fitted with a crane | 42414000 Cranes, mobile lifting frames and works trucks fitted with a crane | 24101600 | Lifting equipment and accessories | 24101600 Lifting equipment and accessories
|  |  |  | CPVL1164 |  |  | UNSPSCL1164
1.1.6.4 see 1.1.1.4 | Minor Bulkheads, Partitions, Deck and Bulkhead Coverings in the Main Hull | 44423000 | Miscellaneous articles | 44423000 Miscellaneous articles | 30191501 | Ladders | 30191501 Ladders
|  | 31523000 | Illuminated signs and nameplates | 31523000 Illuminated signs and nameplates | 41112900 | Navigational equipment and instruments | 41112900 Navigational equipment and instruments
[5 empty] | 55121701 | Metallic nameplates | 55121701 Metallic nameplates
[5 empty] | 55121702 | Non metallic nameplates | 55121702 Non metallic nameplates
|  |  |  | CPVL1165 |  |  | UNSPSCL1165
1.1.6.8 | Equipment for Galleys, Laundries and Workshops | 39000000 | Furniture (incl. office furniture), furnishings, domestic appliances (excl. lighting) and cleaning products | 39000000 Furniture (incl. office furniture), furnishings, domestic appliances (excl. lighting) and cleaning products | 56000000 | Furniture and Furnishings | 56000000 Furniture and Furnishings
|  |  |  | CPVL1166 |  |  | UNSPSCL1166
1.1.6.6 | Furnishings for Living Spaces | 39000000 | Furniture (incl. office furniture), furnishings, domestic appliances (excl. lighting) and cleaning products | 39000000 Furniture (incl. office furniture), furnishings, domestic appliances (excl. lighting) and cleaning products | 56000000 | Furniture and Furnishings | 56000000 Furniture and Furnishings
|  |  |  | CPVL1167 |  |  | UNSPSCL1167
1.1.6.7 | Furnishings for Offices, Medical Spaces | 39000000 | Furniture (incl. office furniture), furnishings, domestic appliances (excl. lighting) and cleaning products | 39000000 Furniture (incl. office furniture), furnishings, domestic appliances (excl. lighting) and cleaning products | 56000000 | Furniture and Furnishings | 56000000 Furniture and Furnishings
|  |  |  | CPVL1168 |  |  | UNSPSCL1168
1.1.6.5 | Furnishings and Fittings in Storerooms and Stowages
|  |  |  | CPVL1169 |  |  | UNSPSCL1169
1.1.6.9 see 1.1.1.4 | Minor Bulkheads, Partitions, Deck and Bulkhead Coverings in the | 45320000 | Insulation work | 45320000 Insulation work | 30140000 | Insulation | 30140000 Insulation
|  |  |  | CPVL11610 |  |  | UNSPSCL11610
1.1.6.2 | General Fittings | 45442000 | Application work of protective coatings | 45442000 Application work of protective coatings | 72151307 | Ship painting service | 72151307 Ship painting service
[5 empty] | 47131802 | Floor finishes or polishes | 47131802 Floor finishes or polishes
|  |  |  | CPVL11611 |  |  | UNSPSCL11611
1.1.6.11 | Water Systems ( Fire Protection) | 44115500 | Sprinkler systems | 44115500 Sprinkler systems | 46191602 | Fire sprinkler systems | 46191602 Fire sprinkler systems
|  |  |  | CPVLL117 |  |  | UNSPSCLL117
1.1.7 | Armament | 35300000 | Weapons, ammunition and associated parts | 35300000 Weapons, ammunition and associated parts | 12130000 | Explosive materials | 12130000 Explosive materials
|  | 35500000 | Warships and associated parts | 35500000 Warships and associated parts | 30000000 | Structures and Building and Construction and Manufacturing Components and Supplies | 30000000 Structures and Building and Construction and Manufacturing Components and Supplies
|  | 35600000 | Military aircrafts, missiles and spacecrafts | 35600000 Military aircrafts, missiles and spacecrafts | 31000000 | Manufacturing Components and Supplies | 31000000 Manufacturing Components and Supplies
|  | 35800000 | Individual and support equipment | 35800000 Individual and support equipment | 40170000 | Pipe piping and pipe fittings | 40170000 Pipe piping and pipe fittings
|  | 39200000 | Furnishing | 39200000 Furnishing | 43230000 | Software | 43230000 Software
|  | 44100000 | Construction materials and associated items | 44100000 Construction materials and associated items | 46120000 | Missiles | 46120000 Missiles
|  | 44300000 | Cable, wire and related products | 44300000 Cable, wire and related products | 46130000 | Rockets and subsystems | 46130000 Rockets and subsystems
|  | 45200000 | Works for complete or part construction and civil engineering work | 45200000 Works for complete or part construction and civil engineering work | 46140000 | Launchers | 46140000 Launchers
|  | 45200000 | Works for complete or part construction and civil engineering work | 45200000 Works for complete or part construction and civil engineering work | 73150000 | Manufacturing support services | 73150000 Manufacturing support services
|  | 48700000 | Software package utilities | 48700000 Software package utilities | 81100000 | Professional engineering services | 81100000 Professional engineering services
|  | 71300000 | Engineering services | 71300000 Engineering services | 81110000 | Computer services | 81110000 Computer services
|  |  |  | CPVLL1171 |  |  | UNSPSCLL1171
1.1.7.1 | Armament Integration, Assembly, Test, and Checkout | 35520000 | Parts of war ships | 35520000 Parts of war ships | 30000000 | Structures and Building and Construction and Manufacturing Components and Supplies | 30000000 Structures and Building and Construction and Manufacturing Components and Supplies
|  | 44110000 | Construction materials | 44110000 Construction materials | 31000000 | Manufacturing Components and Supplies | 31000000 Manufacturing Components and Supplies
|  | 44162000 | Piping | 44162000 Piping | 40170000 | Pipe piping and pipe fittings | 40170000 Pipe piping and pipe fittings
|  | 44316400 | Hardware | 44316400 Hardware | 43230000 | Software | 43230000 Software
|  | 45223100 | Assembly of metal structures | 45223100 Assembly of metal structures | 73151501 | Assembly line work | 73151501 Assembly line work
|  | 45223800 | Assembly and erection of prefabricated structures | 45223800 Assembly and erection of prefabricated structures | 73151502 | Joint sealing services | 73151502 Joint sealing services
|  | 45223820 | Prefabricated units and components | 45223820 Prefabricated units and components | 73151503 | Original design and manufacturing service | 73151503 Original design and manufacturing service
|  | 48780000 | System, storage and content management software package | 48780000 System, storage and content management software package | 73151504 | Electronics manufacturing service | 73151504 Electronics manufacturing service
|  | 71310000 | Consultative engineering and construction services | 71310000 Consultative engineering and construction services | 73151505 | Sequenced delivery service | 73151505 Sequenced delivery service
|  | 71320000 | Engineering design services | 71320000 Engineering design services | 73151506 | Final or sub-assembly service | 73151506 Final or sub-assembly service
|  | 71330000 | Miscellaneous engineering services | 71330000 Miscellaneous engineering services | 81101600 | Mechanical engineering | 81101600 Mechanical engineering
|  | 71340000 | Integrated engineering services | 71340000 Integrated engineering services | 81101700 | Electrical and electronic engineering | 81101700 Electrical and electronic engineering
|  | 71350000 | Engineering-related scientific and technical services | 71350000 Engineering-related scientific and technical services | 81110000 | Computer services | 81110000 Computer services
|  |  |  | CPVL1172N |  |  | UNSPSCL1172N
1.1.7.2 - 1.1.7.7 and 1.1.7.10 | Surface/Air Missile Armament etc | 35342000 | Parts of rocket launchers | 35342000 Parts of rocket launchers | 46140000 | Launchers | 46140000 Launchers
|  |  |  | CPVL1173 |  |  | UNSPSCL1173
1.1.7.8 | Minehunting, Minelaying and Minesweeping Equipment | 35332000 | Ammunition for naval warfare | 35332000 Ammunition for naval warfare
|  |  |  | CPVL1174 |  |  | UNSPSCL1174
1.1.7.4 | Torpedo Stowage's
|  |  |  | CPVL1175 |  |  | UNSPSCL1175
1.1.7.5 | Strategic Weapons Support Systems | 35620000 | Missiles | 35620000 Missiles | 46120000 | Missiles | 46120000 Missiles
|  | 35333200 | Rockets | 35333200 Rockets | 46130000 | Rockets and subsystems | 46130000 Rockets and subsystems
|  | 35332100 | Torpedoes | 35332100 Torpedoes | 46140000 | Launchers | 46140000 Launchers
|  |  |  | CPVL1176 |  |  | UNSPSCL1176
1.1.7.11 | Unmanned Aerial, Surface and Submersible Vehicles (UXVs) Support Systems | 35820000 | Support equipment | 35820000 Support equipment
|  |  |  | CPVL1177 |  |  | UNSPSCL1177
1.1.7.7 | Weapons Support Misc Electrical Distribution Systems
|  |  |  | CPVL1178 |  |  | UNSPSCL1178
1.1.7.8 | Weapons Support Misc Ship Systems
|  |  |  | CPVL1179 |  |  | UNSPSCL1179
1.1.7.9 | Rocket Launchers, Small Arms and Pyrotechnic Stowages and Launchers | 39225500 | Pyrotechnics | 39225500 Pyrotechnics | 12131600 | Pyrotechnics | 12131600 Pyrotechnics
|  |  |  | CPVL11710 |  |  | UNSPSCL11710
1.1.1.7.10 |  |  |  |  | 46101700 | Ammunition handling systems | 46101700 Ammunition handling systems
|  |  |  | CPVL118 |  |  | UNSPSCL118
1.1.8 | Fixed Ballast | 35500000 | Warships and associated parts | 35500000 Warships and associated parts | 25110000 | Marine transport | 25110000 Marine transport
|  | 44100000 | Construction materials and associated items | 44100000 Construction materials and associated items | 30000000 | Structures and Building and Construction and Manufacturing Components and Supplies | 30000000 Structures and Building and Construction and Manufacturing Components and Supplies
|  | 44300000 | Cable, wire and related products | 44300000 Cable, wire and related products | 31000000 | Manufacturing Components and Supplies | 31000000 Manufacturing Components and Supplies
|  | 45200000 | Works for complete or part construction and civil engineering work | 45200000 Works for complete or part construction and civil engineering work | 40170000 | Pipe piping and pipe fittings | 40170000 Pipe piping and pipe fittings
|  | 48700000 | Software package utilities | 48700000 Software package utilities | 43230000 | Software | 43230000 Software
|  | 71300000 | Engineering services | 71300000 Engineering services | 73150000 | Manufacturing support services | 73150000 Manufacturing support services
|  | 71600000 | Technical testing, analysis and consultancy services | 71600000 Technical testing, analysis and consultancy services | 81100000 | Professional engineering services | 81100000 Professional engineering services
|  | 71700000 | Monitoring and control services | 71700000 Monitoring and control services | 81110000 | Computer services | 81110000 Computer services
|  |  |  | CPVL1181 |  |  | UNSPSCL1181
1.1.8.1 | Fixed Ballast Integration, Assembly, Test, and Checkout | 35520000 | Parts of war ships | 35520000 Parts of war ships | 30000000 | Structures and Building and Construction and Manufacturing Components and Supplies | 30000000 Structures and Building and Construction and Manufacturing Components and Supplies
|  | 44110000 | Construction materials | 44110000 Construction materials | 31000000 | Manufacturing Components and Supplies | 31000000 Manufacturing Components and Supplies
|  | 44162000 | Piping | 44162000 Piping | 40170000 | Pipe piping and pipe fittings | 40170000 Pipe piping and pipe fittings
|  | 44316400 | Hardware | 44316400 Hardware | 43230000 | Software | 43230000 Software
|  | 45223100 | Assembly of metal structures | 45223100 Assembly of metal structures | 73151501 | Assembly line work | 73151501 Assembly line work
|  | 45223800 | Assembly and erection of prefabricated structures | 45223800 Assembly and erection of prefabricated structures | 73151502 | Joint sealing services | 73151502 Joint sealing services
|  | 45223820 | Prefabricated units and components | 45223820 Prefabricated units and components | 73151503 | Original design and manufacturing service | 73151503 Original design and manufacturing service
|  | 48780000 | System, storage and content management software package | 48780000 System, storage and content management software package | 73151504 | Electronics manufacturing service | 73151504 Electronics manufacturing service
|  | 71310000 | Consultative engineering and construction services | 71310000 Consultative engineering and construction services | 73151505 | Sequenced delivery service | 73151505 Sequenced delivery service
|  | 71320000 | Engineering design services | 71320000 Engineering design services | 73151506 | Final or sub-assembly service | 73151506 Final or sub-assembly service
|  | 71330000 | Miscellaneous engineering services | 71330000 Miscellaneous engineering services | 81101600 | Mechanical engineering | 81101600 Mechanical engineering
|  | 71340000 | Integrated engineering services | 71340000 Integrated engineering services | 81101700 | Electrical and electronic engineering | 81101700 Electrical and electronic engineering
|  | 71350000 | Engineering-related scientific and technical services | 71350000 Engineering-related scientific and technical services | 81110000 | Computer services | 81110000 Computer services
|  |  |  | CPVL1182 |  |  | UNSPSCL1182
1.1.1.10 | Fixed Ballast | 45234130 | Ballast construction works | 45234130 Ballast construction works | 25111905 | Marine ballast systems | 25111905 Marine ballast systems
|  |  |  | CPVL1183 |  |  | UNSPSCL1183
1.1.8.3 | Special Requirements
|  |  |  | CPVL1184 |  |  | UNSPSCL1184
1.1.8.4 | Shore Testing | 71731000 | Industrial quality control services | 71731000 Industrial quality control services
|  | 71630000 | Technical inspection and testing services | 71630000 Technical inspection and testing services
|  |  |  | CPVL1185 |  |  | UNSPSCL1185
1.1.8.5 | Sundries
|  |  |  | CPVL119 |  |  | UNSPSCL119
1.1.9 | Departmental & General Costs | 34900000 | Miscellaneous transport equipment and spare parts | 34900000 Miscellaneous transport equipment and spare parts
|  |  |  | CPVL1191 |  |  | UNSPSCL1191
1.1.9.1 | Sundry Costs
|  |  |  | CPVL1192 |  |  | UNSPSCL1192
1.1.9.2 | Disbursements
|  |  |  | CPVL1193 |  |  | UNSPSCL1193
1.1.9.3 | Launching & Docking | 34931000 | Harbour equipment | 34931000 Harbour equipment
|  |  |  | CPVL1194 |  |  | UNSPSCL1194
1.1.9.4 | Trials & Special Services
|  |  |  | CPVL1110 |  |  | UNSPSCL1110
1.1.8 | Ship System Software | 48000000 | Software package and information systems | 48000000 Software package and information systems | 43230000 | Software | 43230000 Software
[5 empty] | 81110000 | Computer services | 81110000 Computer services
|  |  |  | CPVL1111 |  |  | UNSPSCLL1111
1.1.9 | Surface Ship Integration, Assembly, Test and Checkout | 35500000 | Warships and associated parts | 35500000 Warships and associated parts | 30000000 | Structures and Building and Construction and Manufacturing Components and Supplies | 30000000 Structures and Building and Construction and Manufacturing Components and Supplies
|  | 44100000 | Construction materials and associated items | 44100000 Construction materials and associated items | 31000000 | Manufacturing Components and Supplies | 31000000 Manufacturing Components and Supplies
|  | 44300000 | Cable, wire and related products | 44300000 Cable, wire and related products | 40170000 | Pipe piping and pipe fittings | 40170000 Pipe piping and pipe fittings
|  | 45200000 | Works for complete or part construction and civil engineering work | 45200000 Works for complete or part construction and civil engineering work | 43230000 | Software | 43230000 Software
|  | 48700000 | Software package utilities | 48700000 Software package utilities | 73150000 | Manufacturing support services | 73150000 Manufacturing support services
|  | 71300000 | Engineering services | 71300000 Engineering services | 81100000 | Professional engineering services | 81100000 Professional engineering services
[5 empty] | 81110000 | Computer services | 81110000 Computer services
|  |  |  | CPVL12 |  |  | UNSPSCL12
1.2 | System Engineering | 71300000 | Engineering services | 71300000 Engineering services | 31300000 | Structural building products | 31300000 Structural building products
[5 empty] | 81100000 | Professional engineering services | 81100000 Professional engineering services
|  |  |  | CPVL13 |  |  | UNSPSCL13
1.3 | Programme Management | 71242000 | Project and design preparation, estimation of costs | 71242000 Project and design preparation, estimation of costs | 80101600 | Project management | 80101600 Project management
|  | 71240000 | Architectural engineering and planning services | 71240000 Architectural engineering and planning services
|  |  |  | CPVL14 |  |  | UNSPSCL14
1.4 | System Test and Evaluation | 73000000 | Research and development services and related consultancy services | 73000000 Research and development services and related consultancy services | 81000000 | Engineering and Research and Technology Based Services | 81000000 Engineering and Research and Technology Based Services
|  |  |  | CPVL141 |  |  | UNSPSCL141
1.4.1 | Development Test and Evaluation | 73400000 | Research and development services on security and defence materials | 73400000 Research and development services on security and defence materials | 81101703 | Engineering testing services | 81101703 Engineering testing services
1.4.2 | Operational Test and Evaluation
1.4.3 | Mock-ups / System Integration Labs (SILs)
1.4.4 | Test and Evaluation Support
1.4.5 | Test Facilities
|  |  |  | CPVL15 |  |  | UNSPSCL15
1.5 | Training | 45000000 | Construction work | 45000000 Construction work | 43000000 | Information Technology Broadcasting and Telecommunications | 43000000 Information Technology Broadcasting and Telecommunications
|  | 48000000 | Software package and information systems | 48000000 Software package and information systems | 46000000 | Defense and Law Enforcement and Security and Safety Equipment and Supplies | 46000000 Defense and Law Enforcement and Security and Safety Equipment and Supplies
|  | 80000000 | Education and training services | 80000000 Education and training services | 86000000 | Education and Training Services | 86000000 Education and Training Services
|  |  |  | CPVL151 |  |  | UNSPSCL151
1.5.1 | Equipment | 48931000 | Training software package | 48931000 Training software package | 43232502 | Computer based training software | 43232502 Computer based training software
[5 empty] | 46200000 | Defense and law enforcement and security and safety training equipment | 46200000 Defense and law enforcement and security and safety training equipment
|  |  |  | CPVL152 |  |  | UNSPSCL152
1.5.2 | Services | 80500000 | Training services | 80500000 Training services | 86100000 | Vocational training | 86100000 Vocational training
|  | 80600000 | Training services in defence and security materials | 80600000 Training services in defence and security materials
|  |  |  | CPVL153 |  |  | UNSPSCL153
1.5.3 | Facilities | 45214800 | Training facilities building | 45214800 Training facilities building
|  |  |  | CPVL16 |  |  | UNSPSCL16
1.6 | Data | 22000000 | Printed matter and related products | 22000000 Printed matter and related products | 55000000 | Published Products | 55000000 Published Products
|  | 72000000 | IT services: consulting, software development, Internet and support | 72000000 IT services: consulting, software development, Internet and support | 81000000 | Engineering and Research and Technology Based Services | 81000000 Engineering and Research and Technology Based Services
|  |  |  | CPVL161 |  |  | UNSPSCL161
1.6.1 | Technical Publications | 22121000 | Technical publications | 22121000 Technical publications | 55101500 | Printed publications | 55101500 Printed publications
[5 empty] | 55111601 | Electronic software documentation or user manuals | 55111601 Electronic software documentation or user manuals
[5 empty] | 81101600 | Mechanical engineering | 81101600 Mechanical engineering
[5 empty] | 81101700 | Electrical and electronic engineering | 81101700 Electrical and electronic engineering
[5 empty] | 81102400 | Electrical power transmission engineering | 81102400 Electrical power transmission engineering
|  |  |  | CPVL162 |  |  | UNSPSCL162
1.6.2 | Engineering Data | 72300000 | Data services | 72300000 Data services | 81100000 | Professional engineering services | 81100000 Professional engineering services
|  |  |  | CPVL163 |  |  | UNSPSCL163
1.6.3 | Management Data |  |  |  |  | Project management?? | Project management??
|  |  |  | CPVL164 |  |  | UNSPSCL164
1.6.4 | Support Data |  |  |  |  | Project management?? | Project management??
|  |  |  | CPVL165 |  |  | UNSPSCL165
1.6.5 | Data Depository |  |  |  |  | Miscellaneous?? | Miscellaneous??
|  |  |  | CPVL17 |  |  | UNSPSCL17
1.7 | Peculiar Support Equipment | 38000000 | Laboratory, optical and precision equipments (excl. glasses) | 38000000 Laboratory, optical and precision equipments (excl. glasses) | 30000000 | Structures and Building and Construction and Manufacturing Components and Supplies | 30000000 Structures and Building and Construction and Manufacturing Components and Supplies
|  | 63000000 | Supporting and auxiliary transport services; travel agencies services | 63000000 Supporting and auxiliary transport services; travel agencies services | 41000000 | Laboratory and Measuring and Observing and Testing Equipment | 41000000 Laboratory and Measuring and Observing and Testing Equipment
|  |  |  | CPVL171 |  |  | UNSPSCL171
1.7.1 | Test and Measurement Equipment | 38500000 | Checking and testing apparatus | 38500000 Checking and testing apparatus | 41110000 | Measuring and observing and testing instruments | 41110000 Measuring and observing and testing instruments
|  |  |  | CPVL172 |  |  | UNSPSCL172
1.7.2 | Support and Handling Equipment | 63700000 | Support services for water transport | 63700000 Support services for water transport | 30190000 | Construction and maintenance support equipment | 30190000 Construction and maintenance support equipment
|  |  |  | CPVL18 |  |  | UNSPSCL18
1.8 | Common Support Equipment
|  |  |  | CPVL181 |  |  | UNSPSCL181
1.8.1 | Test and Measurement Equipment
|  |  |  | CPVL182 |  |  | UNSPSCL182
1.8.2 | Support and Handling Equipment
|  |  |  | CPVL19 |  |  | UNSPSCL19
1.9 | Operational/Site Activation | 35000000 | Security, fire-fighting, police and defence equipment | 35000000 Security, fire-fighting, police and defence equipment | 22000000 | Building and Construction Machinery and Accessories | 22000000 Building and Construction Machinery and Accessories
|  | 42000000 | Industrial machinery | 42000000 Industrial machinery | 30000000 | Structures and Building and Construction and Manufacturing Components and Supplies | 30000000 Structures and Building and Construction and Manufacturing Components and Supplies
|  | 43000000 | Machinery for mining, quarrying, construction equipment | 43000000 Machinery for mining, quarrying, construction equipment | 31000000 | Manufacturing Components and Supplies | 31000000 Manufacturing Components and Supplies
|  | 44000000 | Construction structures and materials; auxiliary products to construction (excepts electric apparatus) | 44000000 Construction structures and materials; auxiliary products to construction (excepts electric apparatus) | 40000000 | Distribution and Conditioning Systems and Equipment and Components | 40000000 Distribution and Conditioning Systems and Equipment and Components
|  | 45000000 | Construction work | 45000000 Construction work | 43000000 | Information Technology Broadcasting and Telecommunications | 43000000 Information Technology Broadcasting and Telecommunications
|  | 48000000 | Software package and information systems | 48000000 Software package and information systems | 72000000 | Building and Facility Construction and Maintenance Services | 72000000 Building and Facility Construction and Maintenance Services
|  | 71000000 | Architectural, construction, engineering and inspection services | 71000000 Architectural, construction, engineering and inspection services | 73000000 | Industrial Production and Manufacturing Services | 73000000 Industrial Production and Manufacturing Services
[5 empty] | 81000000 | Engineering and Research and Technology Based Services | 81000000 Engineering and Research and Technology Based Services
|  |  |  | CPVL191 |  |  | UNSPSCL191
1.9.1 | System Assembly, Installation and Checkout on Site | 35500000 | Warships and associated parts | 35500000 Warships and associated parts | 30000000 | Structures and Building and Construction and Manufacturing Components and Supplies | 30000000 Structures and Building and Construction and Manufacturing Components and Supplies
|  | 44100000 | Construction materials and associated items | 44100000 Construction materials and associated items | 31000000 | Manufacturing Components and Supplies | 31000000 Manufacturing Components and Supplies
|  | 44300000 | Cable, wire and related products | 44300000 Cable, wire and related products | 40170000 | Pipe piping and pipe fittings | 40170000 Pipe piping and pipe fittings
|  | 45200000 | Works for complete or part construction and civil engineering work | 45200000 Works for complete or part construction and civil engineering work | 43230000 | Software | 43230000 Software
|  | 45300000 | Building installation work | 45300000 Building installation work | 43230000 | Software | 43230000 Software
|  | 48700000 | Software package utilities | 48700000 Software package utilities | 73150000 | Manufacturing support services | 73150000 Manufacturing support services
|  | 71300000 | Engineering services | 71300000 Engineering services | 81100000 | Professional engineering services | 81100000 Professional engineering services
[5 empty] | 81110000 | Computer services | 81110000 Computer services
|  |  |  | CPVL192 |  |  | UNSPSCL192
1.9.2 | Contractor Technical Support | 71300000 | Engineering services | 71300000 Engineering services | 72100000 | Building and facility maintenance and repair services | 72100000 Building and facility maintenance and repair services
|  |  |  | CPVL193 |  |  | UNSPSCL193
1.9.3 | Site Construction | 45000000 | Construction work | 45000000 Construction work | 72140000 | Heavy construction services | 72140000 Heavy construction services
|  |  |  | CPVL194 |  |  | UNSPSCL194
1.9.4 | Site/Ship/Vehicle Conversion | 45100000 | Site preparation work | 45100000 Site preparation work | 22100000 | Heavy construction machinery and equipment | 22100000 Heavy construction machinery and equipment
|  |  |  | CPVL195 |  |  | UNSPSCL195
1.9.5 | Sustainment/Interim Contractor Support | 42400000 | Lifting and handling equipment and parts | 42400000 Lifting and handling equipment and parts
|  | 43220000 | Graders and levellers | 43220000 Graders and levellers
|  |  |  | CPVL110 |  |  | UNSPSCL110
1.10 | Industrial Facilities | 42000000 | Industrial machinery | 42000000 Industrial machinery | 22000000 | Building and Construction Machinery and Accessories | 22000000 Building and Construction Machinery and Accessories
|  | 43000000 | Machinery for mining, quarrying, construction equipment | 43000000 Machinery for mining, quarrying, construction equipment | 72000000 | Building and Facility Construction and Maintenance Services | 72000000 Building and Facility Construction and Maintenance Services
|  | 45000000 | Construction work | 45000000 Construction work
|  | 50000000 | Repair and maintenance services | 50000000 Repair and maintenance services
|  |  |  | CPVL1101 |  |  | UNSPSCL1101
1.10.1 | Construction/Conversion/Expansion | 50242000 | Conversion services of ships | 50242000 Conversion services of ships | 72120000 | Nonresidential building construction services | 72120000 Nonresidential building construction services
|  | 45200000 | Works for complete or part construction and civil engineering work | 45200000 Works for complete or part construction and civil engineering work
|  |  |  | CPVL1102 |  |  | UNSPSCL1102
1.10.2 | Equipment Acquisition or Modernization | 50200000 | Repair, maintenance and associated services related to aircraft, railways, roads and marine equipment | 50200000 Repair, maintenance and associated services related to aircraft, railways, roads and marine equipment | 22100000 | Heavy construction machinery and equipment | 22100000 Heavy construction machinery and equipment
|  | 42400000 | Lifting and handling equipment and parts | 42400000 Lifting and handling equipment and parts
|  | 43200000 | Earthmoving and excavating machinery, and associated parts | 43200000 Earthmoving and excavating machinery, and associated parts
|  |  |  | CPVL1103 |  |  | UNSPSCL1103
1.10.3 | Maintenance (Industrial Facilities) | 45200000 | Works for complete or part construction and civil engineering work | 45200000 Works for complete or part construction and civil engineering work | 72100000 | Building and facility maintenance and repair services | 72100000 Building and facility maintenance and repair services
|  |  |  | CPVLL111 |  |  | UNSPSCLL111
1.11 | Initial Spares and Repair Parts | 50240000 | Repair, maintenance and associated services related to marine and other equipment | 50240000 Repair, maintenance and associated services related to marine and other equipment | 31000000 | Manufacturing Components and Supplies | 31000000 Manufacturing Components and Supplies
[5 empty] | 32000000 | Electronic Components and Supplies | 32000000 Electronic Components and Supplies
|  |  |  | CPVLL112 |  |  | UNSPSCLL112
1.12 | Additional Categories Relevant to contracts for; Mid Life Update, Life Extension, Capability Sustainment | 50243000 | Demolition services of ships | 50243000 Demolition services of ships | 72141510 | Demolition services | 72141510 Demolition services
|  |  |  | CPVLL1121 |  |  | UNSPSCLL1121
1.12.1 | Dismantling Costs | 50244000 | Reconditioning services of ships or boats | 50244000 Reconditioning services of ships or boats
|  |  |  | CPVLL1122 |  |  | UNSPSCLL1122
1.12.2 | Emergent Work - Work to bring enduring equipment up to 'entry' level for MLU/CSP/LEP activity | 50200000 | Repair, maintenance and associated services related to aircraft, railways, roads and marine equipment | 50200000 Repair, maintenance and associated services related to aircraft, railways, roads and marine equipment
|  |  |  | CPVLL113 |  |  | UNSPSCLL113
|  |  |  | CPVLL11311 |  |  | UNSPSCLL11311
1.13.1.1 | Depth maintenance activities
|  |  |  | CPVLL11312 |  |  | UNSPSCLL11312
1.13.1.2 | Forward maintenance activities
|  |  |  | CPVLL11313 |  |  | UNSPSCLL11313
1.13.1.3 | Other (Specify, i.e. Forward-Depth Maintenance if carried out by contractor on site)
|  |  |  | CPVLL114 |  |  | UNSPSCLL114
1.14 | Consumables / Fungibles (Contract Specific) | 31000000 | Electrical machinery, apparatus, equipment and consumables; Lighting | 31000000 Electrical machinery, apparatus, equipment and consumables; Lighting | 15100000 | Fuels | 15100000 Fuels
|  | 9100000 | Fuels | 9100000 Fuels | 15130000 | Fuel for nuclear reactors | 15130000 Fuel for nuclear reactors
|  | 44510000 | Tools | 44510000 Tools
|  |  |  | CPVLL115 |  |  | UNSPSCLL115
1.15 | Packing, Handling, Storage and Transportation | 63100000 | Cargo handling and storage services | 63100000 Cargo handling and storage services | 78120000 | Material packing and handling | 78120000 Material packing and handling
|  | 34000000 | Transport equipment and auxiliary products to transportation | 34000000 Transport equipment and auxiliary products to transportation | 78130000 | Storage | 78130000 Storage
|  | 42410000 | Lifting and handling equipment | 42410000 Lifting and handling equipment | 78140000 | Transport services | 78140000 Transport services
|  |  |  | CPVLL116 |  |  | UNSPSCLL116
1.16 | Non Touch Manpower
|  |  |  | CPVLL1161 |  |  | UNSPSCLL1161
1.16.1 | Asset management | 715410000 | Construction project management services | 715410000 Construction project management services
|  | 80000000 | Education and training services | 80000000 Education and training services
|  |  |  | CPVLL11611 |  |  | UNSPSCLL11611
1.16.1.1 | Planning and Optimisation |  |  |  | 81141500 | Quality control | 81141500 Quality control
[5 empty] | 81141700 | Production planning and control | 81141700 Production planning and control
[5 empty] | 81141800 | Facilities management | 81141800 Facilities management
|  |  |  | CPVLL11612 |  |  | UNSPSCLL11612
1.16.1.2 | Inventory Management | 48430000 | Inventory management software package | 48430000 Inventory management software package | 84111507 | Inventory accounting service | 84111507 Inventory accounting service
|  |  |  | CPVLL11613 |  |  | UNSPSCLL11613
1.16.1.3 | Supply Chain Management |  |  |  | 81141600 | Supply chain management | 81141600 Supply chain management
|  |  |  | CPVLL11614 |  |  | UNSPSCLL11614
1.16.1.4 | Procurement Management | 79418000 | Procurement consultancy services | 79418000 Procurement consultancy services | 80101706 | Professional procurement services | 80101706 Professional procurement services
|  |  |  | CPVLL11615 |  |  | UNSPSCLL11615
1.16.1.5 | Other Asset Management item (Please specify)
|  |  |  | CPVLL1162 |  |  | UNSPSCLL1162
1.16.2 | Engineering and Safety | 71336000 | Engineering support services | 71336000 Engineering support services
|  | 71317200 | Health and safety services | 71317200 Health and safety services
|  |  |  | CPVLL11621 |  |  | UNSPSCLL11621
1.16.2.1 | Air/Sea/Road Worthiness - Integrity Assurance |  |  |  | 81111819 | Quality assurance services | 81111819 Quality assurance services
|  |  |  | CPVLL11622 |  |  | UNSPSCLL11622
1.16.2.2 | Specialist Labour |  |  |  | 80101500 | Business and corporate management consultation services | 80101500 Business and corporate management consultation services
|  |  |  | CPVLL11623 |  |  | UNSPSCLL11623
1.16.2.3 | Technical Queries - On Call Support | 79500000 | Office-support services | 79500000 Office-support services | 81111811 | Technical support or help desk services | 81111811 Technical support or help desk services
|  |  |  | CPVLL11624 |  |  | UNSPSCLL11624
1.16.2.4 | Reliability Management | 71700000 | Monitoring and control services | 71700000 Monitoring and control services | 81111819 | Quality assurance services | 81111819 Quality assurance services
|  |  |  | CPVLL11625 |  |  | UNSPSCLL11625
1.16.2.5 | Other Engineering and Safety (Specify)
|  |  |  | CPVLL1163 |  |  | UNSPSCLL1163
1.16.3 | Post design services
|  |  |  | CPVLL11631 |  |  | UNSPSCLL11631
1.16.3.1 | Configuration Management | 72265000 | Software configuration services | 72265000 Software configuration services | 81112200 | Software maintenance and support | 81112200 Software maintenance and support
|  |  |  | CPVLL11632 |  |  | UNSPSCLL11632
1.16.3.2 | Obsolescence Management
|  |  |  | CPVLL11633 |  |  | UNSPSCLL1122
1.16.3.3 | Technical Publications | 22121000 | Technical publications | 22121000 Technical publications | 55101500 | Printed publications | 55101500 Printed publications
|  |  |  | CPVLL11634 |  |  | UNSPSCLL11633
1.16.3.4 | Modifications - Assesment & Design Effort
|  |  |  | CPVLL11635 |  |  | UNSPSCLL11635
1.16.3.5 | Other PDS (Specify)
|  |  |  | CPVLL1164 |  |  | UNSPSCLL1164
1.16.4 | Post design Services (manpower)
|  |  |  | CPVLL11641 |  |  | UNSPSCLL11641
1.16.4.1 | Finance | 79410000 | Business and management consultancy services | 79410000 Business and management consultancy services | 841100 | Accounting and bookkeeping services | 841100 Accounting and bookkeeping services
|  |  |  | CPVLL11642 |  |  | UNSPSCLL11642
1.16.4.2 | Commercial | 22460000 | Trade-advertising material, commercial catalogues and manuals | 22460000 Trade-advertising material, commercial catalogues and manuals | 82100000 | Advertising services | 82100000 Advertising services
|  |  |  | CPVLL11643 |  |  | UNSPSCLL11643
1.16.4.3 | Legal | 79100000 | Legal services | 79100000 Legal services | 94131603 | Legal assistance services | 94131603 Legal assistance services
|  |  |  | CPVLL11644 |  |  | UNSPSCLL11644
1.16.4.4 | Senior Management - Direct to Project or Programme | 79411000 | General management consultancy services | 79411000 General management consultancy services | 80101508 | Business Intelligence conultancy services | 80101508 Business Intelligence conultancy services
|  |  |  | CPVLL11645 |  |  | UNSPSCLL11645
1.16.4.5 | Programme Quality Assurance | 72224000 | Project management consultancy services | 72224000 Project management consultancy services | 80101600 | Project management | 80101600 Project management
|  |  |  | CPVLL11646 |  |  | UNSPSCLL11646
1.16.4.6 | Data Management | 72322000 | Data management services | 72322000 Data management services | 811100 | Computer services | 811100 Computer services
|  |  |  | CPVLL11647 |  |  | UNSPSCLL11647
1.16.4.7 | Security / Insurance | 35120000 | Surveillance and security systems and devices | 35120000 Surveillance and security systems and devices | 461700 | Security surveillance and detection | 461700 Security surveillance and detection
|  | 79710000 | Security services | 79710000 Security services | 841300 | Insurance and retirement services | 841300 Insurance and retirement services
|  | 34928000 | Road furniture | 34928000 Road furniture
|  | 66510000 | Insurance services | 66510000 Insurance services
|  |  |  | CPVLL11648 |  |  | UNSPSCLL11648
1.16.4.8 | Other Contract and Project Management activity (Specify)
|  |  |  | CPVLL1165 |  |  | UNSPSCLL1165
1.16.5 | In service training costs | 80500000 | Training services | 80500000 Training services | 860000 | Educational and training services | 860000 Educational and training services
|  | 80600000 | Training services in defence and security materials | 80600000 Training services in defence and security materials
|  |  |  | CPVLL11651 |  |  | UNSPSCLL11651
1.16.5.1 | Operator or Maintainer Training | 80570000 | Personal development training services | 80570000 Personal development training services | 861018 | In service training and manpower development | 861018 In service training and manpower development
|  |  |  | CPVLL11652 |  |  | UNSPSCLL1122
1.16.5.2 | Project Specific Training | 80510000 | Specialist training services | 80510000 Specialist training services | 80101604 | Project administration or planning | 80101604 Project administration or planning
|  |  |  | CPVLL1166 |  |  | UNSPSCLL11652
1.16.6 | Disposal / Waste Management | 90500000 | Refuse and waste related services | 90500000 Refuse and waste related services | 761200 | Refuse disposal and treatment | 761200 Refuse disposal and treatment
|  | 71800000 | Consulting services for water-supply and waste consultancy | 71800000 Consulting services for water-supply and waste consultancy
|  |  |  | CPVLL1167 |  |  | UNSPSCLL1167
1.16.7 | Other Maintenance Management activity (Specify)
|  |  |  | CPVLL117 |  |  | UNSPSCLL117
1.17 | Specialist equipment | 34000000 | Transport equipment and auxiliary products to transportation | 34000000 Transport equipment and auxiliary products to transportation
|  | 35000000 | Security, fire-fighting, police and defence equipment | 35000000 Security, fire-fighting, police and defence equipment
|  |  |  | CPVLL1171 |  |  | UNSPSCLL1171
1.17.1 | Rigs, Jigs and Support Equipment (all-up) | 34514000 | Floating or submersible drilling or production platforms | 34514000 Floating or submersible drilling or production platforms | 200000 | Mining and Well Drilling Machinery and Accessories | 200000 Mining and Well Drilling Machinery and Accessories
|  | 35800000 | Individual and support equipment | 35800000 Individual and support equipment
|  |  |  | CPVLL11711 |  |  | UNSPSCLL11711
1.17.1.1 | Special To Type Support Equipment
|  |  |  | CPVLL11712 |  |  | UNSPSCLL11712
1.17.1.2 | Common Support Equipment | 35820000 | Support equipment | 35820000 Support equipment | 73150000 | Manufacturing support services | 73150000 Manufacturing support services
|  |  |  | CPVLL1172 |  |  | UNSPSCLL1172
1.17.2 | Testing and diagnostics | 38900000 | Miscellaneous evaluation or testing instruments | 38900000 Miscellaneous evaluation or testing instruments | 811400 | Manufacturing technologies | 811400 Manufacturing technologies
|  | 38400000 | Instruments for checking physical characteristics | 38400000 Instruments for checking physical characteristics
|  |  |  | CPVLL11721 |  |  | UNSPSCLL11721
1.17.2.1 | Special To Type Test Equipment | 33124000 | Diagnostics and radiodiagnostic devices and supplies | 33124000 Diagnostics and radiodiagnostic devices and supplies | 811415 | Quality control | 811415 Quality control
|  | 38430000 | Detection and analysis apparatus | 38430000 Detection and analysis apparatus
|  |  |  | CPVLL11722 |  |  | UNSPSCLL11722
1.17.2.2 | Common Test Equipment | 38970000 | Research, testing and scientific technical simulator | 38970000 Research, testing and scientific technical simulator
|  |  |  | CPVLL1173 |  |  | UNSPSCLL1173
1.17.3 | Specialist facilities | 70300000 | Real estate agency services on a fee or contract basis | 70300000 Real estate agency services on a fee or contract basis | 81141800 | Facilities management | 81141800 Facilities management
|  |  |  | CPVLL11731 |  |  | UNSPSCLL11731
1.17.3.1 | Rent of premises | 70310000 | Building rental or sale services | 70310000 Building rental or sale services | 80131500 | Lease and rental of property or building | 80131500 Lease and rental of property or building
|  |  |  | CPVLL11732 |  |  | UNSPSCLL11732
1.17.3.2 | Major Training Equipment - Simulators & STE (specify) | 80600000 | Training services in defence and security materials | 80600000 Training services in defence and security materials | 251917 | Vehicle servicing equipment | 251917 Vehicle servicing equipment
|  |  |  | CPVLL11733 |  |  | UNSPSCLL11733
1.17.3.3 | Conversion and Expansion
|  |  |  | CPVLL11734 |  |  | UNSPSCLL11734
1.17.3.4 | Maintenance of specialist facilities | 45259000 | Repair and maintenance of plant | 45259000 Repair and maintenance of plant | 72102900 | Facility maintenance and repair services | 72102900 Facility maintenance and repair services
|  |  |  | CPVLL11735 |  |  | UNSPSCLL11735
1.17.3.5 | Other specialist facilities item (Specify)
|  |  |  | CPVLL1174 |  |  | UNSPSCLL1174
1.17.4 | Individual or Small Scale Modifications | 71330000 | Miscellaneous engineering services | 71330000 Miscellaneous engineering services | 80111614 | Temporary engineering services | 80111614 Temporary engineering services
|  |  |  | CPVLL1175 |  |  | UNSPSCLL1175
1.17.5 | Specialist IT | 72000000 | IT services: consulting, software development, Internet and support | 72000000 IT services: consulting, software development, Internet and support | 432100 | Computer Equipment and Accessories | 432100 Computer Equipment and Accessories
|  |  |  | CPVLL11751 |  |  | UNSPSCLL11751
1.17.5.1 | Specialist Software | 72200000 | Software programming and consultancy services | 72200000 Software programming and consultancy services | 81112200 | Software maintenance and support | 81112200 Software maintenance and support
|  | 48100000 | Industry specific software package | 48100000 Industry specific software package | 811120 | Data services | 811120 Data services
|  |  |  | CPVLL11752 |  |  | UNSPSCLL11752
1.17.5.2 | Specialist Hardware | 72100000 | Hardware consultancy services | 72100000 Hardware consultancy services | 811123 | Computer hardware maintenance and support | 811123 Computer hardware maintenance and support
|  | 30210000 | Data-processing machines (hardware) | 30210000 Data-processing machines (hardware)
|  |  |  | CPVLL11753 |  |  | UNSPSCLL11753
1.17.5.3 | Maintenance of specialist IT | 72600000 | Computer support and consultancy services | 72600000 Computer support and consultancy services | 81111812 | Computer hardware maintenance support service | 81111812 Computer hardware maintenance support service
|  |  |  | CPVLL11754 |  |  | UNSPSCLL11754
1.17.5.4 | Other specialist IT equipment (Specify) | 30236000 | Miscellaneous computer equipment | 30236000 Miscellaneous computer equipment
|  |  |  | CPVLL1176 |  |  | UNSPSCLL1176
1.17.6 | Other Specialist Equipment (Specify) | 39300000 | Miscellaneous equipment | 39300000 Miscellaneous equipment | 31162800 | Miscellaneous hardware | 31162800 Miscellaneous hardware